## Fab Project
WBS 152 Central Solenoid Support Structures | 17 | Duration of activity per fiscal year (weeks)

## Engr
WBS 152 Central Solenoid Support Structures
Engineering, Title I, II and III
Description:
This effort covers all Title I, II, and III engineering for the coil support structure, which includes the TF and PF structure, the interface structure between the TF coil structure and the modular coil shell assembly, and the interface structure to the base assembly. The pieces of structure are procured via one or more fixed price contracts. All installation oversight will be performed as part of WBS 7.
Engineering complete

## R&D
WBS 152 Central Solenoid Support Structures
R&D
Description:
No R&D is associated with this WBS

## M&S
Job 1353 - CS Structural Procurement
Materials and Subcontracts (M&S)
Description:
This effort covers manufacturing of the interim central solenoid support structure and integration of the PF1aU&L, with the structure. The pieces of structure are procured via one or more fixed price contracts. This structure is for MIE day-1 operations using the old salvaged PF coils from NSTX. A new structure will be necessary for operations with the baseline PF1,2&3 coils.
Purchased parts:
upper and lower interface hub | 107208 | see notes below
brackets to TF structure | 12800
spacers and tie rods | 25071.5041
subtotal, purchased parts | 145079.5041
outside engr rate = | 130 | $ per hour
outside fab rate = | 92 | $ per hour
outside inspection/technician rate = | 75 | $ per hour
Worksheet:
Center solenoid upperr interface hub
Fabrication / parts costs
Item / description |  |  | Value | Unit | Cost $/unit | No. | Cost $
Center hub Weldment |  |  | 92 | lbs | 28 | 1 | 2576
Upper solenoid hub weldment Assy |  |  | 236 | lbs | 28 | 1 | 6608
Machining of upper hub weldments, 2 setups |  |  | 64 | hrs | 92 | 1 | 5888
Inspection |  |  | 8 | hrs | 75 | 1 | 600
Insulation and shims between weldments |  |  | 1 | interface | 1500 | 12 | 18000
misc bolts and assembly hardware-upper |  |  | 1 | lot | 10000 | 1 | 10000
lower solenoid hub weldment Assy |  |  | 236 | lbs | 28 | 1 | 6608
Machining of lower hub weldments, 2 setups |  |  | 64 | hrs | 92 | 6 | 35328
Inspection |  |  | 8 | hrs | 75 | 6 | 3600
Insulation and shims between castings |  |  | 1 | interface | 1500 | 12 | 18000
misc bolts and assembly hardware-lower |  |  | 1 | lot | 10000 | 1 | 10000
Package & Shipping | [6 empty] | 5000
|  |  |  | subtotal Integrated TF structure fab./matl |  |  | 107208
Material Surcharges 316L - Inconel 625 |  |  | 628 |  | 20 |  | 12560
[5 empty] | Adjusted Total |  | 124768
Brackets to TF structure
Fabrication / parts costs
Item / description |  |  | Value | Unit | Cost $/unit | No. | Cost $
Upper tie plate to TF coil structure |  |  | 500 | lbs | 8 | 1 | 4000
Machining of upper and lower crown segment casting |  |  | 40 | hrs | 92 | 2 | 7360
lower brackets to TF coil structure |  |  | 30 | lbs | 8 | 6 | 1440
machining of lower brackets |  |  | 16 | hrs | 92 | 6 | 8832
|  |  |  | subtotal brackets to TF coil fab./matl |  |  | 12800
Material Surcharges 316L - Inconel 625 |  |  | 516 |  | 20 |  | 10320
[5 empty] | Adjusted Total |  | 23120
Center Solenoid assembly hardware
Item / Description |  |  | Value | Unit | Cost $/unit | No Units | Cost $
1"OD, 96" long Tie Rods |  |  | 90.4779 | lbs | 25 | 6 | 2261.9467
G-10 separation discs & misc. |  |  | 150 | lbs | 20 | 7 | 21000
Material Surcharges 316L - Inconel 625 |  |  | 90.4779 |  | 20 |  | 1809.5574
[6 empty] | Total: | 25071.5041
[5 empty] | JOB 1353 TOTALS: |  | 172959.5041
fy08 $ loaded
243008.1032

## Fab_assy
WBS 152 Central Solenoid Support Structures
In-house Fabrication and Assembly
Description:
No fabrication and assembly is associated with this WBS

## Installation
WBS 152 Central Solenoid Support Structures
Installation
This element is not part of the WBS 1 scope of work