## Fab Project
WBS 162 Coil Leads | [10 empty] | 11 |  | Duration of activity per fiscal year (weeks)
Labor
| Activity Title |  | Manhours | FY2003 $$ | Labor Type | Start Date Month/Yr | End Date Month/Yr | Comments |  |  |  | duration (weeks) | 2002-10-01 | 2003-10-01 | 2004-10-01 | 2005-10-01 | 2006-10-01 | 2007-10-01 | 2008-10-01
Preliminary Design (Title I)
|  | ( 50% of design schedule) | 0 |  | EAEM | 2006-03-22 | 2006-05-03 | PPPL Engineer |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0 |  | 50 | 50% | of design is preliminary design
|  |  | 0 |  | EADM | 2006-03-22 | 2006-05-03 | PPPL Designer |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | 895.2 |  | ORNL Eng | 2006-03-22 | 2006-05-03 | Composite of ORNL Engineer / Designer |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | 20 |  | ORNL Phys. | 2006-03-22 | 2006-05-03 | Composite of ORNL Physics / scientific |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | 0 |  | PPPL Phys. | 2006-03-22 | 2006-05-03 | PPPL Physics/scientific |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
Final Design (Title II)
|  | ( 50% of design schedule) | 0 |  | EAEM | 2006-05-03 | 2006-06-14 | PPPL Engineer |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0 |  | 50 | 50% | of design schedule is final design
|  |  | 0 |  | EADM | 2006-05-03 | 2006-06-14 | PPPL Designer |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | 895.2 |  | ORNL Eng | 2006-05-03 | 2006-06-14 | Composite of ORNL Engineer / Designer |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | 20 |  | ORNL Phys. | 2006-05-03 | 2006-06-14 | Composite of ORNL Physicist |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | 0 |  | PPPL Phys. | 2006-05-03 | 2006-06-14 | PPPL Physics/scientific |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
Lab R&D labor
|  |  | 0 |  | EAEM | 2006-03-22 | 2006-05-03 | PPPL Engineer |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | 0 |  | EADM | 2006-03-22 | 2006-05-03 | PPPL Designer |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | 0 |  | ORNL Eng | 2006-03-22 | 2006-05-03 | Composite of ORNL Engineer / Designer |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | 0 |  | EASM | 2006-03-22 | 2006-05-03 | PPPL monthly support |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | 0 |  | EMTB | 2006-03-22 | 2006-05-03 | PPPL Technician |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
Lab Fab/Assembly/Installation (Title III)
|  |  | 0 |  | EAEM | 2006-06-14 | 2006-11-01 | PPPL Engineer |  |  |  | 20 | 0 | 0 | 0 | 15.5714 | 4.4286 | 0
|  |  | 8 |  | EADM | 2006-06-14 | 2006-11-01 | PPPL Designer |  |  |  | 20 | 0 | 0 | 0 | 15.5714 | 4.4286 | 0
|  |  | 102 |  | ORNL Eng | 2006-06-14 | 2006-11-01 | Composite of ORNL Engineer / Designer |  |  |  | 20 | 0 | 0 | 0 | 15.5714 | 4.4286 | 0
|  |  | 8 |  | EASM | 2006-06-14 | 2006-11-01 | PPPL monthly support |  |  |  | 20 | 0 | 0 | 0 | 15.5714 | 4.4286 | 0
|  |  | 0 |  | EMTB | 2006-06-14 | 2006-11-01 | PPPL Technician |  |  |  | 20 | 0 | 0 | 0 | 15.5714 | 4.4286 | 0
Labor
Manhours per fiscal year by labor category
Level of Effort |  |  |  | FY2003 | FY2004 | FY2005 | FY2006 | FY2007 | FY2008 | TOTAL
| PPPL Engineer |  | EAEM | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 153 | per hour
| PPPL Designer |  | EADM | 0 | 0 | 0 | 6.2286 | 1.7714 | 0 | 8 |  | 800 | 100 | per hour
| Composite of ORNL Engineer / Designer |  | ORNL Eng | 0 | 0 | 0 | 1869.8143 | 22.5857 | 0 | 1892.4 |  | 246012 | 130 | per hour
| PPPL monthly support |  | EASM | 0 | 0 | 0 | 6.2286 | 1.7714 | 0 | 8 |  | 800 | 100 | per hour
| PPPL Technician |  | EMTB | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 73 | per hour
| Composite of ORNL Physics / scientific |  | ORNL Phy | 0 | 0 | 0 | 40 | 0 | 0 | 40 |  | 6400 | 160 | per hour
| PPPL Physics/scientific |  | PPPL Phy | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 141 | per hour
[12 empty] | 16 | 1600 | PPPL
[12 empty] | 1932.4 | 252412 | ORNL
M&S Costs
| Activity Title |  |  | FY2003 $$ |  | Comment
Manufacturing Development (R&D)
|  | Purchased Design Services |  | 0
|  | Procured Hardware/Material |  | 0
|  | Profit at 10% |  | 0
|  | total, manf/dev (R&D) |  | 0 |  | w/o G&A
Procured Hardware/Material
|  | set of cables |  | 0
|  | misc attachment hardware |  | 11541.1226
|  | thermal transition box material |  | 0
|  | materials for in-house fab |  | 0
|  | subtotal, purchased parts |  | 11541.1226
|  | Profit at 10% |  | 0
|  | total, procured hdwe/matl. |  | 11541.1226 |  | w/o G&A
| Purchased Design Services |  |  | 0 |  | no purchased services anticipated
| Procured Installation/Assembly Costs |  |  | 0 |  | All installation and assembly costs are included in WBS 7
Other Costs
| Activity Title |  |  | FY2003 $$ |  | Comment
| Travel |  |  | 0 |  | No travel is anticipated for this WBS
Summary Costs
| Activity Title |  | Manhours | FY2003 $$ |  | Comment
Labor
| PPPL Effort |  | 16 | 1600 |  | Assumed rates: |  | EASM | 100 $/hr
| ORNL effort |  | 1932.4 | 252412 |  | EAEM | 153 $/hr | EMTB | 73 $/hr
|  | subtotal, labor | 1948.4 | 254012 |  | EADM | 100 $/hr | PPPL Phys | 141 $/hr
[6 empty] | ORNL Eng | 130 $/hr | ORNL Phys | 160 $/hr
M&S, Other
| Manufacturing Development (R&D) |  |  | 0
| Procured Hardware/Material |  |  | 11541.1226
| Purchased Design Services |  |  | 0
| Procured Installation/Assembly Costs |  |  | 0
| Travel |  |  | 0
|  | subtotal, M&S |  | 11541.1226
| G&A |  |  | 2885.2806 |  | 25% | on all purchased materials, subcontracts, travel
| Subtotal without contingency |  |  | 268438.4032
| Contingency |  |  | 59056.4487 |  | 22% | Overall on this WBS
| Total cost |  |  | 327494.852

## Engr
WBS 162 Coil Leads
Engineering, Title I, II and III
Description:
This effort covers all Title I, II, and III engineering for the Coil leads. The leads will be procured from a qualified vendor in the correct length for each coil. All installation oversight will be performed as part of WBS 7. |  |  |  |  | Labor category
[5 empty] | total fraction | EAEM |  | EADM |  | ORNL Eng |  | ORNL Physics |  | PPPL Physics
| multiplier | unit | no. | hours |  | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
Title I, II design
Pro-E models | 8 | hrs/model | 50 | 400 | 1 | 0 | 0 | 0 | 0 | 1 | 400 | 0 | 0 | 0 | 0
assy dwgs | 16 | hrs/dwg | 15 | 240 | 1 | 0 | 0 | 0 | 0 | 1 | 240 | 0 | 0 | 0 | 0
Detail drawings | 8 | hrs/dwg | 40 | 320 | 1 | 0 | 0 | 0 | 0 | 1 | 320 | 0 | 0 | 0 | 0
installation dwg | 16 | hrs/dwg | 28 | 448 | 1 | 0 | 0 | 0 | 0 | 1 | 448 | 0 | 0 | 0 | 0
cooling schematic | 0 | hrs/dwg | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
electrical schematic | 8 | hrs/dwg | 14 | 112 | 1 | 0 | 0 | 0 | 0 | 1 | 112 | 0 | 0 | 0 | 0
I&C schematic | 8 | hrs/dwg | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
stress analysis | 0 | hrs/calc | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
thermal analysis | 24 | hrs/calc | 1 | 24 | 1 | 0 | 0 | 0 | 0 | 1 | 24 | 0 | 0 | 0 | 0
special analysis | 40 | hrs/calc | 1 | 40 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 40 | 0 | 0
procurement specifications | 40 | hrs/spec | 1 | 40 | 1 | 0 | 0 | 0 | 0 | 1 | 40 | 0 | 0 | 0 | 0
preliminary and final design reviews | 40 | hrs/rev | 1 | 40 | 1 | 0 | 0 | 0 | 0 | 1 | 40 | 0 | 0 | 0 | 0
meetings/reporting/presentations | 10% | % of tot | 1664 | 166.4 | 1 | 0 | 0 | 0 | 0 | 1 | 166.4 | 0 | 0 | 0 | 0
subtotal |  |  |  | 1830.4 |  |  | 0 |  | 0 |  | 1790.4 |  | 40 |  | 0
[5 empty] | total fraction | EAEM |  | EASM |  | EADM |  | ORNL Eng
Title III | [5 empty] | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
vendor oversight, inspection | 8 | hrs/lot | 1 | 8 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 8
in-house fab/assy oversight and inspection | 2 | hrs/wk | 4 | 8 | 1 | 0 | 0 | 1 | 8 | 0 | 0 | 0 | 0
Disposition of deviation requests and non-conformances | 0.5 | hrs/wk | 20 | 10 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 10
As-built drawings | 1 | hrs/dwg | 84 | 84 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 84
Installation oversight and inspection | 0 | hrs/wk | 4 | 0 | 1 | 0.25 | 0 | 0.75 | 0 | 0 | 0 | 0 | 0
subtotal |  |  |  | 110 |  |  | 0 |  | 8 |  | 0 |  | 102 |  |  |  | 332179.56
Schedule assumptions | start | duration (weeks) | end
Title I Design, R&D | 2006-03-22 | 6 | 2006-05-03
Title II Design | 2006-05-03 | 6 | 2006-06-14
Procurement | 2006-06-14 | 12 | 2006-09-06
In-house fab / sub-assy | 2006-09-06 | 4 | 2006-10-04
Installation / final assembly | 2006-10-04 | 4 | 2006-11-01
Notes and worksheets
PF Coil leads
| total | coils at 10, 70, 130, 190, 250, 310 degrees | coils at 30, 90, 150, 210, 270, 330 degrees | coils at 50, 110, 170, 230, 290, 350 degrees | PF1-2 | PF3 | PF4 | PF5 | PF6 | coils at 0, 120, 240, degrees, top and bottom | coils at 60, 180, 300 degrees Top and bottom | Outer perimeter coils | coil 1 at 10, 70, 130, 190, 250, 310 degrees | coil 2 at 30, 90, 150, 210, 270, 330 degrees | coil 3 at 50, 110, 170, 230, 290, 350 degrees | thermal transition box
Pro-E models | 50 | 6 | 6 | 6 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 2 | 6 | 6 | 6 | 1 | leads modeled to create drawings, reserve space in assembly
assy dwgs | 15 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | one assembly for each circuit
Detail drawings | 40 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | drawings for lead length, mounting details
installation dwg | 29 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | one installation dwg for each cable
cooling schematic | 1 | [15 empty] | one cooling schematic for all leads
electrical schematic | 14 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | one schematic for each circuit
I&C schematic | [16 empty] | part of WBS 163
stress analysis
thermal analysis | 1 | [15 empty] | one analysis to check temp rise, cooling
special analysis | 1 | [15 empty] | one analysis for field error determination
procurement specifications | 1 | [15 empty] | one specification for leads, all carry the same current, will have the same terminations, only the lengths are different
preliminary and final design reviews | 1 | [15 empty] | one review for all coil leads
meetings/reporting/presentations | 10%
Formulas:
multiplier = [no.]-[unit]*7
no. = [multiplier, row below]

## R&D
WBS 162 Coil Leads
R&D
Description:
No R&D is anticipated for this WBS element, but vendor will have non-recurring engineering costs to ensure low temperature capability

## M&S
WBS 162 Coil Leads
Materials and Subcontracts (M&S)
Description:
This effort covers all coil leads that connect the coil terminals to the buswork at the boundary of the cryostat. The lead cables are all the same except for length, and will be procured from a qualified vendor. All installation will be performed as part of WBS 7. The leads exit the cryostat boundary through a thermal transition box that brings leads up to room temperature (or, at a minimum, above the dew point) before exiting to prevent frost build up.
Assumptions:
outside engr rate = | 120 | $ per hour
outside fab rate = | 60 | $ per hour
outside inspection/technician rate = | 80 | $ per hour
TOTAL MATERIAL COST = |  | 109069.7356
Purchased parts:
set of cables | 0
misc attachment hardware | 11541.1226 | @10$/ft
thermal transition box material | 0
subtotal, purchased parts | 11541.1226
Lead bundles consist of six, 250 MCM cable with teflon sleeve. |  | Lead ends are cooled by bleed liquid nitrogen supplied by the coil coolant header (WBS 161)
Leads connect from coil terminals to buswork at bottom of machine.
Each coil is connected separately except PF1 and PF2, which are connected in series within the central solenoid assembly
Purchased materials for in-house fabrication and sub-assembly
None required | 0
subtotal purchased materials | 0
Worksheet, TF Coils:
Lead cost, TF Coils
Terminations,assembly | 200 | ea
Cable with teflon insulation, reinforced teflon outer jacket | 50 | per foot
Total number of cables | 18
Total length of cables | 277.0428
Total cable cost | 17452.1382
Geometry
radius of vertical runs | 12 | ft
height of upper terminals | 11 | ft
height of lower terminals | 7 | ft
Lengths | terminal radius | height from floor | cable length
| (m) | (ft) | (ft)
coils at 10, 130, 250 degrees | 3 | 11 | 12.9199
coils at 70, 190, 310 degrees | 3 | 7 | 8.9199
coils at 30, 150, 270 degrees | 3 | 11 | 16.7596
coils at 90, 210, 330 degrees | 3 | 7 | 12.7596
coils at 50, 170, 290 degrees | 3 | 11 | 22.5192
coils at 110, 230, 350 degrees | 3 | 7 | 18.5192
Subtotals |  |  | 73.8781
Total length | 221.6342 | ft
25% extra for bends, offsets | 55.4086
Total procured length | 277.0428 | ft
Avg length per cable | 15.3913 | ft
Worksheet, PF Coils:
Lead cost, PF Coils
Terminations,assembly | 200 | ea
Cable with teflon insulation, reinforced teflon outer jacket | 50 | per foot
Total number of cables | 10
Total length of cables | 226.085
Total cable cost | 13304.25
Geometry
radius of vertical runs | 10 | ft
height of upper runs | 12 | ft
height of connection to buswork | 0 | ft
Lengths | terminal radius | height from midplane | top length | bottom length
| (m) | (m) | (ft) | (ft)
TF Coils
PF1, PF2, connected in series as assy | 0 | 1.3 | 29.7349 | 14.2651
PF3 | 0 | 1.3 | 29.7349 | 14.2651
PF4 | 0.69 | 1.6 | 28.7507 | 15.2493
PF5 | 2.23 | 1.5 | 14.9213 | 14.9213
PF6 | 2.8 | 1 | 13.2808 | 13.2808
External Trim Coils
Mod Coils
Subtotals |  |  | 116.4226 | 71.9816
Total length | 188.4042 | ft
20% extra for bends, toroidal offsets | 37.6808
Total procured length | 226.085 | ft
Avg length per cable | 22.6085 | ft
Worksheet, Error field correction coil leads:
Lead cost, Error field coils
Terminations,assembly | 200 | ea
Cable with teflon insulation, reinforced teflon outer jacket | 50 | per foot
Total number of cables | 2
Total length of cables | 104.399
Total cable cost | 5619.9483
Geometry
radius of vertical runs | 12 | ft
height of upper terminals | 12 | ft
height of lower terminals | 6 | ft
Lengths | terminal radius | height from floor | cable length
| (m) | (ft) | (ft)
coils at 0 degrees, top and bottom | 3 | 12 | 13.9199
Subtotals |  |  | 13.9199
Total length | 83.5192 | ft
25% extra for bends, offsets | 20.8798
Total procured length | 104.399 | ft
Avg length per cable | 52.1995 | ft
Worksheet, Mod coils:
Lead cost for modular coils
Terminations,assembly | 200 | ea
Cable with teflon insulation, reinforced teflon outer jacket | 50 | per foot
Total number of cables | 36
Total length of cables | 546.5855
Total cable cost | 34529.2764
Geometry
radius of vertical runs | 12 | ft
height of upper terminals | 10 | ft
height of lower terminals | 8 | ft
Lengths | terminal radius | height from floor | cable length
| (m) | (ft) | (ft)
coils at 10, 130, 250 degrees | 3 | 10 | 11.9199
coils at 70, 190, 310 degrees | 3 | 8 | 9.9199
coils at 30, 150, 270 degrees | 3 | 10 | 15.7596
coils at 90, 210, 330 degrees | 3 | 8 | 13.7596
coils at 50, 170, 290 degrees | 3 | 10 | 21.5192
coils at 110, 230, 350 degrees | 3 | 8 | 19.5192
Subtotals |  |  | 72.8781
Total length | 218.6342 | ft
25% extra for bends, offsets | 54.6586
Total procured length | 546.5855 | ft
Avg length per cable | 15.1829 | ft
Worksheet, lead thermal transition box
66 leads, 11 to a box | size
| (in) | number reqd | cost ea | total
sheet material, foil backed insul. foam | 1 x 48 x 96 | 5 | 25 | 125
end seals | 1" tube x 6" | 22 | 20 | 440
cryo epoxy |  | .5 lb | 28.3333 | 14.1667
misc mount hardware, ss base frame |  |  |  | 500
foam caulk | 16 oz | 4 | 4 | 16
acryic sheet window | 3/8" x 12 x 24 | 1 | 62 | 62
assembly | 40 hr each= | 40 | 82 | 3280
|  |  |  | 4437.1667 | each
number required for test floor |  |  |  | 6
|  |  | Total | 26623

## Fab_assy
WBS 162 Coil Leads
In-house Fabrication and Assembly
Description:
No local fab or assembly is anticipated for the Coil leads. Installation is part of WBS 7.

## Installation
WBS 162 Coil Leads
Installation
This element is not part of the WBS 1 scope of work