## Fab Project
WBS 191 Stellarator Core Management and Oversight
Description:
This effort covers general management and oversight for the Stellarator Core. It is assumed to be half time for the duration of the project.
Labor | [10 empty] | R&D labor cost = |  | #REF!
[11 empty] | total R&D costs |  | #REF!
Level of Effort | [5 empty] | FY2007 | FY2008 | FY2009 | TOTAL
| Composite of ORNL Engineer / Designer |  | ORNL Eng | [7 empty] | 0 | 130 | per hour
[6 empty] | 572 | 1144 | 1144 | 2860 |  | 371800
[11 empty] | #REF! | #REF! | PPPL
[11 empty] | #REF! | #REF! | ORNL
M&S Costs | [10 empty] | 2860 | 371800
| Activity Title |  |  | Comment
Manufacturing Development (R&D)
Purchased Design Services
Procured Hardware/Material
|  | Profit |  | profit already included in these items
|  | total, manf/dev (R&D) |  | w/o G&A
Procured Hardware/Material
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
Profit at 10%
|  | total, procured hdwe/matl. |  | w/o G&A
| Purchased Design Services |  |  | no purchased services anticipated
| Procured Installation/Assembly Costs |  |  | All installation and assembly costs are included in WBS 7
Other Costs
| Activity Title |  |  |  |  | FY2007 | FY2008 | FY2009 | TOTAL
| Travel |  |  |  |  | 3000 | 6000 | 6000 | 12000 | assumes one trip every 3 months
| Contingency |  |  | 10% | Overall on this WBS
[6 empty] | 168.7 | 171.9 | 179
[6 empty] | 96496.4 | 196653.6 | 204776 | 497926
509926
Brad at 15% Mike at 40%