## Sheet1
Gettelfinger 4/27/07
| EMEM | EMTB Mech | EMTB Elec | EMSM | EADB | EADM | # units | $/ M&S unit | M&S
WBS 62 Engineering Design and Oversight | 528
WBS-621 LN2-LHe Supply
O2 controller | [6 empty] | 8 | 2000 | 16000
O2 conduit M&S | [6 empty] | 1 | 1000 | 1000 | 4/17/07 - O2 controllers upped to 8
O2 install |  |  | 80 |  | 16 |  |  |  | 0
0
Foam Insulated Line | [8 empty] | 0
1 5/8, 50' roll copper |  | 120 |  |  | 24 |  | 4 | 470 | 1880
2" , 3' insul | [6 empty] | 70 | 22 | 1540
Misc Hdwe | [6 empty] | 1 | 5000 | 5000
pneu vac jacket LN2 valve | [6 empty] | 100 | 120 | 12000 | estimate, 200 ft 1 5/8 annealed with 2" urethane foam insul.
man vac jacket LN2 valve | [6 empty] | 1 | 3300 | 3300
[7 empty] | 1 | 3100 | 3100
0
4/17/07 - NB scope deleted
WBS-622 LN2 Coil Cooling Supply System | [8 empty] | 0
pump(s) | [8 empty] | 0
relief valves |  | 40 |  |  |  |  | 20 | 100 | 2000
pump starters& disconnect |  | 10 |  |  | 40 |  | 20 | 100 | 2000 | ACD 200 gpm, 200 psi ceramic/carbon seal, AC-30 50 HP 2x4x12.5, 3500
piping |  | 80 |  |  |  |  | 1 | 10000 | 10000 | 4/13/07 - 26K requoted for 170 gpm 6 atm. pump. Make it 30K
isolation valves | [6 empty] | 20 | 30 | 600
Relocate pump skid to NCSX machine area |  | 320 | [6 empty] | 0
WBS-623 GN2 Cryostat Cooling System | [8 empty] | 0
duct board200 sf/10 ft | [8 empty] | 0
pneumatic valves | [6 empty] | 2800 | 0.6 | 1680
Circulating Fans | [6 empty] | 20 | 600 | 12000
Evaporator Trays | [6 empty] | 18 | 1000 | 18000
Evaporator Drops | [6 empty] | 18 | 500 | 9000
Thermax Vaporizer | [6 empty] | 18 | 500 | 9000
Thermax starter/controls |  |  |  |  | 40 |  | 1 | 15000 | 15000
duct heater |  |  | 120 |  |  |  | 2 | 4000 | 8000 | 4/17/07 $19 per sheet
heater starter/controls | [6 empty] | 1 | 20000 | 20000
controllers/TCs |  |  | 120 |  | 40 |  | 2 | 4000 | 8000
GN2, Duct, & Insul Labor |  | 1680 |  |  |  |  | 20 | 300 | 6000
Engineering Analysis | 160 | [7 empty] | 0
0
mcmaster 3HT9716kw@$1400ea
| 688 | 2250 | 320 | 0 | 160 | 0 |  | sum=(w/o G&A | 165100
| 164 | 82 | 82 | 135 | 122 | 122 |  |  | 1.44
| 112832 | 184500 | 26240 | 0 | 19520 | 0 |  |  | 237744 | 580836