## Chit Summary
Design Review/QA Audit [Cog Engr/RLM/Chair] | Rvw Date | # | Chit/Audit Finding [Originator] | Review Board Recommendation | Project Disposition | Responsibility | Status | Due Date
VV Weld Joint R&D Plan Peer Review Dudek/Nelson/Heitzenroeder | 2004-03-25 | 1 | Add TC Instrumentation to the back side of the Spool Piece test to monitor the temperature during the weld. | Concur |  | Dudek, Larry | This will be added to the Spool piece at the time of the test. | By 5/19/2005
VV Weld Joint R&D Plan Peer Review Dudek/Nelson/Heitzenroeder | 2004-03-25 | 2 | Perform a visual inspection of the root pass of the welds | Concur |  | Dudek, Larry | This was done on the first test pieces. The parts passed. | Completed
VV Weld Joint R&D Plan Peer Review Dudek/Nelson/Heitzenroeder | 2004-03-25 | 3 | Insulate the backside of the weld with microtherm to determine if there are any burning issues with the insulation during the test | Concur |  | Dudek, Larry | This was done on the test piece. It was determined that there was no effect | Completed
VV Weld Joint R&D Plan Peer Review Dudek/Nelson/Heitzenroeder | 2004-03-25 | 4 | Is there a flux that can be used to make Inconel weld flow better | Concur |  | Dudek, Larry | Still investigating | By 1/31/2005
VV Weld Joint R&D Plan Peer Review Dudek/Nelson/Heitzenroeder | 2004-03-25 | 5 | Anneal pieces before welding to ensure it's in a similar condition to the | Concur |  | Dudek, Larry | This was done on the test pieces. | Completed