## Chits
Design Review/QA Audit [Cog Engr/RLM/Chair] | Rvw Date | # | Chit/Audit Finding [Originator] | Review Board Recommendation | Project Disposition | Responsibility | Status | Due Date
Goranson/Cole/Reiersen Vacuum Vessel Spec.SRD Review | 2004-04-01 | 1 | Location of the inconel-to-stainless transition joint and requirements for diagnostic flexibility need to be captured somewhere. Is it an interface or flowed down from the GRD? [ Neilson] | The location of the transition joint is a design feature, not a requirement. However, the need for a joint to accommodate alternate port extensions is an interface requirement and should be captured in the SRD. | Add port extension interface requirement to 3.1.2.13. Detailed requirements are covered in ICD-121-300-0001 Vacuum Vessel Diagnostic Port Allocation and Orientation. | Reiersen | Complete
Goranson/Cole/Reiersen Vacuum Vessel Spec.SRD Review | 2004-04-01 | 2 | What sets the VV insulation thickness? Is there a reference in the interface section or do you state that the insulation is 1" thick. [ Brown] | Concur | ICD-12-14-3-0001 VV Insulation sets thickness. SRD covers insulation requirements in 3.2.2.1.2. | Reiersen | Complete
Goranson/Cole/Reiersen Vacuum Vessel Spec.SRD Review | 2004-04-01 | 3 | Section 3.2.1.2.1.2 or section 3.2.1.3.2 needs to recognize the GRD requirement to operate with the 250ºC liner (for lithium OP), presumably by operating with the vessel at 250ºC. [Zarnstorff] | Concur | Agreed. | Reiersen | Complete
Goranson/Cole/Reiersen Vacuum Vessel Spec.SRD Review | 2004-04-01 | 4 | Need a metrology requirement requiring that design features be incorporated to enable accurate measurement of the vessel position during assembly and in the assembled state during operation. [Zarnstoff] | Concur | Agreed. Requirement covered in 3.3.1.6. | Reiersen | Complete
Goranson/Cole/Reiersen Vacuum Vessel Spec.SRD Review | 2004-04-01 | 5 | Need to look at consequences of loss of site power, loss of heating/cooling , etc., see any requirements derived from this? [ Reiersen] | Concur | Add statement to 3.2.2.1.3 requiring accommodation of loss of systems. Concerns are addressed in the FMECA. | Reiersen | Complete
Goranson/Cole/Reiersen Vacuum Vessel Spec.SRD Review | 2004-04-01 | 6 | Resolve issue of "what is possible" i.e. horizontal and vertical design loads. [Reiersen] | Concur | VV is being designed to accommodate loads from a 320kA instantaneous plasma disruption which has no net radial or vertical loads | Reiersen | Complete
Goranson/Cole/Reiersen Vacuum Vessel Spec.SRD Review | 2004-04-01 | 7 | Organize 3.13 as a stand-alone section, not along WBS lines. [ Reiersen] | Concur | Done | Reiersen | Complete
Goranson/Cole/Reiersen Vacuum Vessel Spec.SRD Review | 2004-04-01 | 8 | Section 3.3.1.4: NCSX structural & cryogenic design criteria is a draft & almost 2 yrs. old. Valid reference? [Malsbury] | Concur | The design criteria document is under revision control and properly referenced in the SRD. | Reiersen | Complete
Goranson/Cole/Reiersen Vacuum Vessel Spec.SRD Review | 2004-04-01 | 9 | Section 3.3.1.3 b) standards for degreases & cleaning. [Malsbury] | Concur | Add reference that the cleaning procedure is controlled by requirements set forth in the VVSA specification. | Reiersen | Complete
Goranson/Cole/Reiersen Vacuum Vessel Spec.SRD Review | 2004-04-01 | 10 | ( paragraph 2) add all docs ref'd in body of spec. [Malsbury] | Concur | Agreed. | Reiersen | Complete
Goranson/Cole/Reiersen Vacuum Vessel Spec.SRD Review | 2004-04-01 | 11 | Revise GRD to clarify pre-pulse temp. 20-60 ºC following pulse. Uniformities of temp required on VV? [Simmons] | Concur | GRD modified appropriately. SRD is consistent with GRD. | Reiersen | Complete