Applicability

This procedure covers the process for preparing and processing Requests for Deviation (RFDs) on the NCSX Project.

Introduction

As an item approaches either a the start or a step in the manufacturing and/or fabrication process, it is not at all unusual that the organization (either the Project or the supplier) notes an alternative method/material that they believe will fully meet the performance or design requirements as originally specified in the technical documentation (i.e., product specification, models and drawings, and - if used to convey technical information in lieu of a product specification – statements of work.  The documentation to alert the project of this proposed departure from the established performance or design requirements is called a Request for Deviation (RFD).  The RFD is specific written request to depart from a particular requirement(s) of the item’s current approved technical documentation (e.g., specification, SOW – if used to define technical requirements, and models and drawings, etc.).  The RFD must be submitted and granted prior the start of the first manufacturing step that incorporates the proposed deviation. The RFD may be  either a letter or tabular format and shall contain the specific required information as defined in this procedure.  A RFD shall be processed and adjudicated under the ECP process defined in the NCSX Configuration Management Plan (NCSX-PLAN-CMP) and its accompanying NCSX Configuration Control Procedure (NCSX-PROC-002).  Until the RFD is approved, the item may not deviate from the technical requirements.

A deviation is distinguished from non-conformance reports (NCRs) in that NCRs address the departure after-the-fact when the item has been physically made.  The processing of NCRs is addressed in PPPL Quality Assurance Procedure QA-005, “Control of Nonconformances.”

Referenced Documents

| NCSX-PLAN-CMP | NCSX Configuration Management Plan |
| --- | --- |
| NCSX-PROC-002 | NCSX Configuration Control |
| NCSX-PROC-008 | NCSX Procurement Contract Fast Response Process |
| QA-005 | Control of Non-conformances |

ATTACHMENT 1

The RFD may be provided in any format (i.e., letter, tabular, or supplier format), but must contain at a minimum the following information in sufficient detail to permit NCSX Project assessment of the RFD:

- Initiator Name and Organization

- Date RFD was initiated

- RFD Title – short description of the deviation requested

- Severity Level: Major or Minor

  - Major – the RFD with contract and/or technical baseline documentation requirements affecting health, performance, interchageability, survivability, maintainability, effective use or operation, weight, or appearance.

  - Minor – anything not deemed major

- List of impacted documents (e.g., specification and sections, each model and drawing, SOW sections – if the SOW has been used to convey technical information).  Be as specific as possible.

- Impact on cost, schedule, and interfaces with other items – if none so state.  If there are impacts be as specific as possible.

- Full description of the deviation requested, including specific item/part impacted by this RFD and the rationale on why this deviation is needed. Include amplifying information that may assist in the NCSX Project’s assessment of this RFD.

A Sample Form

| NCSX RFD | Number: | RFD Description: |
| --- | --- | --- |
| Initiator: | Organization: | Major : Minor: |
| List of Impacted Documents: |
| Cost Impact: (If none, so state) |
| Schedule Impact: (If none, so state) |
| Impact on Interfaces with Other WBS Elements/Items: |
| Full Description of the Deviation Requested: (Use continuation pages as needed and include amplifying information as appropriate) |

# Text boxes

Page 2

Page 3

RFD information is complete

- Systems Engineering Support Manager

- Posts the dispositioned RFD and ECP on the NCSX Engineering Web page

- Provides unique RFD number per Attachment 1 to this procedure. using the format 
NCSX-DEV-WBS-###-XX where:

  - WBS is the three digit WBS number (e.g., 121, 142, etc.)

  - ### is sequential number of the deviation

  - XX is the revision number of the deviation

- Processes an ECP for the RFD in accordance with the appropriate NCSX configuration control procedure (NCSX-PROC-002 or NCSX-PROC-008).

Note:  If the RFD is initiated by a supplier, the PPPL Procurement Technical Representative and PPPL Subcontract Administrator will be invited to participate in the CCB.

  - PPPL Subcontract Administrator Receives the RFD from the supplier and:

- Notifies the supplier that they are NOT authorized to proceed with the proposed departure until such time that the RFD is approved;

- Ensures that the PPPL Technical Representative has a copy of the RFD; and

- Forwards the RFD to the Systems Engineering Support Manager.

Project

Supplier

- Submits the RFD containing at a minimum the information specified in Attachment 1 to this procedure.  Submits RFD to the Systems Engineering Support Manager.

- Notifies the PPPL Procurement Technical Representative and the respective PPPL Subcontract Administrator of the issue and submits a Request for Deviation (RFD) containing at a minimum the information specified in Attachment 1 to this procedure.

Initiator (Anyone on the Project or a Supplier)

- Identifies an alternative approach, material, etc. with the current contract documentation requirements in one or all of the following:

- Statement of Work (if used to convey technical information in lieu of a product specification);

- Product Specification; or

- Models and drawings

RLM determines how the RFD will be incorporated into the design documentation

11.  Do Nothing (Usually only reserved for prototypes or items that will not be installed on the experiment).

Page 3

9.Revise design documentation to incorporate the RFD

Annotate

Revise

END

10. Annotate design documentation by adding a stamp on the documentation that clearly identifies the RFD.

Page 4

- CCB Chair (or NCSX Engineering Manager if an expedited ECP) approves or disapproves the RFD and associated ECP, notifies the initiator directly if project initiated RFD or PPPL Procurement Technical Representative and PPPL Subcontract Administrator if the RFD is supplier initiated.

Initiator

- Systems Engineering Support Manager Reviews the RFD to ensure that it contains all the necessary information.  If additional information is needed, iterates with:

- The initiator directly if a project initiated RFD;  or

- The PPPL Technical Representative and Procurement Technical Representative if the RFD is supplier initiated.