## Funding analysis
NCSX FUNDING ANALYSIS (MIE FUNDS)
|  | MIE Budget (BA in-hand) | Spent through 9/1/08 | September Forcast | Total Cost Through FY08 | Carryover (FY08 into FY09) | FY09 ETC |  | TOTAL EAC FORECAST | Total Under-run (give back)
| PPPL | 77837000 | 74328891 | 862357 | 75191248 | 2645752 | 1618248 | * | 76809496 | 1027504
| LANL | 420000 | 266500 | 35500 | 302000 | 118000 | 68000 |  | 370000 | 50000
| DCMA | 75000 | 75000 | 0 | 75000 | 0 | 0 |  | 75000 | 0
| ORNL | 11800000 | 11126138 | 77280 | 11203418 | 596582 | 91760 |  | 11295178 | 504822
| TOTAL | 90132000 | 85796529 | 975137 | 86771666 | 3360334 | 1778008 |  | 88549674 | 1582326
* $323,000 for closeout manuscripts/journals to be converted to OPC in accordance with Generally Accepted Accounting Principals and applicable DOE accounting rules.
NCSX Closeout Status
September 1, 2008
Page
[11 empty] | Funding Analysis |  | 2
[11 empty] | Cost Performance Report |  | 3
Staffing
[12 empty] | Summary | 4
[12 empty] | Detail | 5-9
Documentation Closeout (Job 8221)
[12 empty] | Status | 10-11
[12 empty] | Man-hour Tracking | 12
[11 empty] | Resource Loaded Statused Schedule |  | 13-21

## cpr
NCSX Closeout Scope
Cost Performance Through August 2008
WBS | Job | Rev/Date | Status | Job Title | Job Manager | BCWS | BCWP | ACWP | SPI | CPI | BUDGET (Closeout ETC ($K) from 6/1/08) | ETC (or BCWR) | EAC | over / (under) | June Costs ($K) | July Costs ($K) | Aug Costs ($K) | Total Costs ($K) | Remaining Budget ($K) | Variance Analysis
12 - Vacuum Vessel Systems | 1204 |  | COMPLETE | VV System | Viola | 0 | 0 | 4.188 |  | 0 | 0.0001 | 0 | 4.188 | 4.1879 | 4.188 | 0 | 0 | 4.188 | -4.1879
13 - Conventional Coils | 1352 |  | COMPLETE | PF Coil Procurements | Chrzanowski | 93.1 | 93.1 | 97.7 | 1 | 0.95292 | 93.1 | 0 | 97.7 | 4.6 | 0.1 | 97.6 | 0 | 97.7 | -4.6
| 1354 | Rev 4/Mar 3 |  | Trim Coil Design & Procurement | Kalish | 23.8 | 22.2 | 22.536 | 0.93277 | 0.98509 | 24 | 1.8 | 24.336 | 0.336 | 21.5 | 0.686 | 0.35 | 22.536 | 1.464
| 1361 | Rev 5/Mar 3 |  | TF Coil Fabrication | Kalish/Meighan | 144.2 | 138.4 | 142.78 | 0.95978 | 0.96932 | 245 | 106.6 | 249.38 | 4.38 | 41.2 | 44.6 | 56.98 | 142.78 | 102.22
14 - Modular Coils | 1408 | Rev 11/Mar 10 |  | Modular Coil Winding Supplies | Chrzanowski | 20.5 | 18.8 | 9.5 | 0.91707 | 1.9789 | 20.8 | 2 | 11.5 | -9.3 | 0.7 | 6.7 | 2.1 | 9.5 | 11.3
| 1416 | Rev 5/Mar 3 | COMPLETE | Modular Coil Type A&B Design | Cole | 37.4 | 37.4 | 6.005 | 1 | 6.2281 | 37.4 | 0 | 6.005 | -31.395 | 5.581 | 0.424 | 0 | 6.005 | 31.395
| 1421 | Rev 6/Feb 23 | COMPLETE | Modular Coil Interface Design | Cole | 49.8 | 49.8 | 36.623 | 1 | 1.3598 | 49.8 | 0 | 36.623 | -13.177 | -7.25 | 42.752 | 1.121 | 36.623 | 13.177
| 1429 |  | COMPLETE | Mod Coil Interface R&D | Gettelfinger? | 0 | 0.0001 | 1.2 |  | 8.3333e-05 | 0.0001 | 0 | 1.2 | 1.1999 | 1.2 | 0 | 0 | 1.2 | -1.1999
| 1431 | Rev 9/Mar 3 | COMPLETE | Modular Coil Interface Hardware | Dudek | 97 | 97 | 92.1 | 1 | 1.0532 | 97 | 0 | 92.1 | -4.9 | 92.1 |  | 0 | 92.1 | 4.9
| 1451 |  |  | Modular Coil Winding Operations | Chrzanowski | 269.5 | 240 | 288.24 | 0.89054 | 0.83264 | 280 | 40 | 328.24 | 48.24 | 99.7 | 78.6 | 109.94 | 288.24 | -8.24
| 1459 |  |  | Modular Coil Fabr Punch List Items | Chrzanowski | 67.6 | 43.1 | 54.9 | 0.63757 | 0.78506 | 67.6 | 24.5 | 79.4 | 11.8 | 16.8 | 13.5 | 24.6 | 54.9 | 12.7
15 - Coil Support Structures | 1501 | Rev 12a/Mar 20 | COMPLETE | Coil Structures Design | Dahlgren | 73.6 | 74 | 172.499 | 1.0054 | 0.42899 | 74 | 0 | 172.499 | 98.499 | 68.299 | 84.2 | 20 | 172.499 | -98.499 | Re-iterated design based on Trim Coil design and Cryostat Concep. Fault modes and structural models developed which were not planned.
16 - Coil Services | 1601 | Rev 9a/Mar 19 | COMPLETE | LN2 Distribution System | Goranson | 30.2 | 30.2 | 63.582 | 1 | 0.47498 | 30.2 | 0 | 63.582 | 33.382 | 24.429 | 36.332 | 2.821 | 63.582 | -33.382
| 1701 |  | COMPLETE | Cryostat | Raftopoulos | 0 | 0.0001 | 16.2 |  | 6.1728e-06 | 0.0001 | 0 | 16.2 | 16.1999 | 16.2 |  | 0 | 16.2 | -16.1999
17 - Cryostat & Base Support Structure | 1702 | Rev 4a/Mar 20 | COMPLETE | Base Support Structure Design | Dahlgren | 11.7 | 11.7 | 18.7 | 1 | 0.62567 | 11.7 | 0 | 18.7 | 7 | 37.7 | -19 | 0 | 18.7 | -7 |  | July | Aug | remaining
18 - Field Period Assembly | 1802 | Rev 22/Mar 8 |  | FPA Oversight & Support | Viola | 240.8 | 265.771 | 186.471 | 1.1037 | 1.4253 | 355.3 | 89.529 | 276 | -79.3 | 67.572 | 45.039 | 73.86 | 186.471 | 168.829 |  | 271.939 | 244.56 | 230.329
| 1803 & 1805 | Rev 7/Feb 29 | COMPLETE | FPA Tooling Design & Constructability and Procurements | Brown | 108.9 | 114 | 164.6 | 1.0468 | 0.69259 | 114 | 0 | 164.6 | 50.6 | 110.6 | 33.2 | 20.8 | 164.6 | -50.6
| 1806 | Rev 7/Feb 23 | COMPLETE | FPA Specifications & Drawings | Cole | 6 | 6 | 14.539 | 1 | 0.41268 | 6 | 0 | 14.539 | 8.539 | 8.481 | 6.058 | 0 | 14.539 | -8.539
| 1810 |  |  | FPA Operations - Stations 1, 2 & 3 | Viola | 637.7 | 635.173 | 750.5 | 0.99604 | 0.84633 | 812 | 176.827 | 927.327 | 115.327 | 352.9 | 226.9 | 170.7 | 750.5 | 61.5
19 - Stellarator Core Mgmt & Integration | 1901 | Rev 6/Mar 5 |  | Stellarator Core Mgmnt & Integration | Cole | 98.9 | 98.72 | 81.458 | 0.99818 | 1.2119 | 127.4 | 28.68 | 110.138 | -17.262 | 5.62 | 51.907 | 23.931 | 81.458 | 45.942
3 - Diagnostic Systems | 3101 | Rev 8/Mar 1 | COMPLETE | Magnetic Diagnostic Systems | Stratton | 28.2 | 28 | 41.1 | 0.99291 | 0.68127 | 28 | 0 | 41.1 | 13.1 | 31.9 | 9.2 | 0 | 41.1 | -13.1
| 3901 |  | COMPLETE | Diagnostics System Integration | Stratton | 0 | 0.0001 | 7.7 |  | 1.2987e-05 | 0.0001 | 0 | 7.7 | 7.6999 | 2.1 | 5.6 | 0 | 7.7 | -7.6999
4- Power Sys | 4301 |  | COMPLETE | DC Systems | Raki | 0 | 0.0001 | 7.001 |  | 1.4284e-05 | 0.0001 | 0 | 7.001 | 7.0009 | 0.001 | 7 | 0 | 7.001 | -7.0009
| 4401 |  | COMPLETE | Control & Protection | Raki | 0 | 0.0001 | 4.101 |  | 2.4384e-05 | 0.0001 | 0 | 4.101 | 4.1009 | 0.001 | 4.1 | 0 | 4.101 | -4.1009
5- I&C | 5801 |  | COMPLETE | Central I&C Integration | Sichta | 0 | 0.001 | 2.2 |  | 0.00045455 | 0.001 | 0 | 2.2 | 2.199 | 2.2 | 0 | 0 | 2.2 | -2.199
6 - Facility Systems | 6201 |  | COMPLETE | Cryogenic systems | Raftopoulos | 0 | 0.0001 | 43.7 |  | 2.2883e-06 | 0.0001 | 0 | 43.7 | 43.6999 | 31.5 | 12.2 | 0 | 43.7 | -43.6999
7 - Test Cell Preparation and Machine Assy | 7401 |  | COMPLETE | TC Prep 7 Mach Assy Planning | Perry | 0 | 0.0001 | 2.7151 |  | 3.6831e-05 | 0.0001 | 0 | 2.7151 | 2.715 | 2.7 | 0.0001 | 0.015 | 2.7151 | -2.715
81 - Project Management & Integration | 8101 | Rev 14/Mar 21 |  | Project Management @ PPPL | Rej | 257.5 | 260.7 | 168.6 | 1.0124 | 1.5463 | 633 | 372.3 | 540.9 | -92.1 | 93.45 | 77.05 | -1.9 | 168.6 | 464.4
| 8102 |  |  | Project Management @ ORNL | Harris | 76.8 | 76.624 | 29.639 | 0.99771 | 2.5852 | 136.5 | 59.876 | 89.515 | -46.985 | 9.153 | 11.812 | 8.674 | 29.639 | 106.861
| 8998 |  |  | PPPL Direct Allocations | Strykowsky | 108.5 | 108.6 | 91.382 | 1.0009 | 1.1884 | 201.8 | 93.2 | 184.582 | -17.218 | 26.453 | 28.954 | 35.975 | 91.382 | 110.418
82 - Project Engineering | 8202 | Rev 7/Mar 7 |  | Engr Management & Syst Engineering | Heitzenroeder | 143.9 | 171 | 91.448 | 1.1883 | 1.8699 | 362.9 | 191.9 | 283.348 | -79.552 | 40.5 | 29.9 | 21.048 | 91.448 | 271.452
| 8203 | Rev 5/Feb 29 | COMPLETE | Design Integration | Brown | 10.6 | 14.1 | 26.6 | 1.3302 | 0.53008 | 14.1 | 0 | 26.6 | 12.5 | 18.6 | 7.3 | 0.7 | 26.6 | -12.5
| 8204 | Rev 4/Mar 1 |  | Systems Analysis & Tech Assurance | Brooks | 31.7 | 37.4 | 42.108 | 1.1798 | 0.88819 | 42.1 | 4.7 | 46.808 | 4.708 | 29 | 24 | -10.892 | 42.108 | -0.008
| 8205 | Rev 4/Feb 29 |  | Dimensional Control Coordination | Ellis | 29.7 | 30.1 | 22.5 | 1.0135 | 1.3378 | 33.8 | 3.7 | 26.2 | -7.6 | 9.3 | 5.9 | 7.3 | 22.5 | 11.3
| 8210 |  | COMPLETE | Proj Rebaseline Estimate | Reiersen | 0 | 0.0001 | 7.7 |  | 1.2987e-05 | 0.0001 | 0 | 7.7 | 7.6999 | 0.7 | 7 | 0 | 7.7 | -7.6999
| 8220 |  |  | Equipment Disposition & Facility Restorations | Perry | 176.5 | 180.005 | 111.2 | 1.0199 | 1.6187 | 530 | 349.995 | 461.195 | -68.805 | 3.6 | 23.9 | 83.7 | 111.2 | 418.8
| 8221 |  |  | Documentation for Closeout | Heitzenroeder | 550 | 191.8 | 180.72 | 0.34873 | 1.0613 | 1133.6 | 941.8 | 1122.52 | -11.08 | 36.305 | 49.052 | 95.363 | 180.72 | 952.88 | Closeout documentation, analyses, and as-built drawings all behind
| 8222 |  |  | Prepare manuscripts for peer-reviewed archival journals | Neilson | 0 | 6.6 | 9.9 |  | 0.66667 | 300 | 293.4 | 303.3 | 3.3 |  | 1.5 | 8.4 | 9.9 | 290.1
| 8501 |  | COMPLETE | Integrated Test Documetnation | Gentile | 0 | 0.0001 | 0.7001 |  | 0.00014284 | 0.0001 |  | 0.7001 | 0.7 | 0.7 | 0.0001 | 0 | 0.7001 | -0.7
[5 empty] | Subtotal = | 3424.1 | 3080.2949 | 3115.3352 | 0.89959 | 0.98875 | 5861.102 | 2780.807 | 5896.1422 | 35.0402 | 1305.783 | 1053.9662 | 755.586 | 3115.3352 | 2745.7668
[5 empty] | Contingency = | [5 empty] | 1172.2204
[5 empty] | Total = | [5 empty] | 7033.3224

## job 8221 documentation manhour
Close-Out Notes/Backup Analysis Files (Due Dates)
Org | Participant |  | TOTALs (Thru Aug) | ETC | Jobs | [6 empty] | Comments
ORNL | COLE | Planned | 79 |  | 1260 | 1355 | 1416 | 1421 |  |  |  | Include hours to review overall close out report
|  | Actuals | 64 |  | 2008-09-16 | 2008-09-08 | 2008-09-16 | 2008-09-20
ORNL | FOGARTY | Planned | 79 |  | 1421 | [6 empty] | Files received - only need summary
|  | Actuals | 0 |  | 2008-09-15
ORNL | FREUDENBERG | Planned | 280 |  | 1421 | [6 empty] | Only backup ANSYS files/models needed
|  | Actuals | 8 |  | 2008-09-15
ORNL | GORANSON | Planned | 79 |  | 1270 | 161 | 162
|  | Actual | 0 |  | Done | Done | Done
ORNL | HARRIS/HILLIS | Planned | 20 |  | 163 | [6 empty] | Include hours to review overall close out report
|  | Actual | 42 |  | 2008-09-08
ORNL | MMORRIS | Planned | 20
|  | Actual | 0
ORNL | MOON | Planned | 10
|  | Actual | 0
ORNL | NELSON | Planned | 10 | [8 empty] | Include hours to review overall close out report
|  | Actual | 0
ORNL | WILLIAMSON | Planned | 79 |  | 1421 | [6 empty] | Only backup ANSYS files/models needed
|  | Actual | 16 |  | 2008-09-15
PPPL | AVASARALA | Planned | 0
|  | Actual | 0 | 0
PPPL | BLANCHARD | Planned | 41 |  | 1905-10-01 | 2201
|  | Actual | 6 |  | Done | Done
PPPL | BROOKS | Planned | 99 |  | 8204 | [6 empty] | Close out note & backup ANSYS files/models
|  | Actual | 0 |  | 2008-09-30
PPPL | BROWN | Planned | 376 |  | 1830 | 8203
|  | Actual | 0 |  | 2008-10-15 | 2008-10-15
PPPL | CARROL | Planned | 0 |  | 8221
|  | Actual | 0 |  | 2008-10-31 | [6 empty] | Include hours for as-built drawings
PPPL | CHRZANOWSKI | Planned | 168 |  | 1903-07-25 | 1451
|  | Actual | 52 |  | Done | Done
PPPL | DAHLGREN | Planned | 560 |  | 1353 | 1501 | 1702 |  |  |  |  | Close out note & backup ANSYS files/models
|  | Actual | 160 |  | 2008-08-29 | 2008-08-29 | 2008-08-29 |  |  |  |  | Need new dates & ETC
PPPL | DODSON | Planned | 41 |  | 8221 | [6 empty] | Include hours for as-built drawings
|  | Actual | 0 |  | 2008-10-31
PPPL | DUDEK | Planned | 32 |  | 1204 | 1429 | 1431 | 1805 | 6101 | 6301
|  | Actual | 0 |  | Done | Done | Done | Done | Done | Done
PPPL | ELLIS | Planned | 41 |  | 8205 | [6 empty] | Close out note & backup ANSYS files/models
|  | Actual | 0 |  | 2008-09-30
PPPL | FAN | Planned | 160 |  | 8204 | [6 empty] | Only backup ANSYS files/models needed
|  | Actual | 160 |  | 2008-09-19
PPPL | GENTILE | Planned | 20 |  | 8501
|  | Actual | 0 |  | Done
PPPL | HAMPTON | Planned | 100 |  | 8221
|  | Actual | 0 |  | 2008-12-31
PPPL | HEITZENROED | Planned | 160 |  | 8221
|  | Actual | 26 |  | 2008-12-31
PPPL | JUN | Planned | 99
|  | Actual | 0
PPPL | KALISH | Planned | 57 |  | 1361 | 1354 | 6401
|  | Actual | 8 |  | 2008-10-15 | 2008-10-15 | 2008-09-30
PPPL | LABIK | Planned | 41 |  | 3101
|  | Actual | 0 |  | 2008-09-15
PPPL | LANGISH | Planned | 24 |  | 1459
|  | Actual | 0 |  | 2008-09-30
PPPL | MORRIS | Planned | 336 |  | 1354 | 1803 | 1810 | 8221 |  |  |  | Include hours for as-built drawings
|  | Actual | 40 |  | 2008-10-15 | 2008-10-15 | 2008-11-15 | 2008-10-31
PPPL | PERRY | Planned | 16 |  | 7301 | 7401 | 7501 | 7503 | 7601 | 8215 | 8220
|  | Actual | 0 |  | 2008-09-24 | 2008-09-24 | 2008-09-24 | 2008-09-24 | 2008-09-24 | 2008-09-24 | 2008-12-31
PPPL | PRINISKI | Planned | 16 |  | 8205 | [6 empty] | Need backup data files
|  | Actual | 0 |  | 2008-09-30
PPPL | RAFTOPOULOS | Planned | 220 |  | 1701 | 1804 | 6201
|  | Actual | 17 |  | 2008-09-13 | 2008-09-13 | 2008-09-13
PPPL | RAKI | Planned | 160 |  | 4101 | 4301 | 4401 | 4501 |  |  |  | Include designer hours to complete drawings
|  | Actual | 39 |  | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30
PPPL | REIERSEN | Planned | 160 |  | 8221 | [6 empty] | Include hours to review overall close out report
|  | Actual | 0 |  | 2008-11-30
PPPL | RUSHINSKI | Planned | 336 |  | 1354 | 1803 | 1810 | 8221 |  |  |  | Include hours for as-built drawings
|  | Actual | 0 |  | 2008-10-15 | 2008-10-15 | 2008-11-15 | 2008-10-31
PPPL | SICHTA | Planned | 79 |  | 5101 | 5201 | 5301 | 5401 | 5501 | 5601 | 5801
|  | Actual | 0 |  | Done | Done | Done | Done | Done | Done | Done
PPPL | SIMMONS | Planned | 762 |  | 8221
|  | Actual | 304 | 304 | 2008-12-31
PPPL | SMITH | Planned | 16 |  | 8205
|  | Actual | 0 |  | 2008-09-30
PPPL | STRATTON | Planned | 41 |  | 3101 | 3601 | 3801 | 3901
|  | Actual | 0 |  | 2008-09-15 | 2008-09-15 | 2008-09-15 | 2008-09-15
PPPL | STRYKOWSKY | Planned | 160 |  | 8221
|  | Actual | 0 |  | 2008-12-31
PPPL | SUCH | Planned | 200 |  | 8221
|  | Actual | 0 |  | 2008-12-31
PPPL | TYRELL | Planned | 0 |  | 8221
|  | Actual | 100 |  | 2008-12-31
PPPL | UPCAVAGE | Planned | 215 |  | 8221
|  | Actual | 0 |  | 2008-11-30
PPPL | VIOLA | Planned | 158 |  | 1802 | 1810 | 1815 |  |  |  |  | Include hours to update FPA assembly estimate
|  | Actual | 0 |  | 2008-11-15 | 2008-11-15 | 2008-11-15
PPPL | ZHANG | Planned | 160 |  | 8204 | [6 empty] | Only backup ANSYS files/models needed
|  | Actual | 0 |  | 2008-09-30
|  | TOTAL PLAN = | 5710
|  | TOTAL ACTUAL = | 970
|  | TOTAL ETC = | 304
|  | TOTAL EAC = | 1274
|  | TOTAL Delta = | 4436
Responsible Manager |  |  | Personnel that you should provide ETC for:
| Mike Cole |  | Cole, Fogarty, Freudenberg, Goranson, Morris, Moon, Nelson, Williamson
| Jeff Harris |  | Harris
| Art Brooks |  | Brooks, Fan, Zhang
| Tom Brown |  | Brown + ETC for Designers (by name) who will support as-builts
| Bob Elllis |  | Ellis, Priniski, Smith
| Phil Heitzenroeder |  | Heitzenroeder, Tyrrell, Jun, Dahlgren, & Fan (in support of Fred)
| Jim Chrzanowski |  | Langish
| Mike Kalish |  | Kalish+ ETC for Designers (by name) supporting his work
| Brent Stratton |  | Stratton & Labik
| Erik Perry |  | Perry
| Bob Simmons |  | Simmons & Such
| Ron Strykowsky |  | Strykowsky
| Wayne Reiersen |  | Reiersen
| Mike Viola |  | Viola
| Raki Ramakrishnan |  | Raki + any designer hours to complete in-process drawings
| Steve Raftopoulos |  | Raftopoulos

## Sheet2
COST
| JOB |  | etc | cost thru 2/1/08 | April lehman eac | 4/30/03 - 4/30/07 | 5/1/07 - 1/31/08 | 2/1/08 - 4/30/08 | May 08 | TOTAL COST TRHOUGH MAY 2008 |  | may pppl | may ornl
|  |  |  | 0 | 0
11171.9006 | 1201 - Vacuum Vessel Prelim Dsn |  |  | 424.495 | 424.495 | 424.495 |  |  | 0 | 424.495 | 424.495
1202 | 1202 - Vacuum Vessel R&D |  |  | 1770.58 | 1770.58 | 1770.58 |  |  | 0 | 1770.58 | 2195.075
1203 | 1203 - Vacuum Vessel Final Dsn |  |  | 1217.343 | 1217.343 | 1217.343 |  |  | 0 | 1217.343 | 3412.418
1204 | Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 220.6 | 777.4519 | 998.0519 | 535.641 | 241.8109 | 76.9327 | 13.75 | 868.1346 | 4280.5526 | 13.75
1206 | 1206 - VV Field Weld Joint R&D |  |  | 15.954 | 15.954 | 15.954 |  |  | 0 | 15.954 | 4296.5066
1250 | Job: 1250 - Vacuum Vessel Fabrication**CLOSED** |  |  | 5537.0867 | 5537.0867 | 5788.857 | -251.7703 | 0 | 0 | 5537.0867 | 9833.5933
| Job: 1260 NB Transition Ducts- COLE | Job: 1260 NB Transition Ducts- COLE | 566.73 | 0 | 566.73 |  |  | 0 | 4.48 | 4.48 | 9838.0733 |  | 4.48
| Job: 1270 - Heater Control System-PPPL ( tbd) | Job: 1270 - Heater Control System-PPPL ( tbd) | 641.66 | 0 | 641.66 |  |  | 0 | 0 | 0 | 9838.0733
8085.8745 | 1301 - TF Design |  |  | 970.154 | 957.154 | 970.154 |  |  | 0 | 970.154 | 10808.2273
| Job: 1302 - PF Design -KALISH | Job: 1302 - PF Design -CHRZANOWSKI | 90.9 | 96.371 | 187.271 | 19.338 | 77.033 | 31.9119 | 0 | 128.2829 | 10936.5101
| 1303 - Central Solenoid Support Design |  |  | 154.795 | 154.795 | 154.795 |  |  | 0 | 154.795 | 11091.3051
| 1350 - TF Coil Fabr Prep |  |  | 535.879 | 535.879 | 535.879 |  |  | 0 | 535.879 | 11627.1841
| 1351 - TF Coil Fabr Supplies |  |  | 482.959 | 482.959 | 482.959 |  |  | 0 | 482.959 | 12110.1431
| Job: 1352 - PF Coil Procurement-KALISH | Job: 1352 - PF Coil Procurement-CHRZANOWSKI | 1637.64 | 7.832 | 1645.472 |  | 7.832 | 58.2171 | 13.735 | 79.7841 | 12189.9273 | 13.735
| Job: 1353 - CS Structure Procurement-DAHLGREN | Job: 1353 - CS Structure Procurement-PERRY | 357.38 | 0 | 357.38 |  | 0 | 0 | 0 | 0 | 12189.9273
| Job: 1354 - Trim Coil Design &Procurement-KALISH | Job: 1354 - Trim Coil Design &Procurement-KALISH | 1433.01 | 49.246 | 1482.256 | 0 | 49.246 | 112.2541 | 39.941 | 201.4411 | 12391.3684 | 39.941
| Job: 1355 - WBS 13 I&C Proc and Coil Assy-KALISH | Job: 1355 - WBS 13 I&C Proc and Coil Assy-COLE | 109.96 | 0 | 109.96 | 0 | 0 | 0.883 | 0 | 0.883 | 12392.2514
| Job: 1361 - TF Fabrication-KALISH | Job: 1361 - TF Fabrication-KALISH | 627.6 | 1545.1485 | 2172.7485 | 1073.601 | 471.5475 | 224.13 | 95.854 | 1865.1325 | 14257.3839 | 95.854
40735.1178 | 1401 - Mod Coil Prel.Dsn |  |  | 304.356 | 304.356 | 304.356 |  |  | 0 | 304.356 | 14561.7399
| 1402 - Mod.Coil Analyses |  |  | 239.14 | 239.14 | 239.14 |  |  | 0 | 239.14 | 14800.8799
| 1404 -MCWF R&D & 1st Prod Casting |  |  | 2519.2016 | 2519.2016 | 2554.149 | -34.9474 | 0 | 0 | 2519.2016 | 17320.0815
| 1405 -Mod Coil Winding R&D Prep |  |  | 168 | 168 | 168 |  |  | 0 | 168 | 17488.0815
| 1406 - Mod. Coil Winding Facility |  |  | 2263.137 | 2263.137 | 2263.137 |  |  | 0 | 2263.137 | 19751.2185
| 1407 -Mod Coil Winding Facility |  |  | 2569.776 | 2569.776 | 2569.776 |  |  | 0 | 2569.776 | 22320.9945
| 1408 -Mod Coil Winding Supplies | Job: 1408 - MC Winding Supplies-CHRZANOWSKI | 123.92 | 2497.7554 | 2621.6754 | 2353.142 | 144.6134 | 86.7329 | 77.685 | 2662.1733 | 24983.1678 | 77.685
| 1409 - Mod. Coil Test Stand |  |  | 832.579 | 832.579 | 832.579 |  |  | 0 | 832.579 | 25815.7468
| 1410 MC Twisted Racetrack Fabr |  |  | 1049.608 | 1049.608 | 1049.608 |  |  | 0 | 1049.608 | 26865.3548
| 1411-MCWF Fabrication S005242 |  |  | 9900.5744 | 9845.5744 | 9965.687 | -65.1126 | 0 | 0 | 9900.5744 | 36765.9292
| 1412 - Complete Winding Facilities |  |  | 540.732 | 540.732 | 540.732 |  |  | 0 | 540.732 | 37306.6612
| 1413 - Mod Coil Fracture Analysis |  |  | 27.819 | 27.819 | 27.819 |  |  | 0 | 27.819 | 37334.4802
| 1414 - Coil Testing |  |  | 638.674 | 638.674 | 638.674 |  |  | 0 | 638.674 | 37973.1542
| 1415 - Dimensional Control Testing |  |  | 24.038 | 24.038 | 24.038 |  |  | 0 | 24.038 | 37997.1922
| 1416 Mod Coil Design Job 1403, 1416 Coil Design, Job 1421 Interface design | Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | 140.35 | 4602.9249 | 4743.2749 | 4418.659 | 184.2659 | 74.41 | 9.941 | 4687.2759 | 42684.468 |  | 9.941
| 1419 - Winding Facility Modification |  |  | 48.434 | 48.434 | 48.434 |  |  | 0 | 48.434 | 42732.902
| Job: 1421 - Mod Coil Interface Design-WILLIAMSON | Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 28.17 | 1062.0957 | 1090.2657 |  | 1062.0957 | 356.74 | 32.173 | 1451.0087 | 44183.9108 | 2.303 | 29.87
| 1429 Interface R&D/Test | Job: 1429 - MC Interface R&D-DUDEK | 4.42 | 245.6132 | 250.0332 | 157.99 | 87.6232 | 20.0875 | 1.856 | 267.5568 | 44451.4675 | 1.856
| Job: 1431 - Mod. Coil Interface Hardware-DUDEK | Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 1074.03 | 471.1149 | 1545.1449 |  | 471.1149 | 152.8294 | 2.088 | 626.0323 | 45077.4998 | 2.088
| 1451 - Mod Coil Winding (incl 1459 punch list and unplanned work) | Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 909.14 | 7736.7827 | 8645.9227 | 6042.318 | 1694.4647 | 545.7396 | 176.56 | 8459.0823 | 53536.5822 | 155.525 | 21.035
| 1459 | Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI | 282.75 | 427.645 | 710.395 |  | 427.645 | 91.8773 | 21.147 | 540.6693 | 54077.2515 | 21.147
| 1460 - 3rd Winding Fixture |  |  | 57.337 | 57.337 | 57.337 |  |  | 0 | 57.337 | 54134.5885
2077.5351 | 1501 - Structures Design | Job: 1501 - Coil Structures Design-DAHLGREN | 88.98 | 545.5041 | 634.4841 | 335.94 | 209.5641 | 65.2431 | 24.474 | 635.2212 | 54769.8096 | 24.474
| 1550 - Structures Procurement | Job: 1550 - Coil Struct. Procurement -PERRY | 1438.99 | 4.061 | 1443.051 | 4.061 | 0 | 17.1514 | 0 | 21.2124 | 54791.0221
| 1601 - Coil Services | Job: 1601 - Coil Services Design-GORANSON | 1084.66 | 2.614 | 1088.274 | 2.614 | 0 | 37.284 | 29.064 | 68.962 | 54859.9841 |  | 29.064
1985.7952 | 1701 -Cryostat design | Job: 1701 - Cryostat Design-RAFTOPOLOUS | 577.63 | 436.3062 | 1013.9362 | 431.073 | 5.2332 | 38.3323 | 28.892 | 503.5305 | 55363.5146 | 28.892
| 1702 -Base Support structure design | Job: 1702 - Base Support Struct Design-DAHLGREN | 139.34 | 52.979 | 192.319 | 0 | 52.979 | 86.5116 | 26.542 | 166.0326 | 55529.5472 | 26.542
| 1751 - Cryostat Procurement | Job: 1751 - Cryostat Procurement-RAFTOPOLOUS | 549.98 | 0 | 549.98 |  | 0 | 0 | 0 | 0 | 55529.5472
| 1752 - Base Support Structure Procurement | Job: 1752 - Base Support Proc-PERRY | 229.56 | 0 | 229.56 | 0 | 0 | 0 | 0 | 0 | 55529.5472
19951.8137 | 1801 -Field Period Assy |  |  | 64.38 | 64.38 | 64.38 |  |  | 0 | 64.38 | 55593.9272
| 1802 - FP Assy Oversight Support | Job: 1802 - FP Assy Oversight&Support-VIOLA | 3825.83 | 1517.4037 | 5311.2337 | 997.703 | 519.7007 | 205.736 | 86.3 | 1809.4397 | 57403.3669 | 68.937 | 17.363
| Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 993.97 | 1432.0419 | 2426.0119 | 1149.138 | 282.9039 | 206.7543 | 96.318 | 1735.1141 | 59138.481 | 96.318
| 1804-FP Assy Measurement |  |  | 558.937 | 558.937 | 558.937 |  |  | 0 | 558.937 | 59697.418
| 1806 - FP Assy Specs and Drawings | Job: 1806 - FP Assembly specs | 360.36 | 32.939 | 393.299 | 26.517 | 6.422 | 33.541 | 0 | 66.48 | 59763.898
| 1810 - Field Period Assembly plus 1859 unplanned work | Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | 7343.14 | 1966.5021 | 9309.6421 | 704.632 | 1261.8701 | 705.4328 | 457.543 | 3129.4779 | 62893.376 | 457.543
| Job: 1815 - Field Period Assy | Job: 1815 - Field Period Assy | 1888.31 | 0 | 1888.31 |  | 0 | 0 | 0 | 0 | 62893.376
4572.445 | 1901 - Stellarator Core Mngt & Integr | Job: 1901 - Stellarator Core Mngtt&Integr-COLE | 2255.15 | 2317.295 | 4572.445 | 2128.336 | 188.959 | 127.46 | 63.325 | 2508.08 | 65401.456 |  | 63.325
1366.429 | 2001-VPS Gas& Cond Sys Oversight |  |  | 62.893 | 62.893 | 62.893 |  |  | 0 | 62.893 | 65464.349
| 2101 - Fueling Systems | Job: 2101 - Fueling Systems-BLANCHARD | 338.23 | 0 | 338.23 | 0 | 0 | 0 | 0 | 0 | 65464.349
| 2201 - Torus Vacuum Pumping Systems | Job: 2201 - Vacuum Pumping Systems-BLANCHARD | 679.36 | 0 | 679.36 | 0 | 0 | 0 | 0 | 0 | 65464.349
| 2501 - Neutral Beam Refurbishment |  |  | 284.946 | 285.946 | 284.946 |  |  | 0 | 284.946 | 65749.295
1941.9538 | 3101 Magnetic Diagnostics | Job: 3101 - Magnetic Diagnostics-STRATTON | 411.26 | 756.0796 | 1165.3396 | 614.023 | 142.0566 | 50.4813 | 44.581 | 851.1419 | 66600.4369 | 44.581
| 3601 - Edge and Divertor Diagnostics | Job: 3601 - Edge Divertor Diagnostics-STRATTON | 30.12 | 0 | 30.12 | 0 | 0 | 0 | 0 | 0 | 66600.4369
| 3801 - Electron Beam (EB) Mapping | Job: 3801 - Electron Beam Mapping-FOGARTY | 258.06 | 0 | 258.06 | 0 | 0 | 0 | 0 | 0 | 66600.4369
| 3901 - Diagnostics sys Integration | Job: 3901 - Diagnostics sys Integration-STRATTON | 111.52 | 376.9142 | 488.4342 | 342.506 | 34.4082 | 30.2534 | 4.214 | 411.3816 | 67011.8185 | 4.214
3333.6615 | 4101 - AC Power | Job: 4101 - AC Power-RAMAKRISHNAN | 154.3 | 3.2483 | 157.5483 | 107.351 | -104.1027 | 0 | 0 | 3.2483 | 67015.0668
| 4301 - DC Systems | Job: 4301 - DC Systems-RAMAKRISHNAN | 579.14 | 369.762 | 948.902 | 369.762 | 0 | 20.5037 | 2.755 | 393.0206 | 67408.0875 | 2.755
| 4401 - Control & Protection | Job: 4401 - Control & Protection-RAMAKRISHNAN | 1079.99 | 80.521 | 1160.511 | 80.521 | 0 | 5.5105 | 2.066 | 88.0975 | 67496.185 | 2.066
| 4501 - Power Sys Dsn & Integr | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 904.9 | 160.5002 | 1065.4002 | 161.056 | -0.55581 | 0 | 0 | 160.5002 | 67656.6852
| 4601 - FCPC Bldg Mods |  |  | 1.3 | 1.3 | 1.3 |  |  | 0 | 1.3 | 67657.9852
2131.522 | 5101- TCP/IP Infrastructure Systems | Job: 5101 - Network and Fiber | 221.35 | 0 | 221.35 | 0 | 0 | 0 | 0 | 0 | 67657.9852
| 5201 - Central Instrumentation & Control | Job: 5201 - I&C Systems-SICHTA | 411.62 | 0 | 411.62 | 0 | 0 | 0 | 0 | 0 | 67657.9852
| 5301 - Data Acquisition & Fac Computing | Job: 5301 - Data Acquisition-SICHTA | 166.41 | 0 | 166.41 | 0 | 0 | 0 | 0 | 0 | 67657.9852
| 5401 - Facility Timing & Synchronization | Job: 5401 - Facility Timing & | 358.31 | 0 | 358.31 | 0 | 0 | 0 | 0 | 0 | 67657.9852
| 5501 - Real Time Plasma & Power Supply Ctrl | Job: 5501 - Real Time Control | 501.86 | 0 | 501.86 | 0 | 0 | 0 | 0 | 0 | 67657.9852
| 5601 - Central Safety Interlock Systems | Job: 5601 - Central Safety &Interlock Sys-SICHTA | 372.41 | 0 | 372.41 | 0 | 0 | 0 | 0 | 0 | 67657.9852
| 5801 -Central I&C Integr | Job: 5801 - Central I&C Integr& Oversight-SICHTA | 66.54 | 33.022 | 99.562 | 33.022 | 0 | 11.2196 | 3.926 | 48.1676 | 67706.1528 | 3.926
2447.433 | 6101 - Water Systems | Job: 6101 - Water Systems-DUDEK | 112.25 | 14.873 | 127.123 | 14.873 | 0 | 0 | 0 | 14.873 | 67721.0258
| 6201 - Cryogenic Systems | Job: 6201 - Cryogenic Syst-RAFTOPOLOUS | 1567.72 | 0 | 1567.72 | 0 | 0 | 0 | 0 | 0 | 67721.0258
| 6301 - Utility Systems | Job: 6301 - Utility Systems-DUDEK | 109.44 | 0 | 109.44 | 0 | 0 | 0 | 0 | 0 | 67721.0258
| Job: 6401 - PFC/VV Htng/Cooling(bakeout)- KALISH | Job: 6401 - Bakeout System GORANSON | 633.78 | 0 | 633.78 |  | 0 | 0 | 0 | 0 | 67721.0258
| 6501 - Facility Systems Integration |  |  | 9.37 | 9.37 | 9.37 |  |  | 0 | 9.37 | 67730.3958
9284.8497 | 7101 - Shield Wall Modif |  |  | 32.605 | 32.605 | 32.605 |  |  | 0 | 32.605 | 67763.0008
| 7201 - Control Room Walls Floors |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 67763.0008
| 7301 - Platform Design & | Job: 7301 - Platform Design & | 212.67 | 75.836 | 288.506 | 75.836 | 0 | 0 | 10.65 | 86.486 | 67849.4868 | 10.65
| 7401 - TC Prep & Mach Assy Planning | Job: 7401 - TC Prep & Mach Assy Planning-PERRY | 2322.89 | 599.5187 | 2922.4087 | 854.594 | -255.0753 | 55.9541 | 0 | 655.4729 | 68504.9597
| 7501 - Construction Support Crew | Job: 7501 - Construction Support Crew-PERRY | 1325.21 | 0 | 1325.21 | 0 | 0 | 0 | 0 | 0 | 68504.9597
| 7502 - Test Cell Facility Preparations | Job: 7503 - Machine Assembly (station 6)-PERRY | 4317.43 | 0 | 4317.43 | 0 |  |  | 0 | 0 | 68504.9597
| 7503 - Machine Assembly |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68504.9597
| 7601 - Tooling Design & Fabrication | Job: 7601 - Tooling Design & Fabrication-PERRY | 398.69 | 0 | 398.69 | 0 | 0 | 0 | 0 | 0 | 68504.9597
8837.8018 | 8101 - Project Management & Control | Job: 8101 - Project Management &Control-ANDERSON | 4159.8 | 3316.0858 | 7462.8858 | 2829.849 | 486.2368 | 430.6355 | -59.619 | 3687.1023 | 72192.062 | -59.619
| 8102 - NCSX MIE Management ORNL | Job: 8102 - NCSX MIE Management ORNL-LYON | 654.21 | 720.706 | 1374.916 | 553.747 | 166.959 | 66.9 | 12.665 | 800.271 | 72992.333 |  | 12.665
14107.083 | 8202 - Engr Mgmt & Sys Eng Support | Job: 8202 - Engr Mgmt & Sys Eng Sprt-HEITZENROED | 3253.64 | 3190.7191 | 6429.3591 | 2653.261 | 537.4581 | 185.0085 | 83.566 | 3459.2936 | 76451.6265 | 83.566
| 8203 - Design Integration | Job: 8203 - Design Integration-BROWN | 2580.51 | 1102.648 | 3683.158 | 988.511 | 114.137 | 59.415 | 32.385 | 1194.448 | 77646.0746 | 32.385
| 8204 - Systems Analysis | Job: 8204 - Systems Analysis-BROOKS | 1031.97 | 1692.7393 | 2724.7093 | 1283.906 | 408.8333 | 205.5569 | 67.24 | 1965.5362 | 79611.6108 | 67.24
| 8205 - Dimensional Control Coord. | Job: 8205 - Dimensional Control Coordin-ELLIS | 541.78 | 435.1141 | 976.8941 | 301.334 | 133.7801 | 30.2689 | 9.611 | 474.994 | 80086.6047 | 9.611
| 8210 - Project Rebaseline Estimating |  |  | 93.0925 | 93.0925 | 37.646 | 55.4465 | 12.672 | 0.332 | 106.0965 | 80192.7013 | 0.332
| Job: 8215 Plant Design | Job: 8215 Plant Design | 199.87 | 0 | 199.87 |  | 0 | 6.0624 | 0 | 6.0624 | 80198.7637
470.016 | 8401 - Project Physics |  |  | 323.549 | 323.549 | 323.549 |  |  | 0 | 323.549 | 80522.3127
| 8402 - Project Physics MIE ORNL |  |  | 146.467 | 146.467 | 146.467 |  |  | 0 | 146.467 | 80668.7797
| 8501 - Integrated Systems Testing | Job: 8501 - Integrated Systems Testing-GENTILE | 794.61 | 0 | 794.61 | 0 | 0 | 0 | 3.328 | 3.328 | 80672.1077 | 3.328
| 8998 - Allocations | Job: 8998 - Allocations-STRYKOWSKY | 1927.89 | 1791.9648 | 3719.8548 | 1419.933 | 372.0318 | 126.1886 | 20.942 | 1939.0954 | 82611.2031 | 20.942
| dcma |  |  | 75 | 75 | 75 |  |  |  | 75 | 82686.2031
|  | Total project (May 1 through completion) | 61813.9 | [6 empty] | 0
|  |  |  | 76493.0706 | 138103.9706 | 67306.363 | 9186.7076 | 4652.8226 | 1540.31 | 82686.2031 |  | 1352.567 | 187.743
76493.0706
82686.2031

## bcws
BCWS
ACT CODE | DESCRIPTION | bcws june july aug | TOTAL | JUN FY08 | JUL FY08 | AUG FY08 | SEP FY08 | OCT FY09 | NOV FY09 | DEC FY09 | JAN FY09 | FEB FY09 | MAR FY09 | APR FY09
1302 | Job: 1302 - PF Design -CHRZANOWSKI | 0 | 0 | 0 | 0
1352 | Job: 1352 - PF Coil Procurement-CHRZANOWSKI | 93.1 | 93.1 | 57.5 | 35.6
1354 | Job: 1354 - Trim Coil Design &Procurement-KALISH | 23.8 | 23.8 | 23.8
1361 | Job: 1361 - TF Fabrication-KALISH | 144.2 | 245 | 28.8 | 57.9 | 57.5 | 100.8
1408 | Job: 1408 - MC Winding Supplies-CHRZANOWSKI | 20.5 | 20.5 | 10 | 10.5
1416 | Job: 1416 - Mod Coil Type AB Fnl Dsn-COLE | 37.4 | 37.4 | 37.4
1421 | Job: 1421 - Mod Coil Interface Design-COLE | 49.8 | 49.8 | 37.7 | 12.1
1431 | Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 97 | 97 | 97
1451 | Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 269.5 | 279.9 | 93.1 | 117.2 | 59.2 | 10.4
1459 | Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI | 67.6 | 67.6 | 22.2 | 23.2 | 22.2
1501 | Job: 1501 - Coil Structures Design-DAHLGREN | 73.6 | 73.6 | 73.6
1601 | Job: 1601 - Coil Services Design-GORANSON | 30.2 | 30.2 | 30.2
1702 | Job: 1702 - Base Support Struct Design-DAHLGREN | 11.7 | 11.7 | 11.7
1802 | Job: 1802 - FP Assy Oversight&Support-VIOLA | 240.8 | 355.3 | 80.7 | 81.9 | 78.2 | 78.2 | 14.4 | 11.3 | 10.6
1803 | Job: 1803/1805- FPA Tooling/Constr-BROWN | 108.9 | 113.9 | 96.8 | 2.2 | 9.9 | 5
1806 | Job: 1806 - FP Assembly specs | 6 | 6 | 6
1810 | Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | 637.7 | 812.6 | 254.7 | 218.3 | 164.7 | 151.8 | 23.1
1901 | Job: 1901 - Stellarator Core Mngtt&Integr-COLE | 98.9 | 127.4 | 32.6 | 34.1 | 32.2 | 28.5
3101 | Job: 3101 - Magnetic Diagnostics-STRATTON | 28.2 | 28.2 | 28.2
8101 | Job: 8101 - Project Management &Control-REJ | 257.5 | 633 | 84.5 | 88.5 | 84.5 | 84.5 | 55.3 | 43.3 | 40.9 | 50.5 | 48.1 | 52.9
8102 | Job: 8102 - NCSX MIE Management ORNL-HARRIS | 76.8 | 136.5 | 25.2 | 26.4 | 25.2 | 24 | 6.8 | 5.3 | 5 | 6.2 | 5.9 | 6.5
8202 | Job: 8202 - Engr Mgmt & Sys Eng Sprt-HEITZENROED | 143.9 | 362.9 | 47.2 | 49.5 | 47.2 | 47.2 | 32.7 | 25.6 | 24.1 | 29.8 | 28.4 | 31.2
8203 | Job: 8203 - Design Integration-BROWN | 10.6 | 14.1 | 3.5 | 3.6 | 3.5 | 3.5
8204 | Job: 8204 - Systems Analysis-BROOKS | 31.7 | 42.1 | 10.4 | 10.9 | 10.4 | 10.4
8205 | Job: 8205 - Dimensional Control Coordin-ELLIS | 29.7 | 33.7 | 8.4 | 10.9 | 10.4 | 4
8220 | Job: 8220 - Equipt Save & Facility Restora-PERRY | 176.5 | 529.6 | 8.8 | 80.3 | 87.4 | 120.6 | 107.7 | 64.2 | 60.6
8221 | Job: 8221 -Documentation Closeout-HEITZENROEDER | 550 | 1133.6 | 52 | 254.8 | 243.2 | 241.3 | 222.2 | 44.3 | 41.9 | 11.7 | 11.1 | 11.1
8222 | Job: 8222 - Manuscripts and Papers - NEILSON | 0 | 299.6 |  |  |  | 44.3 | 48.5 | 38 | 35.9 | 44.3 | 42.2 | 46.4
8998 | Job: 8998 - Allocations-STRYKOWSKY | 108.5 | 201.8 | 35.6 | 37.3 | 35.6 | 33.9 | 11.3 | 8.8 | 8.4 | 10.3 | 9.8 | 10.8
CCCP | Contingency-Project |  | 1172.2 | 119.5 | 125.2 | 119.5 | 119.5 | 130.9 | 102.4 | 96.7 | 119.5 | 113.8 | 125.2
|  | 3424.1 | 7032.1

## bcwr
JJJJ | None | ACT CODE | DESCRIPTION | TOTAL | SEP FY08 | OCT FY09 | NOV FY09 | DEC FY09 | JAN FY09 | FEB FY09 | MAR FY09 | APR FY09 | MAY FY09 | JUN FY09 | JUL FY09 | AUG FY09 | SEP FY09
| 1361 - Job: 1361 - TF Fabrication-KALISH | 1361 | Job: 1361 - TF Fabrication-KALISH | 106.6 | 106.6
| 1302 - Job: 1302 - PF Design -CHRZANOWSKI | 1302 | Job: 1302 - PF Design -CHRZANOWSKI | 0
| 1352 - Job: 1352 - PF Coil Procurement-CHRZANOWSKI | 1352 | Job: 1352 - PF Coil Procurement-CHRZANOWSKI | 0
| 1354 - Job: 1354 - Trim Coil Design &Procurement-KALISH | 1354 | Job: 1354 - Trim Coil Design &Procurement-KALISH | 1.8 | 1.8
| 1416 - Job: 1416 - Mod Coil Type AB Fnl Dsn-COLE | 1416 | Job: 1416 - Mod Coil Type AB Fnl Dsn-COLE | 0
| 1408 - Job: 1408 - MC Winding Supplies-CHRZANOWSKI | 1408 | Job: 1408 - MC Winding Supplies-CHRZANOWSKI | 2 | 2
| 1451 - Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 1451 | Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 40 | 40
| 1459 - Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI | 1459 | Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI | 24.6 | 18 | 3.7 | 2.9
| 1421 - Job: 1421 - Mod Coil Interface Design-COLE | 1421 | Job: 1421 - Mod Coil Interface Design-COLE | 0
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 1431 | Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 0
| 1601 - Job: 1601 - Coil Services Design-GORANSON | 1601 | Job: 1601 - Coil Services Design-GORANSON | 0
| 1702 - Job: 1702 - Base Support Struct Design-DAHLGREN | 1702 | Job: 1702 - Base Support Struct Design-DAHLGREN | 0
| 1901 - Job: 1901 - Stellarator Core Mngtt&Integr-COLE | 1901 | Job: 1901 - Stellarator Core Mngtt&Integr-COLE | 50 | 50
| 1803 - Job: 1803/1805- FPA Tooling/Constr-BROWN | 1803 | Job: 1803/1805- FPA Tooling/Constr-BROWN | 0
| 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | 1806 | Job: 1806 - FP Assembly specs | 0
| 8205 - Job: 8205 - Dimensional Control Coordin-ELLIS | 8205 | Job: 8205 - Dimensional Control Coordin-ELLIS | 3.7 | 3.7
| 1802 - Job: 1802 - FP Assy Oversight&Support-VIOLA | 1802 | Job: 1802 - FP Assy Oversight&Support-VIOLA | 89.6 | 53.3 | 14.4 | 11.3 | 10.6
| 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | 1810 | Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | 176.8 | 176.8
| 1501 - Job: 1501 - Coil Structures Design-DAHLGREN | 1501 | Job: 1501 - Coil Structures Design-DAHLGREN | 0
| 3101 - Job: 3101 - Magnetic Diagnostics-STRATTON | 3101 | Job: 3101 - Magnetic Diagnostics-STRATTON | 0
| 8101 - Job: 8101 - Project Management &Control-REJ | 8101 | Job: 8101 - Project Management &Control-REJ | 372.3 | 81.3 | 55.3 | 43.3 | 40.9 | 50.5 | 48.1 | 52.9
| 8102 - Job: 8102 - NCSX MIE Management ORNL-HARRIS | 8102 | Job: 8102 - NCSX MIE Management ORNL-HARRIS | 107.3 | 71.6 | 6.8 | 5.3 | 5 | 6.2 | 5.9 | 6.5
| 8202 - Job: 8202 - Engr Mgmt & Sys Eng Sprt-HEITZENROED | 8202 | Job: 8202 - Engr Mgmt & Sys Eng Sprt-HEITZENROED | 191.9 | 43.5 | 28.2 | 22.1 | 20.8 | 25.8 | 24.5 | 27
| 8203 - Job: 8203 - Design Integration-BROWN | 8203 | Job: 8203 - Design Integration-BROWN | 0
| 8204 - Job: 8204 - Systems Analysis-BROOKS | 8204 | Job: 8204 - Systems Analysis-BROOKS | 4.7 | 4.7
| 8220 - Job: 8220 - Equipt Save & Facility Restora-PERRY | 8220 | Job: 8220 - Equipt Save & Facility Restora-PERRY | 347.9 | 81 | 48.5 | 41 | 67.7 | 56.2 | 53.5
| 8221 - Job: 8221 -Documentation Closeout-HEITZENROEDER | 8221 | Job: 8221 -Documentation Closeout-HEITZENROEDER | 941.8 | 226.8 | 244.8 | 191.6 | 149.1 | 50.9 | 48.5 | 30.1
| 8222 - Job: 8222 - Manuscripts and Papers - NEILSON | 8222 | Job: 8222 - Manuscripts and Papers - NEILSON | 293.4 | 43.4 | 47.5 | 37.2 | 35.1 | 43.4 | 41.3 | 45.5
| 8998 - Job: 8998 - Allocations-STRYKOWSKY | 8998 | Job: 8998 - Allocations-STRYKOWSKY | 93.2 | 33.8 | 11.3 | 8.8 | 8.4 | 10.3 | 9.8 | 10.8
2847.6