## Sheet1
Task ID |  | Multiplier | Unit | Number of Units | Hours | ORNL EM | ORNL Dsn | ORNL RM | EMEM | EMSM | EMSB | EMTB | EASM | EASB
Title I & II Design
| ProE Models (avg) | 8 | hrs/model | 21 | 168 | 168
| Assy Dwgs | 16 | hrs/dwg | 24 | 384 | 384
| Detail Dwgs | 8 | hrs/dwg | 13 | 104 | 104
| Installation Dwg | 16 | hrs/dwg | 14 | 224 | 224
| Cooling Schematic | 20 | hrs/dwg | 1 | 20 | 20
| Electrical Schematic | 0 | hrs/dwg | 1 | 0 | 0
| I&C Schematic | 20 | hrs/dwg | 1 | 20 | 20
| Stress Analysis | 40 | hrs/calc | 1 | 40 | 40
| Thermal Analysis | 40 | hrs/calc | 1 | 40 | 40
| Special Analysis (Electomagnetis) | 160 | hrs/calc | 0 | 0 | 0
| Fab Specifications | 160 | hrs/spec | 2 | 320 | 320
| PDR/FDR Reviews | 80 | hrs/review | 2 | 160 | 160
| Resolve PDR Comments | 40 | hrs/PDR | 1 | 40 | 40
| Meetings/Reporting/Presentations | 10% | % Total Hrs |  | 152 | 152
| Subtotal Title I & II Design |  |  |  | 1672 | 1672
R&D Activities
| R&D - Pressure drop simulation w/ pressurized LN2 & valve |  |  |  |  | 40
| Subtotal R&D Activities |  |  |  |  | 40
Title III Activities
| Disposition of RFDs & NCRs | 1 | hrs/ | 38 | 38 |  |  |  | 38
| As Built Drawings | 2 | # dwgs | 52 | 104 | 104
| Procurement Support |  |  |  | 80 |  |  |  | 40 | 40