## Combined
| Half Period Assembly Outline |  | No Inner Shim Assembly |  |  |  | Optimized Assembly |  |  |  | Baseline - tight bushing; |  |  |  | Mod 1 - tight bushing; |  |  |  | Mod 2 - insul only bushing;
[11 empty] | nose shear plate; no diamond |  |  |  | no shear plate; diamond |  |  |  | no shear plate; diamond
|  |  | $ M&S | #men | days | man-days | $ M&S | #men | days | man-days | Back Office MD | #men | days | man-days | Back Office MD | #men | days | man-days | Back Office MD | #men | days | man-days
[11 empty] | SR TB AB |  |  |  | SR TB AB |  |  |  | SR TB AB
FITUP (all 4 joints) | Inventory pre-fabricated shims (insulated on top & bottom) |  | 5000 |  |  | 0 | 5000 |  |  | 0 |  | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 1 | 1 | 1
| Mount MCWF A on assembly stand. |  |  | 4 | 1 | 4 |  | 4 | 1 | 4 |  | 4 | 1 | 4 |  | 4 | 1 | 4 |  | 4 | 1 | 4
| Determine location with laser tracker. |  |  | 2 | 1 | 2 |  | 2 | 1 | 2 |  | X | X | X |  | X | X | X |  | X | X | X
| Install 3 point spherical balls into their locations. |  | 1000 | 1 | 1 | 1 | 1000 | 1 | 1 | 1 |  | X | X | X |  | X | X | X |  | X | X | X
| Use laser tracker to establish MCWF FPA coordinate system |  |  | 1 | 1 | 1 |  | 1 | 1 | 1 | 6 | 3 | 4 | 12 | 6 | 3 | 4 | 12 | 6 | 3 | 4 | 12
| Hone the seats as required (this applies to Type C 1-3 only - the others only have a counterbore to accept a socket insert piece)). |  |  | 1 | 1 | 1 |  | 1 | 1 | 1 |  | X | X | X |  | X | X | X |  | X | X | X
| Use laser tracker or romer arm to set ball locations per CAD space. |  |  | 1 | 1 | 1 |  | 1 | 1 | 1 |  | X | X | X |  | X | X | X |  | X | X | X
| Check that MCWF A has not moved and balls are correctly located. |  |  | 1 | 1 | 1 |  | 1 | 1 | 1 |  | X | X | X |  | X | X | X |  | X | X | X
| Lower MCWF B onto A - visually guide into positon |  |  | 4 | 1 | 4 |  | 4 | 1 | 4 |  | 4 | 0.5 | 2 |  | 4 | 0.5 | 2 |  | 4 | 0.5 | 2
[6 empty] | 0 |  |  |  | 0 |  | 4 | 0.5 | X |  | 4 | 0.5 | X |  | 4 | 0.5 | X
| Install corner aligment plates. |  |  | X | X | X |  | X | X | X |  | 4 | 0.5 | 2 |  | 4 | 0.5 | 2 |  | 4 | 0.5 | 2
| Check fiducials on A - re-set to re-establish default coordinate system due to added weight deflecting things. |  |  | 2 | 2 | 4 |  | 2 | 1 | 2 | 6 | 2 | 1 | 2 | 6 | 2 | 1 | 2 | 6 | 2 | 1 | 2
| Install a few offset bushings and torque. Assumes a full set of varous sized eccentric bushings are available. |  |  | X | X | X |  | X | X | X |  | 2 | 1 | 2 |  | 2 | 1 | 2 |  | 2 | 0.5 | 1
| If bushings need custom machining | [10 empty] | 2 | 2 | 4 |  | 2 | 2 | 4 |  | X | X | X
| Check fiducials on A & B determine if correction required, adjust 3 points, and re-shim. |  |  | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 1 | 1 | 1
| Back office review data & approve or set corrective action. |  |  | 1 | 1 | 1 |  | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 4 | 1 | 1 | 1
| Check each shim location - verify that shim thicknesses are correct. Grind shim as req'd. |  |  | 2 | 5 | 10 |  | 2 | 5 | 10 |  | 2 | 5 | 10 |  | 2 | 5 | 10 |  | 2 | 5 | 10
| Separate A and B |  |  |  |  | 0 |  |  |  | 0 |  | 4 | 0.5 | 2 |  | 4 | 0.5 | 2 |  | 4 | 0.5 | 2
Diamond | Diamond coat all shims | [10 empty] | X | X | X |  | 0 | 7 | 1 |  | 0 | 7 | 1
NOSE | Stud weld shear pin studs using a template. |  | X | X | X | X | X | X | X | X |  | 4 | 4 | 16 |  | X | X | X |  | X | X | X
NOSE | Clean weld splatter; Snap studs or grind to correct height. Install sleeve on studs? |  |  | X | X | X |  | X | X | X |  | 2 | 2 | 4 |  | X | X | X |  | X | X | X
| Install G-11 insulators; Check fit-up of shim plates |  |  | X | X | X |  | X | X | X |  | 2 | 1 | 2 |  | 2 | 1 | 2 |  | 2 | 1 | 2
| Place all shim packs in correct locations |  |  | 2 | 1 | 2 |  | 2 | 1 | 2 |  | 2 | 1 | 2 |  | 2 | 1 | 2 |  | 2 | 1 | 2
| Install wing bladders |  | 1000 | 2 | 1 | 2 | 1000 | 2 | 1 | 2 |  | 2 | 1 | 2 |  | 2 | 1 | 2 |  | 2 | 1 | 2
| Install the remaining offset bushings and torque | [10 empty] | 2 | 3 | 6 |  | 2 | 3 | 6 |  | 2 | 3 | 6
| Check for correct position of coils readjust shims as needed |  |  | 2 | 1 | 2 |  | 2 | 1 | 2 |  | 2 | 1 | 2 |  | 2 | 1 | 2 |  | 2 | 1 | 2
| Confirm final position |  |  | 2 | 1 | 2 |  | 2 | 1 | 2 | 6 | 2 | 1 | 2 | 6 | 2 | 1 | 2 | 6 | 2 | 1 | 2
JOIN | Install studs / bolts; torque in sequence. |  |  | 2 | 0.5 | 1 |  | 2 | 0.5 | 1 |  | 2 | 0.5 | 1 |  | 2 | 0.5 | 1 |  | 2 | 0.5 | 1
| Check MCWF positions again. |  |  | 2 | 1 | 2 |  | 2 | 1 | 2 | 4 | 2 | 1 | 2 | 4 | 2 | 1 | 2 | 4 | 2 | 1 | 2
| Inject Stycast 2850 into shear plate holes (this assumes communication holes between shim plate holes and fill tubes) DO SIMLTANEOUS INJECTION OF A-B B-C |  | X | X | X | X | X | X | X | X |  | 3 | 1 | 3 |  | 3 | 1 | 3 |  | 3 | 1 | 3
| Allow 48 hrs. for Stycast to cure. |  |  | 0 | 2 | 0 |  | 0 | 0 | 0 |  | 0 | 2 | 0 |  | 0 | 2 | 0 |  | 0 | 2 | 0
| Subtotals | per joint | 7000 |  |  | 42 | 7000 | 33 | 21.5 | 40 | 26 | 59 | 37.5 | 85 | 26 | 53 | 38.5 | 66 | 26 | 51 | 36 | 61
For all joints |  |  | Total Labor = |  |  | 514080 | Total Labor = |  |  | 489600 | Total Labor = |  |  | 1040400 | Total Labor = |  |  | 807840 | Total Labor = |  |  | 746640
[5 empty] | M&S | 126000 |  |  | M&S | 126000 |  |  | Back office labor | 159120 |  |  | Back office labor | 159120 |  |  | Back office labor | 159120
Repeated | Remove, catalog and store shims | [10 empty] | 2 | 1 | 2 |  | 2 | 1 | 2 |  | 2 | 1 | 2
work | Install G-11 insulators; Check fit-up of shim plates |  |  | X | X | X |  | X | X | X |  | 2 | 2 | 4 |  | 2 | 2 | 4 |  | 2 | 2 | 4
for 6 | Place all shim packs in correct locations |  |  | 2 | 1 | 2 |  | 2 | 1 | 2 |  | 2 | 1 | 2 |  | 2 | 1 | 2 |  | 2 | 1 | 2
vertical | Install wing bladders |  | 1000 | 2 | 1 | 2 | 1000 | 2 | 1 | 2 |  | 2 | 1 | 2 |  | 2 | 1 | 2 |  | 2 | 1 | 2
joints | Install the remaining offset bushings and torque | [10 empty] | 2 | 2 | 4 |  | 2 | 2 | 4 |  | 2 | 2 | 4
A-A and C-C | Check for correct position of coils readjust shims as needed |  |  | 2 | 1 | 2 |  | 2 | 1 | 2 |  | 2 | 1 | 2 |  | 2 | 1 | 2 |  | 2 | 1 | 2
| Confirm final position |  |  | 2 | 1 | 2 |  | 2 | 1 | 2 | 6 | 2 | 1 | 2 | 6 | 2 | 1 | 2 | 6 | 2 | 1 | 2
Additional For 6 Vertical joints A-A and C-C |  |  | Total Labor = |  |  | 1542240000 | Total Labor = |  |  | 1542240000 | Total Labor = |  |  | 73440 | Total Labor = |  |  | 73440 | Total Labor = |  |  | 73440
|  |  | Total Labor = |  |  | 24480 | Total Labor = |  |  | 24480 | Total Labor = |  |  | 1113840 | Total Labor = |  |  | 881280 | Total Labor = |  |  | 820080
[5 empty] | M&S | 18000 |  |  | M&S | 18000 |  |  | Back office labor | 159120 |  |  | Back office labor | 159120 |  |  | Back office labor | 159120
[15 empty] | Cost of Diamond coating |  |  | 300000 | Cost of Diamond coating |  |  | 300000
Grand TOTAL | [13 empty] | 1113840 |  |  |  | 1181280 |  |  |  | 1120080