## Sheet1
| FY 2006 | [9 empty] | FY2007
[6 empty] | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | M&S |  | DEW | PLG | MJC | GM | GL | KF | total | TB | LM | JR | LD
[25 empty] | 112 | 396 | 196 | 480 | 480 | 180 | 1844
[24 empty] | Fraction | 0.23333 | 0.825 | 0.40833 | 1 | 1 | 0.375
(assume 480 avail design hours full time)
|  | Forecast Start | Duration (weeks) | Forecast Finish
| Define requirements, design concept, plan of attack | 2006-08-14 | 2 | 2006-08-28
| Information meeting |  |  | 2006-08-28
| Conduct development activities | 2006-08-28 | 6 | 2006-10-09
| Complete analyses, finalize PD | 2006-10-09 | 3 | 2006-10-30
| PDR |  |  | 2006-10-30
| Complete final design | 2006-10-30 | 4 | 2006-11-27
| FDR |  |  | 2006-11-27
| Release specs and drawings for fab | 2006-11-27 | 2 | 2006-12-11
| Issue requisition | 2006-12-11 | 1 | 2006-12-18 | Probably multiple requisitions
| Receive parts | 2006-12-18 | 8 | 2007-02-12
| Begin assembly of first 3-pack |  |  | 2007-03-02 | Free float shown in duration column
|  | Forecast Start | Duration (weeks) | Forecast Finish
3 point positioning hardware (Paul Goranson, Gary McGinnis)
review requirements, as-built casting features, etc. |  | 2006-08-28 | 3 | 2006-09-18 | [21 empty] | 40
obtain results from mockup test
Review for approval to proceed
Prepare dwgs and release |  | 2006-09-15 | 7 | 2006-11-03 | [21 empty] | 16 |  | 120
Issue dwgs for Fabrication
Bid, Award, Procure or Fabricate |  | 2006-11-01 | 12 | 2007-01-24 | [30 empty] | 20
Receive and inspect
Bladders (Paul Goranson, Kevin Freudenberg, Gary McGinnis)
review and finalize structural requirements |  | 2006-08-28 | 5 | 2006-10-02 | [25 empty] | 40
select and test concept(s) | [25 empty] | 160
Finalize / select design (config and materials) |  | 2006-08-28 | 10 | 2006-11-06 | [20 empty] | 40 | 120
Review for approval to proceed
Prepare dwgs and release |  | 2006-11-13 | 7 | 2007-01-01 | [23 empty] | 200
Issue dwgs for Fabrication
Bid, Award, Procure or Fabricate |  | 2006-01-01 | 7 | 2006-02-19
Receive and inspect
Bolt Reaming (Paul Goranson, Mike Cole, Kevin Freudenberg)
review and finalize structural requirements |  | 2006-08-28 | 3 | 2006-09-18 | [25 empty] | 40
Finalize concept |  | 2006-09-04 | 2 | 2006-09-18 | [21 empty] | 40 | 20
Review for approval to proceed
Prepare tooling specs, drawings |  | 2006-09-18 | 6 | 2006-10-30 | [21 empty] | 20 | 80
Issue dwgs for Procuremenet/ Fabrication
Bid, Award, Procure or Fabricate |  | 2006-11-01 | 12 | 2007-01-24
Receive and inspect
Shear plate and shims (Kevin Freudenberg,Dave Williamson, Garry Lovett)
Complete testing |  | 2006-08-28 | 4 | 2006-09-25 | [25 empty] | 80
Finalize design, select material |  | 2006-09-04 | 2 | 2006-09-18 | [20 empty] | 40 |  |  |  |  | 20
Review for approval to prceed
Prepare dwgs and release |  | 2006-09-11 | 6 | 2006-10-23 | [24 empty] | 240
Issue dwgs for Fabrication
Bid, Award, Procure or Fabricate |  | 2006-10-31 | 12 | 2007-01-23
Receive and inspect
Top assy drawings (Dave Williamson, Mike Cole, Gary Lovett)
Identify all stud, bushing, sperical washer, insulator, nut types |  | 2006-10-09 | 4 | 2006-11-06 | [22 empty] | 16
Prepare advanced procurement dwgs calling out parts |  | 2006-10-16 | 4 | 2006-11-13 | [22 empty] | 40
Issue specs/dwgs for procurement (studs, bushings, etc.)
Finish 3-coil, 6 coil, and 18 coil top assemblies |  | 2006-11-20 | 4 | 2006-12-18 | [23 empty] | 160 | 160
Develop as-built model and drawing format |  | 2006-12-11 | 4 | 2007-01-08 | [22 empty] | 40
Complete assembly spec |  | 2006-12-18 | 3 | 2007-01-08
Bid, Award, Procure |  | 2006-11-20 | 10 | 2007-01-29
Receive and inspect
Other insulation over wings (Dave Williamson, Gary Lovett)
Finalize requirements |  | 2006-09-11 | 4 | 2006-10-09 | [20 empty] | 16
finalize design |  | 2006-09-18 | 3 | 2006-10-09 | [20 empty] | 16
Review for approval to proceed
Prepare dwgs and release |  | 2006-10-09 | 5 | 2006-11-13 | [24 empty] | 80
Issue dwgs for Fabrication
Bid, Award, Procure or Fabricate |  | 2006-11-20 | 10 | 2007-01-29
Receive and inspect
Long lead procurements
Studs
nuts
G11 bushings
Formulas:
Forecast Finish = [Forecast Start]+[Duration (weeks)]*7
Forecast Finish = [Forecast Finish, row above]
Forecast Start = [Forecast Finish, row above]

## Sheet2
hours
| 243 | 1403-11.1 51 1421 Describe interfaces as part of coil FDR's
| 131 | 1403-16 51 1421 Assembly bolts, nuts,washers
| 171 | 1403-17 51 1421 Assembly shims
| 211 | 1403-18 51 1421 Eccentric ball assembly
| 235 | 1403-19 51 1421 Top assembly dwgs for mod coil shell
| 179 | 1403-19A 51 1421 Bladder Details
| 160 | 1403-20 1421 3 coil assembly specification
| 80 | 1421-10 1421 add'l analysis of coil to coil joints/friction
| 80 | 1421-15 1421 develop design fix for issue
| 80 | 1421-20 1421 rework type A,B,C design as req'd
| 80 | 1421-25 1421 detailed design of add'l hardware
| 160 | 1421-30 1421 check and promote 6 coil dwgs 91
FY06CV-111 1421 ECP45 FY06
1810
1403-11.1 51 1421 Describe interfaces as part of coil FDR's
1403-16 51 1421 Assembly bolts, nuts,washers
1403-17 51 1421 Assembly shims
1403-18 51 1421 Eccentric ball assembly
1403-19 51 1421 Top assembly dwgs for mod coil shell
1403-19A 51 1421 Bladder Details
1403-20 1421 3 coil assembly specification
1421-10 1421 add'l analysis of coil to coil joints/friction
1421-15 1421 develop design fix for issue
1421-20 1421 rework type A,B,C design as req'd
1421-25 1421 detailed design of add'l hardware
1421-30 1421 check and promote 6 coil dwgs 91
FY06CV-111 1421 ECP45 FY06