## PPPL FAB
NCSX TF FABRICATION BY PPPL
| Assumptions: | [7 empty] | Rate | EM | 171.6 | fy06 rate
| 1) Conductors will arrive in 90to 100 ft. length spools |  |  |  |  | MHX (fy05/06)= | 25/40% |  |  | SM | 112.72 | fy06 rate
| 2) Conductors need to be primed |  |  |  |  | MHX G&A | 13% |  | fy05 | TB | 82.37 | fy06 rate
| 3) Torch Braze joints |  |  |  |  | Composite (fy05/06 MHX | 33.9% |  | 162.77 | DM | 101.46 | fy05 rate
| 4) Four conductor spools per TF coil | [8 empty] | per R. Strykowsky 10/5/04
|  | Duration | Start | End | EAEM | EETB | EADM | EMSM | EMSM | EMTB | M&S
| TASK DESCRIPTION |  |  |  | Engr | Tech | Designer |  | machinist | Tech
|  | Days |  |  | hours | hours | hours | hours | hours | hours | w/o G&A | w/G&A
1 | ENGINEERING and OVERSIGHT
| Design tooling and winding facility |  |  |  | 288 |  | 720
| Field Oversight FY05 |  |  |  | 0 |  |  | 120
| Field Oversight FY06 |  |  |  | 0 |  |  | 120
| Field Oversight FY07 |  |  |  | 0 |  |  | 40 |  |  |  |  | Total Cost
| Sub total (hours) |  |  |  | 288 | 0 | 720 | 280 |  |  |  |  | 151490.56
| Sub total cost |  |  |  | 46877.76 |  | 73051.2 | 31561.6
2 | Braze Qualification Program
| Fabricate work coils | [7 empty] | 0 | 0
| Prepare braze samples | [7 empty] | 80
| Develop braze technique | [8 empty] | 60 |  |  | Total cost
| Braze conductor samples | [8 empty] | 60
| Test brazed samples | [6 empty] | 80
| Sub total (hours) |  |  |  | 0 | 0 | 0 | 80 | 80 | 120 |  |  | 27919.6
| Sub total cost | [6 empty] | 9017.6 | 9017.6 | 9884.4
|  | Duration | Start | End | EAEM | EETB | EADM | EMSM | EMSM | EMTB | M&S
| TASK DESCRIPTION |  |  |  | Engr | Tech | Designer |  | machinist | Tech
|  | Days |  |  | hours | hours | hours | hours | hours | hours | w/o G&A | w/G&A
3 | EQUIPMENT and TOOLING COSTS
Fabricate Coil WIndingTooling/Fixtures
| Recondition turning fixture | [8 empty] | 360 | 5000
| Winding clamps | [7 empty] | 80 | 80 | 5000
| Taping machine conditioning |  |  |  |  | 80 |  |  | 80 | 160 | 1000
| Winding mandrel | [7 empty] | 120 | 160 | 5000
| Miscellaneous tools and equipment | [9 empty] | 3000
| TF mold (2) | [7 empty] | 360 | 360 | 10000
| Braze unit (TBD torch brazing assumed) | [9 empty] | 0 |  | Total cost
| Sub total (hours) |  |  |  | 0 | 80 | 0 | 0 | 640 | 1120 |  |  | 209815.8
| Sub total cost |  |  |  |  | 6589.6 |  |  | 72140.8 | 92254.4 | 29000 | 38831
4 | AREA PREPARATION
| Setup winding facility in the TFTR Test Cell | [6 empty] | 320 | 0 | 480 | 5000 | 6695
Install winding table
Setup copper delivery system
Install taping machine
Complete setup of facility
| Build cleanroom | [6 empty] | 0 |  | 0 | 5000 | 6695 | Total Cost
| Sub total (hours) |  |  |  | 0 | 0 | 0 | 320 | 0 | 480 |  |  | 79286
| Sub total cost | [6 empty] | 26358.4 | 0 | 39537.6 | 10000 | 13390
5 | MATERIAL & SUPPLIES
5a | Coil Supplies
| 1) Insulation [t/t and groundwrap] | [9 empty] | 80000
| 2) Epoxy- CTD-101K | [9 empty] | 60000
[8 gallons per coil @ $1500.00 per kit- assume 20 injections]
| 5) Copper conductor | [9 empty] | 80000
| 6) G-11 fillers [Fillers for transitions and leads] | [7 empty] | 480 | 80 | 4000
| 7) Lead blocks | [7 empty] | 144 | 40 | 4680
| 8) Safety and PPE equipment and supplies | [9 empty] | 8000
| 9) Miscellaneous supplies [Includes rags, hardware, braze material etc.] | [9 empty] | 8000
| 10) Primer | [9 empty] | 8000
5b | VPI Supplies
| 1) Misc VPI supplies | [9 empty] | 8000
| 2) Disposable VPI hardware | [8 empty] | 432
| valves | [9 empty] | 10000
| High & low temperature vac. Tubing | [9 empty] | 20000
| Copper tubing | [9 empty] | 5000 |  | Total Cost
| Sub total (hours) |  |  |  | 0 | 0 | 0 | 0 | 624 | 552 | 295680 | 395915.52 | 511721.04
| Sub total cost | [7 empty] | 70337.28 | 45468.24
Task | TASK DESCRIPTION | Working | Shifts | No. of | EMTB
No. |  | Days | per day | Tech. | man-hours
6 | Station No. 1- Conductor Preparation | 21 | Total working days
6a | Receive conductors | [6 empty] | Hours | Cost
| Unload and sample measure each spool | 3 | 1 | 2 | 48 |  | TOTAL | 336 | 27676.32
6b | Flush inner bore | 18 | 1 | 2 | 288
6c | Clean, prime and bag conductor | 0 | 0 | 0 | 0
Task | TASK DESCRIPTION | Working | Shifts | No. of | No. of |  | Working | Shifts | No. of | No. of | No. of | Man-hrs | Total
No. |  | Days | per day | Tech. | man-hours |  | Days | per day | Tech. | man-hours | Items | 2 thru 18 | Man-hrs
7 | Station No. 2- Coil Winding | 18 | Total working days 1st. coil |  |  |  | 8.5 | Total working days coils 2 thru 18
7a | Prepare winding station for winding TF coil | 3 |  |  | 72 |  | 1 |  |  | 16 | 17 | 272 | 344
| Install and prepare mandral | 3 | 1 | 3 | 72 |  | 1 | 1 | 2 | 16
3
7b | Wind TF coil | 15 |  |  | 224 |  | 7.5 |  |  | 128 | 17 | 2176 | 2400
| Position starting conductor & wind layer #1 | 4 | 1 | 2 | 64 |  | 1 | 1 | 2 | 16 | 17
| Braze lead spur | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Position 2nd. Conductor and braze layer 1 to 2 | 4 | 1 | 2 | 64 |  | 1 | 1 | 2 | 16
| Wind layer #2 - | 2 | 1 | 2 | 32 |  | 1 | 1 | 2 | 16
| Position 3rd. Conductor & wind layer 3 | 1 | 1 | 2 | 16 |  | 1 | 1 | 2 | 16
| Perform locking braze layers 2 to 3 | 1 | 1 | 2 | 16 |  | 1 | 1 | 2 | 16
| Position 4nd. Conductor and braze layer 3 to 4 | 1 | 1 | 2 | 16 |  | 1 | 1 | 2 | 16
| Wind layer #4/ Torch braze | 1 | 1 | 2 | 16 |  | 0.5 | 1 | 2 | 8 |  |  | 2744
| Secure and transfer TF coil to station #3 | 1 | 1 | 3 | 24 |  | 1 | 1 | 3 | 24 |  | Total | 226023.28
8 | Station No. 3- Ground wrapping & Mold Application | 8 | Total working days 1st. coil |  |  |  | 5 | Total working days coils 2 thru 18
8a | Ground wrap TF coil | 4 | 1 | 2 | 64 |  | 3 | 1 | 2 | 48 | 17 | 816 | 880
Notes:
1) 2-man teams can apply approximately 5 wraps per minute. (2" wide tape)
2) (6) half-lapped layers of glass & (2) half-lapped layers of glass/Kapton
3) Circumference: approx. 353 inches
4) Approximately 70 minutes to complete (1) half-lapped layer
5) Approximately 10 hours to complete groudwrap operation
8b | Install TF coil in mold | 4 | 1 | 3 | 96 |  | 2 | 1 | 2 | 32 | 17 | 544 | 640
1520
[12 empty] | Total | 125202.4
Task | TASK DESCRIPTION | Working | Shifts | No. of | No. of |  | No. of | Total
No. |  | Days | per day | Tech. | man-hours |  | Items | Manhrs
9 | VPI TF Coil | 9 | Total working days per coil
Assumption: VPI (2) TF coils together
9a | Transfer TF coil to Autoclave | 1 | 1 | 4 | 32 |  | 9 | 288
9b | Prepare TF coil for VPI | [6 empty] | 0
| Connect fill lines, manifolds, hookup thermocouples & leak check | 2 | 1 | 2 | 32 |  | 18 | 576
0
9c | VPI TF coil | 8 | [5 empty] | 0
| Vacuum pumpdown mold and autoclave | 1 | 1 | 3 | 24 |  | 9 | 216
| Epoxy fill coil | 1 | 2 | 3 | 48 |  | 9 | 432
| Temperature rampup and Cure | 0 | 0 | 0 | 0 |  | 9 | 0
| [parallel activity] Station cleanup during cure | 1 | 1 | 3 | 24 |  | 9 | 216
| Temperature rampup and Post cure | 1 | 2 | 1 | 16 |  | 9 | 144
| Temperature rampdown | 1 | 1 | 1 | 8 |  | 9 | 72 |  | Hours | Cost
| Cleanup & ready autoclave | 2 | 1 | 2 | 32 |  | 9 | 288 | Total | 2808 | 231294.96
| Remove TF coil from mold/clean mold | 2 | 1 | 2 | 32 |  | 18 | 576
10 | Station No. 6- Electrical Test Station | 1
[10 empty] | Hours | Cost
| Perform electrical & Pressure Tests | 1 | 1 | 2 | 16 | 0 | 18 | 288 | Total | 288 | 23722.56
Warm tests (room temperature) only
Engineering & Oversight |  | 151490.56 |  | Summary Manpower Requirements
Brazing qualification |  | 27919.6 |  |  | FTE
Equip. & Tooling |  | 209815.8 |  | EA**EM (Engineering) | 0.16686
Area Preparation |  | 79286 |  | EA**SM (design) | 0.41715
Materials & supplies |  | 511721.04 |  | EM**SM (Machinists) | 0.77868
Conductor prep |  | 27676.32 |  | EM**SM (Senior L&S) | 0.39397
Coil winding |  | 226023.28 |  | EM**TB (Technicians) | 5.7752
Ground wrap/mold |  | 125202.4 |  |  | 7.5319
VPI |  | 231294.96
Testing |  | 23722.56 | ECP21
Total TF Fabrication |  | 1614152.52 | 1162679
Kalish oversight @ 75for 1st coil,25% on balance% |  | 145173.6 | 113900
over 17 mo. FAb period
Kalish travel |  | 0 | 1e-05
TOTAL COST FORPPPL FAB= |  | 1759326.12 | 1276579
Increase from baseline |  | 482747.12

## summary of COSTS
Summary Comparison of costs
Does not include;
1) Casting fabrication and oversight (same in both cases)
2) Assembly of castings to TF coil (same in both cases)
3) Contingency
4) No net Cost savings from modular coil VPI.(see mc tf vpi cost efficiency worksheet)
PPPL FAB |  |  | Variance | VENDOR FAB |  |  | ECP21
Engineering & Oversight |  | 151490.56 | 18290.56 | Engineering & Oversight |  | 133200
Brazing qualification |  | 27919.6 | 10919.6 | Brazing qualification |  | 17000
Equip. & Tooling |  | 209815.8 | 155885.8 | Equip. & Tooling |  | 53930
Area Preparation |  | 79286 | 52776 | Area Preparation |  | 26510
Materials & supplies |  | 511721.04 | 87868.24 | Materials & supplies |  | 423852.8
Conductor prep |  | 27676.32 | 17776.32 | Conductor prep |  | 9900
Coil winding |  | 226023.28 | 123503.28 | Coil winding |  | 102520
Ground wrap/mold |  | 125202.4 | 41602.4 | Ground wrap/mold |  | 83600
VPI |  | 231294.96 | 80814.96 | VPI |  | 150480
Testing |  | 23722.56 | -19117.44 | Testing |  | 42840
| subtotal = | 1614152.52 | 570319.72 |  | subtotal = | 1043832.8
|  |  |  | Vendor Contingency | 20% | 208766.56
|  |  |  | Vendor Profit | 10% | 125259.936
|  |  |  | Total Billed by Vendor |  | 1377859.296 | 1015100
|  |  |  | PPPL MHX on 1st $500k @ | 25 & 40% | 147650
|  |  |  | PPPL G&A on MHX @ | 12.5&13% | 19194.5
Total TF Fabrication |  | 1614152.52 | 69448.724 | Total With PPPL G&A |  | 1544703.796 | 1162679
Kalish oversight @ 75for 1st coil,25% on balance% |  | 145173.6 | 0 | Kalish oversight @ 75for 1st coil,25% on balance% |  | 145173.6 | 113900
over 17 mo. FAb period |  |  |  | over 17 mo. Contract period
|  |  |  | Kalish trips to vendor for Vendor supervision (3days/mo. x17) |  | 70012.8
Kalish travel |  | 0 | -43222.5 | Kalish travel@$1.5k/mo.plus G&A |  | 43222.5 | 1e-05
TOTAL COST FOR PPPL FAB= |  | 1759326.12 | -43786.576 | TOTAL COST FOR OUTSIDE FAB= |  | 1803112.696 | 1272565.52
Increase from baseline |  | 486760.6 | -43786.576 | Increase from baseline |  | 530547.176
Additional Manpower Requirements for in-house fab
MANYEARS
|  | EA**EM (Engineering) | 0.16686
|  | EA**SM (design) | 0.41715
|  | EM**SM (Machinists) | 0.77868
|  | EM**SM (Senior L&S) | 0.39397
|  | EM**TB (Technicians) | 5.7752
7.5319

## summary of HOURS
SUMMARY OF FABRICATION HOURS
| TASK DESCRIPTION | PPPL FAB | VENDOR FAB | DELTA
1 | ENGINEERING and OVERSIGHT
| Design tooling and winding facility | 1008 | 444 | 564
| LOE FY05 | 120 | 240 | -120
| LOE FY06 | 120 | 576 | -456
| LOE FY07 | 40 | 144 | -104
2 | Braze Qualification Program
| Fabricate work coils | 0 | 0 | 0
| Prepare braze samples | 80 | 80 | 0
| Develop braze technique | 60 | 60 | 0
| Braze conductor samples | 60 | 60 | 0
| Test brazed samples | 80 | 80 | 0
3 | EQUIPMENT and TOOLING COSTS
Fabricate Coil WIndingTooling/Fixtures
| Recondition turning fixture | 360 | 0 | 360
| Winding clamps | 160 | 0 | 160
| Taping machine conditioning | 320 | 0 | 320
| Winding mandrel | 280 | 280 | 0
| Miscellaneous tools and equipment | 0 | 0 | 0
| TF mold (2) | 720 | 360 | 360
| Braze unit (TBD torch brazing assumed) | 0 | 0 | 0
4 | AREA PREPARATION
| Setup winding facility in the TFTR Test Cell | 800 | 120 | 680
| Install winding table | 0 | 0 | 0
| Setup copper delivery system | 0 | 0 | 0
| Install taping machine | 0 | 0 | 0
| Complete setup of facility | 0 | 0 | 0
| Build cleanroom | 0 | 120 | -120
5 | MATERIAL & SUPPLIES
5a | Coil Supplies
| 1) Insulation [t/t and groundwrap] | 0 | 0
| 2) Epoxy- CTD-101K | 0 | 0
| [8 gallons per coil @ $1500.00 per kit- assume 20 injections] | 0 | 0
| 5) Copper conductor | 0 | 0
| 6) G-11 fillers [Fillers for transitions and leads] | 560 | 560 | 0
| 7) Lead blocks | 184 | 184 | 0
| 8) Safety and PPE equipment and supplies | 0 | 0
| 9) Miscellaneous supplies [Includes rags, hardware, braze material etc.] | 0 | 0
| 10) Primer | 0 | 0
5b | VPI Supplies
| 1) Misc VPI supplies | 0 | 0
| 2) Disposable VPI hardware | 432 | 432 | 0
| valves | 0 | 0
| High & low temperature vac. Tubing | 0 | 0
| Copper tubing | 0 | 0
6 | Station No. 1- Conductor Preparation
6a | Receive conductors | 0 | 0 | 0
| Unload and sample measure each spool | 48 | 36 | 12
6b | Flush inner bore | 288 | 144 | 144
6c | Clean, prime and bag conductor | 0 | 0 | 0
7 | Station No. 2- Coil Winding
7a | Prepare winding station for winding TF coil
| Install and prepare mandral | 344 | 344 | 0
0
7b | Wind TF coil | 2400 | 1520 | 880
Position starting conductor & wind layer #1
Braze lead spur
Position 2nd. Conductor and braze layer 1 to 2
Wind layer #2 -
Position 3rd. Conductor & wind layer 3
Perform locking braze layers 2 to 3
Position 4nd. Conductor and braze layer 3 to 4
Wind layer #4/ Torch braze
Secure and transfer TF coil to station #3
8 | Station No. 3- Ground wrapping & Mold Application
8a | Ground wrap TF coil | 880 | 880 | 0
| Notes: |  | 0 | 0
| 1) 2-man teams can apply approximately 5 wraps per minute. (2" wide tape) |  | 0 | 0
| 2) (6) half-lapped layers of glass & (2) half-lapped layers of glass/Kapton |  | 0 | 0
| 3) Circumference: approx. 353 inches |  | 0 | 0
| 4) Approximately 70 minutes to complete (1) half-lapped layer |  | 0 | 0
| 5) Approximately 10 hours to complete groudwrap operation |  | 0 | 0
|  |  | 0 | 0
8b | Install TF coil in mold | 640 | 640 | 0
|  |  | 0 | 0
8c | Transport TF to NCSX Coil Facility
9 | VPI TF Coil
| Assumption: VPI (2) TF coils together | 0 | 0
|  | 0 | 0
9a | Transfer TF coil to Autoclave | 288 | 288 | 0
|  | 0 | 0 | 0
9b | Prepare TF coil for VPI
| Connect fill lines, manifolds, hookup thermocouples & leak check | 576 | 432 | 144
|  | 0 | 0 | 0
9c | VPI TF coil
| Vacuum pumpdown mold and autoclave | 216 | 288 | -72
| Epoxy fill coil | 432 | 576 | -144
| Temperature rampup and Cure | 0 | 432 | -432
| [parallel activity] Station cleanup during cure | 216 | 72 | 144
| Temperature rampup and Post cure | 144 | 288 | -144
| Temperature rampdown | 72 | 144 | -72
| Cleanup & ready autoclave | 288 | 72 | 216
| Remove TF coil from mold/clean mold | 576 | 144 | 432
10 | Station No. 6- Electrical Test Station
| Perform electrical & Pressure Tests | 288 | 288 | 0
Warm tests (room temperature) only
| TOTAL = | 13080 | 10328 | 2752

## VENDOR FAB
NCSX TF FABRICATION BY VENDOR
| Assumptions: | [7 empty] | Rates from Everson-Tesla | Rate | EM | 100
| 1) Conductors will arrive in 90to 100 ft. length spools | [8 empty] | per Hr | SM | 65
| 2) Conductors need to be primed | [9 empty] | TB | 55
| 3) Induction Braze joints | [9 empty] | DM | 76
| 4) Four conductor spools per TF coil | [9 empty] | M&S Overhead = | 21%
|  |  | Duration | Start | End | EAEM | EETB | EADM | EMSM | EMSM | EMTB | M&S
| TASK DESCRIPTION |  |  |  |  | Engr | Tech | Designer |  | machinist | Tech |  | 21%
|  |  | Days |  |  | hours | hours | hours | hours | hours | hours | w/o G&A | w/G&A
1 | ENGINEERING and OVERSIGHT
| Design tooling and winding facility |  |  |  |  | 144 |  | 300
| Field Oversight FY05 |  |  |  |  | 240 |  |  | 0
| Field Oversight FY06 |  |  |  |  | 576 |  |  | 0
| Field Oversight FY07 |  |  |  |  | 144 |  |  | 0 |  |  |  |  | Total Cost
| Sub total (hours) |  |  |  |  | 1104 |  | 300 | 0 |  |  |  |  | 133200
| Sub total cost |  |  |  |  | 110400 |  | 22800 | 0
2 | Braze Qualification Program
| Fabricate work coils | [8 empty] | 0 | 0
| Prepare braze samples | [8 empty] | 80
| Develop braze technique | [9 empty] | 60
| Braze conductor samples | [9 empty] | 60 |  |  | Total cost
| Test brazed samples (by PPPL) | [7 empty] | 80
| Sub total (hours) | [7 empty] | 80 | 80 | 120 |  |  | 17000
| Sub total cost | [7 empty] | 5200 | 5200 | 6600
|  |  | Duration | Start | End | EAEM | EETB | EADM | EMSM | EMSM | EMTB | M&S
| TASK DESCRIPTION |  |  |  |  | Engr | Tech | Designer |  | machinist | Tech
|  |  | Days |  |  | hours | hours | hours | hours | hours | hours | w/o G&A | w/G&A
3 | EQUIPMENT and TOOLING COSTS
Fabricate Coil WIndingTooling/Fixtures
| Recondition turning fixture | [9 empty] | 0 | 0
| Winding clamps | [8 empty] | 0 | 0 | 0
| Taping machine conditioning | [8 empty] | 0 | 0 | 0
| Winding mandrel | [8 empty] | 120 | 160 | 5000
| Miscellaneous tools and equipment | [10 empty] | 3000
| TF mold (1) | [8 empty] | 180 | 180 | 5000
| Braze unit | [10 empty] | 0 |  | Total cost
| Sub total (hours) | [8 empty] | 300 | 340 |  |  | 53930
| Sub total cost | [8 empty] | 19500 | 18700 | 13000 | 15730
4 | AREA PREPARATION
| Setup winding facility | [7 empty] | 0 | 0 | 120 | 1000 | 1210
Install winding table
Setup copper delivery system
Install taping machine
Complete setup of facility
| Build cleanroom | [7 empty] | 0 |  | 120 | 10000 | 12100 | Total Cost
| Sub total (hours) | [7 empty] | 0 | 0 | 240 |  |  | 26510
| Sub total cost | [7 empty] | 0 | 0 | 13200 | 11000 | 13310
5 | MATERIAL & SUPPLIES
5a | Coil Supplies
| 1) Insulation [t/t and groundwrap] | [10 empty] | 80000
| 2) Epoxy- CTD-101K | [10 empty] | 60000
[8 gallons per coil @ $1500.00 per kit- assume 20 injections]
| 5) Copper conductor | [10 empty] | 80000
| 6) G-11 fillers [Fillers for transitions and leads] | [8 empty] | 480 | 80 | 4000
| 7) Lead blocks | [8 empty] | 144 | 40 | 4680
| 8) Safety and PPE equipment and supplies | [10 empty] | 4000
| 9) Miscellaneous supplies [Includes rags, hardware, braze material etc.] | [10 empty] | 8000
| 10) Primer | [10 empty] | 8000
5b | VPI Supplies
| 1) Misc VPI supplies | [10 empty] | 8000
| 2) Disposable VPI hardware | [9 empty] | 432
| valves | [10 empty] | 10000
| High & low temperature vac. Tubing | [10 empty] | 20000
| Copper tubing | [10 empty] | 5000 |  | Total Cost
| Sub total (hours) | [8 empty] | 624 | 552 | 291680 | 352932.8 | 423852.8
| Sub total cost | [8 empty] | 40560 | 30360
Task | TASK DESCRIPTION |  | Working | Shifts | No. of | EMTB
No. |  |  | Days | per day | Tech. | man-hours
6 | Station No. 1- Conductor Preparation |  | 21 | Total working days
6a | Receive conductors | [7 empty] | Hours | Cost
| Unload and sample measure each spool |  | 3 | 1 | 1.5 | 36 |  | TOTAL | 180 | 9900
6b | Flush inner bore |  | 18 | 1 | 1 | 144
6c | Clean, prime and bag conductor |  | 0 | 0 | 0 | 0
Task | TASK DESCRIPTION |  | Working | Shifts | No. of | No. of |  | Working | Shifts | No. of | No. of | No. of | Man-hrs | Total
No. |  |  | Days | per day | Tech. | man-hours |  | Days | per day | Tech. | man-hours | Items | 2 thru 18 | Man-hrs
7 | Station No. 2- Coil Winding |  | 14 | Total working days 1st. coil |  |  |  | 7.5 | Total working days coils 2 thru 18
7a | Prepare winding station for winding TF coil |  | 3 |  |  | 72 |  | 1 |  |  | 16 | 17 | 272 | 344
| Install and prepare mandral |  | 3 | 1 | 3 | 72 |  | 1 | 1 | 2 | 16
7b | Wind TF coil |  | 11 |  |  | 160 |  | 6.5 |  |  | 80 | 17 | 1360 | 1520
| Position starting conductor & wind layer #1 |  | 2 | 1 | 2 | 32 |  | 1 | 1 | 1.5 | 12 | 17
| Braze lead spur |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Position 2nd. Conductor and braze layer 1 to 2 |  | 3 | 1 | 2 | 48 |  | 1 | 1 | 1.5 | 12
| Wind layer #2 - |  | 1 | 1 | 2 | 16 |  | 0.5 | 1 | 1.5 | 6
| Position 3rd. Conductor & wind layer 3 |  | 1 | 1 | 2 | 16 |  | 0.5 | 1 | 1.5 | 6
| Perform locking braze layers 2 to 3 |  | 1 | 1 | 2 | 16 |  | 1 | 1 | 1.5 | 12
| Position 4nd. Conductor and braze layer 3 to 4 |  | 1 | 1 | 2 | 16 |  | 1 | 1 | 1.5 | 12
| Wind layer #4/ Torch braze |  | 1 | 1 | 2 | 16 |  | 1 | 1 | 1.5 | 12 |  |  | 1864
| Secure and transfer TF coil to station #3 |  | 1 | 1 | 3 | 24 |  | 0.5 | 1 | 2 | 8 |  | Total | 102520
8 | Station No. 3- Ground wrapping & Mold Application |  | 8 | Total working days 1st. coil |  |  |  | 5 | Total working days coils 2 thru 18
8a | Ground wrap TF coil |  | 4 | 1 | 2 | 64 |  | 3 | 1 | 2 | 48 | 17 | 816 | 880
Notes:
1) 2-man teams can apply approximately 5 wraps per minute. (2" wide tape)
2) (6) half-lapped layers of glass & (2) half-lapped layers of glass/Kapton
3) Circumference: approx. 353 inches
4) Approximately 70 minutes to complete (1) half-lapped layer
5) Approximately 10 hours to complete groudwrap operation
8b | Install TF coil in mold |  | 4 | 1 | 3 | 96 |  | 2 | 1 | 2 | 32 | 17 | 544 | 640
1520
[13 empty] | Total | 83600
Task | TASK DESCRIPTION |  | Working | Shifts | No. of | No. of |  | No. of | Total
No. |  |  | Days | per day | Tech. | man-hours |  | Items | Manhrs
9 | VPI TF Coil |  | 7.5 | Total working days per coil
Assumption: VPI (1) TF coils together
9a | Transfer TF coil to Autoclave |  | 1 | 1 | 2 | 16 |  | 18 | 288
9b | Prepare TF coil for VPI | [7 empty] | 0
| Connect fill lines, manifolds, hookup thermocouples & leak check |  | 1.5 | 1 | 2 | 24 |  | 18 | 432
0
9c | VPI TF coil |  | 6.5 | [5 empty] | 0
| Vacuum pumpdown mold and autoclave |  | 1 | 1 | 2 | 16 |  | 18 | 288
| Epoxy fill coil |  | 1 | 2 | 2 | 32 |  | 18 | 576
| Temperature rampup and Cure |  | 1 | 3 | 1 | 24 |  | 18 | 432
| [parallel activity] Station cleanup during cure |  | 0.5 | 1 | 1 | 4 |  | 18 | 72
| Temperature rampup and Post cure |  | 1 | 2 | 1 | 16 |  | 18 | 288
| Temperature rampdown |  | 1 | 1 | 1 | 8 |  | 18 | 144 |  | Hours | Cost
| Cleanup & ready autoclave |  | 0.5 | 1 | 1 | 4 |  | 18 | 72 | Total | 2736 | 150480
| Remove TF coil from mold/clean mold |  | 1 | 1 | 1 | 8 |  | 18 | 144
10 | Station No. 6- Electrical Test Station |  | 1
Hours
10a | Perform electrical & Pressure Tests |  | 1 | 1 | 2 | 16 | 0 | 18 | 288 |  | 288
| Warm tests (room temperature) only | [10 empty] | Cost
10b | Shipping to PPPL (2 coils per trip @ $3k/trip | [7 empty] | 27000 | Total |  | 42840
| Engineering & Oversight |  | 133200
| Brazing qualification |  | 17000
| Equip. & Tooling |  | 53930
| Area Preparation |  | 26510
| Materials & supplies |  | 423852.8
| Conductor prep |  | 9900
| Coil winding |  | 102520
| Ground wrap/mold |  | 83600
| VPI |  | 150480
| Testing & Shipping |  | 42840 |  |  |  | *Note: This estimate assumes vendor can provide an induction braze unit.
Everson-Tesla may not have access to one and may charge us $85K additional
| TF Fabrication |  | 1043832.8 |  |  |  | It is unknown if other potential vendors have an induction braze unit
| Vendor Contingency | 20% | 208766.56
| Vendor Profit | 10% | 125259.936
| Total Billed by Vendor |  | 1377859.296
| PPPL MHX on 1st $500k @ | 25/40% | 147650
| PPPL G&A on MHX @ | 13% | 19194.5 | ECP21
| Total With PPPL G&A |  | 1544703.796 | 1162679
| Kalish WBS mgr oversight @ 75for 1st coil,25% on balance |  | 145173.6 | 113900
over 17 mo. Contract period
| Kalish trips to vendor for Vendor supervision (3days/mo. x17) |  | 70012.8
| Kalish travel@$1.5k/mo.plus G&A |  | 43222.5 | 1e-05
| TOTAL COST FOR OUTSIDE FAB= |  | 1803112.696 | 1276579
| Increase from baseline |  | 526533.696

## xx
MC & TF VPI Cost Efficiency Analysis
| Bottoms-up estimate | [11 empty] | Top-down estimate (schedule based)
Baseline Modular Coil VPI Cost Estimate
|  |  | TASK DESCRIPTION | Working | Shifts | No. of | No. of | No. of | Total
|  |  |  | Days | per day | Tech. | man-hours | Items | Manhrs
|  |  | Station No. 5- VPI Coil | 12 | Total working days per coil
|  |  | Transfer modular coil to Autoclave | 1 | 1 | 4 | 32 | 18 | 576
0
|  |  | Prepare modular coil for VPI | 3 |  |  |  |  | 0
|  |  | Connect fill lines, manifolds, hookup thermocouples & leak check | 3 | 1 | 4 | 96 | 18 | 1728
0
|  |  | VPI modular coil | 8 |  |  |  |  | 0
|  |  | Vacuum pumpdown mold and autoclave | 1 | 1 | 3 | 24 | 18 | 432
|  |  | Epoxy fill coil | 1 | 3 | 4 | 96 | 18 | 1728
|  |  | Temperature rampup and Cure | 1 | 3 | 3 | 72 | 18 | 1296
|  |  | [parallel activity] Station cleanup during cure | 1 | 1 | 3 | 24 | 18 | 432
|  |  | Temperature rampup and Post cure | 1 | 2 | 2 | 32 | 18 | 576
|  |  | Temperature rampdown | 1 | 1 | 1 | 8 | 18 | 144
|  |  | Cleanup & ready autoclave | 2 | 1 | 4 | 64 | 18 | 1152 | Total | 8064
448
TF Coil VPI Cost Estimate
|  |  | TASK DESCRIPTION | Working | Shifts | No. of | No. of | No. of | Total
|  |  |  | Days | per day | Tech. | man-hours | Items | Manhrs
|  |  | VPI TF Coil | 9 | Total working days per coil
Assumption: VPI (2) TF coils together
288 |  |  | Transfer TF coil to Autoclave | 1 | 1 | 4 | 32 | 9 | 288
0 |  |  | Prepare TF coil for VPI | [5 empty] | 0
576 |  |  | Connect fill lines, manifolds, hookup thermocouples & leak check | 2 | 1 | 2 | 32 | 18 | 576
0 | [8 empty] | 0
0 |  |  | VPI TF coil | 8 |  |  |  |  | 0
216 |  |  | Vacuum pumpdown mold and autoclave | 1 | 1 | 3 | 24 | 9 | 216
432 |  |  | Epoxy fill coil | 1 | 2 | 3 | 48 | 9 | 432
0 |  |  | Temperature rampup and Cure | 0 | 0 | 0 | 0 | 9 | 0
216 |  |  | [parallel activity] Station cleanup during cure | 1 | 1 | 3 | 24 | 9 | 216
144 |  |  | Temperature rampup and Post cure | 1 | 2 | 1 | 16 | 9 | 144
72 |  |  | Temperature rampdown | 1 | 1 | 1 | 8 | 9 | 72 |  | Hours
288 |  |  | Cleanup & ready autoclave | 2 | 1 | 2 | 32 | 9 | 288 | Total | 2808
576 |  |  | Remove TF coil from mold/clean mold | 2 | 1 | 2 | 32 | 18 | 576
[14 empty] | Assume 4 men full time to man the VPI station during this period = | 10416 | hours
[14 empty] | sparatic manning of VPI station for these 6 MC's = | 2560 | hours
[10 empty] | Total hours = | 10872 |  |  | Total hours = | 12976
Conclusion; no savings can be assumed

## Sheet2
NCSX
TF COIL
MAKE or BUY COST ANALYSIS
2005-02-24
Mike Kalish
Jim Chrzanowski
1) Summary Conclusion
2) Cost Summary Table
3) Manhour Summary Table
4) Detail PPPL Estimate (J.Chrzanowski)
5) Detail Vendor Estimate (M.Kalish)