Modular coil interface design review schedule

June 29	FDR for outboard shims (done)

- review design of universal outboard shim

- shim drawings ready to be released for fabrication pending resolution of chits

July 27		FDR for balance of outboard bolted joint assembly

- review bolt kit drawings

- review analysis of bolted joint components

- bolt kit components largely on order already because of long lead times and need for testing – drawings for remaining components to be released for fabrication

August 1	PDR for welded shims (AA/AB/BC)

- establish design basis for welded shims

- review results of weld trials

- review design basis analyses

- review plan for completion of final design

- design definition and feasibility to be established

- shim material to be released for procurement

August 2	PDR for CC interface

- establish design basis for CC interface

- review bolt kit design and analysis for additional CC bolt locations

- review design and analysis of sliding interface

- review plan for completion of final design including access studies on mockups, remote tooling development activities, and qualification of sliding interface

- design definition and feasibility to be established

- CC flange design modifications to be released for fabrication

September 4	FDR for welded shims (AA/AB/BC)

- review shim drawings including weld details

- review weld procedure

- review updated analyses

- inboard shim drawings to be released for fabrication

- weld procedure defined for field period assembly

January 7	FDR for CC interface

- review shim drawings

- review results of the bolt reach and access studies

- review design of remote tooling development

- review results of sliding interface qualification testing

- review updated analysis results

- CC shim drawings to be released for fabrication

- bolt kit component drawings to be released for fabrication

- sliding interface drawings to be released for fabrication