## P3
NCSX MIE Project FTE's (incl contingency)
|  | FY 2005 | FY 2006 | FY 2007 | FY 2008
| B///CB - PPPL Project Clerical | 0.6 | 0.6 | 0.5 | 0.1
| EA//EM - PPPL Analysis engineer | 6.6 | 5.6 | 2.8 | 0.8
| EA//SM - PPPL Designer | 3.1 | 4.3 | 2
| EC//EM - PPPL Comuter Engineer | 0 | 0.4 | 4.1 | 0.2
| EC//SM - PPPL Computer Senior Tech |  |  | 1
| EE//AM - | 0.1 | 0.1 | 0.1
| EE//EM - PPPL Electrical engineer | 0.9 | 2.5 | 1.5 | 0.7
| EE//SM - PPPL Electrical Senior Tech | 0.1 | 2.2 | 2.9 | 1
| EE//TB - PPPL Electrical Technician | 0.3 | 2.4 | 1.5 | 0.4
| EM//EM - PPPL FO&M Engineer | 2.6 | 3 | 5 | 1.7
| EM//SM - PPPL FO&M Senior Tech | 2.4 | 5.5 | 9.3 | 3.2
| EM//TB - PPPL FO&M Technician | 8.3 | 20.4 | 21.9 | 3.7
| FC//AM - PPPL P&CO am | 1 | 1 | 0.8 | 0.3
| FC//EM - PPPL P&CO em | 0.5 | 0.5 | 0.2
| R///RM2 - PPPL Scientist pdg2 | 0.1 | 0.3 | 0.3 | 0.2
| R///RM3 - PPPL Scientist pdg3 | 1 | 1 | 0.6 | 0.1
| SH//TB - HP Techs | 0.7 | 0.7 | 0
|  | 28.3 | 50.5 | 54.5 | 12.4
RES | None | OCT FY05 | NOV FY05 | DEC FY05 | JAN FY05 | FEB FY05 | MAR FY05 | APR FY05 | MAY FY05 | JUN FY05 | JUL FY05 | AUG FY05 | SEP FY05 | OCT FY06 | NOV FY06 | DEC FY06 | JAN FY06 | FEB FY06 | MAR FY06 | APR FY06 | MAY FY06 | JUN FY06 | JUL FY06 | AUG FY06 | SEP FY06 | OCT FY07 | NOV FY07 | DEC FY07 | JAN FY07 | FEB FY07 | MAR FY07 | APR FY07 | MAY FY07 | JUN FY07 | JUL FY07 | AUG FY07 | SEP FY07 | OCT FY08 | NOV FY08 | DEC FY08 | JAN FY08 | FEB FY08 | MAR FY08 | APR FY08 | MAY FY08 | JUN FY08 | JUL FY08 | AUG FY08 | SEP FY08
| B///CB - PPPL Project Clerical | 0.5 | 0.5 | 0.6 | 0.5 | 0.5 | 0.6 | 0.5 | 0.5 | 0.6 | 0.5 | 0.6 | 0.6 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.6 | 0.5 | 0.6 | 0.6 | 0.5 | 0.6 | 0.5 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.5 | 0.4 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1
| EA//EM - PPPL Analysis engineer | 7.7 | 8 | 6.2 | 5.7 | 4.2 | 4.5 | 5.2 | 6.3 | 7.3 | 5.8 | 5.9 | 5.6 | 4.8 | 4.7 | 4.6 | 5 | 4.8 | 5.6 | 5 | 5.6 | 5.3 | 5.1 | 6.1 | 5.4 | 4.7 | 3.9 | 3 | 2.9 | 2.2 | 2.3 | 2.2 | 2.3 | 2.2 | 2.2 | 2 | 1.5 | 1.1 | 1 | 1 | 1.1 | 1 | 1 | 1.1 | 1.1
| EA//SM - PPPL Designer | 4.9 | 2.7 | 2.1 | 2 | 1.9 | 2.4 | 3.1 | 3.9 | 3.9 | 2.5 | 2.4 | 2.5 | 5.9 | 5.8 | 5 | 6.1 | 4.4 | 4.1 | 2.4 | 2.4 | 2.7 | 2.5 | 2.9 | 2.6 | 3 | 2.6 | 1.8 | 2.1 | 1.9 | 1.9 | 1.5 | 1.5 | 1.3 | 1.4 | 1.4 | 1.2
| EC//EM - PPPL Comuter Engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0.4 | 1.6 | 1.9 | 3.4 | 3.2 | 2.7 | 4 | 3.8 | 4.2 | 4.2 | 4.5 | 4.1 | 3.6 | 4 | 2.7 | 0.9 | 0.8 | 0.3
| EC//SM - PPPL Computer Senior Tech | [27 empty] | 0.6 | 1 | 1.4 | 1.7 | 1.8 | 1.7 | 1.1 | 1.2 | 0.7
| EE//AM - | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| EE//EM - PPPL Electrical engineer | 1.9 | 1.3 | 0.9 | 0.8 | 0.7 | 1 | 1.1 | 0.6 | 0.4 | 0.3 | 0.4 | 0.5 | 3.7 | 3.7 | 3 | 3.4 | 2.3 | 1.7 | 1.6 | 1.8 | 1.7 | 1.5 | 1.6 | 1.3 | 2.2 | 2.8 | 2.1 | 2.2 | 1.8 | 1.7 | 0.8 | 0.6 | 0.6 | 0.5 | 0.6 | 1.2 | 1.6 | 1.4 | 1 | 0.7 | 0.6 | 0.6 | 0.7 | 0.7
| EE//SM - PPPL Electrical Senior Tech | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0.3 |  |  |  |  | 0.1 | 1 | 1 | 1 | 2 | 2.3 | 3.2 | 2.6 | 2.6 | 2.6 | 2.1 | 2.1 | 1.4 | 2.7 | 3 | 3 | 3.2 | 2.6 | 2.4 | 2.7 | 3.1 | 2.4 | 2.4 | 2.6 | 1.5 | 1.5 | 1.3 | 1.3 | 1.4 | 1.3 | 1.3 | 1.4 | 1.4
| EE//TB - PPPL Electrical Technician | 0.4 | 0.4 | 0.3 | 1.7 | 0.3 |  | 0.4 |  |  |  |  | 0.1 | 0.8 | 1 | 1.2 | 1.6 | 1.9 | 2.6 | 2.6 | 2.9 | 3.1 | 2.7 | 3.4 | 3 | 4.1 | 4.1 | 2.6 | 2.3 | 1.1 | 0.6 | 0.1 |  |  |  | 0.1 | 1.4 | 1.7 | 1.5 | 0.7
| EM//EM - PPPL FO&M Engineer | 3.3 | 2.2 | 2.2 | 2.8 | 2 | 2.3 | 2.4 | 2.2 | 2.3 | 2.1 | 2.5 | 2.1 | 3 | 2.8 | 2.6 | 2.7 | 2.4 | 2.7 | 2 | 2.3 | 2.6 | 3 | 3.7 | 3.8 | 5.3 | 4.7 | 3.7 | 4.3 | 4.7 | 5.2 | 4.5 | 4.4 | 4 | 4 | 5 | 5 | 4.7 | 3.3 | 1.9 | 1.4 | 1.3 | 1.3 | 1.4 | 1.4 | 0.7 | 0.7 | 0.7 | 0.1
| EM//SM - PPPL FO&M Senior Tech | 5.1 | 1.5 | 0.7 | 1.5 | 1.6 | 2.1 | 1.9 | 2.3 | 2.8 | 2.4 | 2.2 | 2.1 | 4.2 | 3.9 | 3.5 | 4 | 3.6 | 5 | 4.2 | 6 | 7.1 | 6.2 | 7.2 | 5.5 | 8.8 | 9.4 | 8.7 | 12.7 | 10.4 | 10.4 | 8.3 | 7.3 | 5.9 | 5.6 | 7.9 | 6.6 | 7.5 | 5.1 | 3.8 | 3.5 | 3.3 | 3.3 | 3.5 | 3.5 | 0.7 | 0.7 | 0.7 | 0.1
| EM//TB - PPPL FO&M Technician | 7 | 4.2 | 3.7 | 3.4 | 3.4 | 4.9 | 3.6 | 7.7 | 13.5 | 12.3 | 14.1 | 12.9 | 16.6 | 16 | 14.6 | 17.9 | 16.2 | 19.3 | 17 | 21.9 | 24.9 | 19.4 | 22.2 | 19 | 25.4 | 28 | 24.8 | 31.4 | 22.4 | 23.1 | 18.4 | 15.8 | 12.3 | 11.7 | 18 | 10.1 | 12.6 | 7.1 | 5.3 | 4.4 | 2.6 | 2.6 | 2.8 | 2.8
| FC//AM - PPPL P&CO am | 0.9 | 0.8 | 0.9 | 0.8 | 0.8 | 0.9 | 0.9 | 0.9 | 0.9 | 0.8 | 0.9 | 0.9 | 0.9 | 0.8 | 0.9 | 0.9 | 0.8 | 1 | 0.8 | 0.9 | 0.9 | 0.8 | 1 | 0.9 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.4 | 0.3 | 0.3 | 0.4 | 0.4 | 0.4 | 0.4 | 0.3
| FC//EM - PPPL P&CO em | 0.4 | 0.4 | 0.5 | 0.4 | 0.4 | 0.5 | 0.4 | 0.4 | 0.5 | 0.4 | 0.5 | 0.5 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.5 | 0.4 | 0.5 | 0.5 | 0.4 | 0.5 | 0.4 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1
| ORNL35 - ORNL Travel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ORNL41 - ORNL M&S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ORNL81 - ORNL cost
| ORNLAM - ORNL Admin | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0
| ORNLEM - ORNL Engineer | 12.7 | 7.7 | 7.4 | 8.4 | 6.8 | 6.9 | 7 | 7 | 5.7 | 5.6 | 6.2 | 5.1 | 4 | 3.8 | 4.7 | 5.3 | 5 | 5.9 | 5.2 | 5.7 | 4.7 | 4 | 4.6 | 4 | 2.4 | 2.1 | 1.4 | 1.5 | 1.3 | 1.3 | 1.1 | 1.2 | 1.1 | 1.1 | 1.1 | 0.4 | 1.5 | 1.3 | 1.2 | 1.5 | 1.3 | 1.3 | 1.5 | 1.4 | 0.2
| ORNLRM - ORNL Scientist | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.2 | 0.2 | 0.3 | 0.2 | 0.3 | 0.4 | 0.4 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| R///RM2 - PPPL Scientist pdg2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.4 | 0.4 | 0.4 | 0.5 | 0.5 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.3 | 0.3 |  | 0.1 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.1 | 0 | 0.8 | 1 | 0.9 | 0.4
| R///RM3 - PPPL Scientist pdg3 | 0.9 | 0.8 | 0.9 | 0.8 | 0.8 | 0.9 | 0.9 | 0.9 | 0.9 | 0.8 | 0.9 | 0.9 | 0.9 | 0.8 | 0.9 | 0.9 | 0.8 | 1 | 0.8 | 0.9 | 0.9 | 0.8 | 1 | 0.9 | 0.6 | 0.5 | 0.5 | 0.6 | 0.5 | 0.6 | 0.5 | 0.6 | 0.5 | 0.6 | 0.6 | 0.5 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| SH//TB - HP Techs | 0.7 | 0.7 | 0.6 | 0.7 | 0.7 | 0.8 | 0.7 | 0.7 | 0.7 | 0.7 | 0.8 | 0.7 | 0.7 | 0.7 | 0.6 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0