## Risk Register
[7 empty] | Likelihood: VL: P>80% L: 80%>P>40% U: 40%>P>10% VU: P<10% NC: P<1% | Consequences: Negligible: ≤$100k, ≤0.5 month Marginal: $100k-$500k, 0.5-1 month Significant: $500k-$1M, 1-3 months Critical: $1M-$5M, 3-6 months Crisis: >$5M, > 6 months
No. | Affected Jobs (absorb the impacts) | Risk Description | Mitigation Plan (& job where budgeted) | Deadline to Retire Risk or Absorb Impact | Owner | Current Status (As of March 21, 2008) | Likelihood of Occurrence | Consequences | Risk Ranking | Basis of Estimate | Cost Impact ($k) | Critical Path Schedule Impact (mos) | Cost and schedule impact calculation basis |  |  | consequences |  |  | Rank Value
MANAGEMENT & ORGANIZATION RISKS | [13 empty] | High | 2 | cost | sched | max
Mgmt-1 |  | Loss or prolonged unavailability of certain key personnel from the project could substantially impact the schedule. | See mitigation plans for individuals listed below. | [10 empty] | Moderate | 20
a | 1901 | Mike Cole (ORNL) Loss of "corporate memory" of stellarator core design intent, delayed turnaround on Title III issues andproblem resolution might impact FPA schedule. | Brad Nelson is been budgeted (15%) on the project. Should Cole become unavailable, Nelson would step in and handle Cole's responsibilities until a suitable longer term solution was implemented. ORNL Mgt., Job 1901 |  | Harris | Oak Ridge is investigating securing additional engineering support for Mike Cole. Currently reviewing resumes and re-evluationg work load to determine whether additional staff will indeed be needed. | VU | Marginal | Low | Estimated impact is <0.5 months on the critical path. | 0 | 0.5 |  | Low | 58 | 1 | 2 | 2 | VU2
b | 1810 7503 | Tom Brown, Art Brooks, Bob Ellis "Back office" support for FPA and final assembly becomes a chronic bottleneck, stretching out the time required to complete assembly operations | Additional support budgeted for Brown, Brooks, and Ellis providing "2 deep" back office support. Should be available to mitigate peak demands once training in key skills is completed. Jobs 8203, 8204, 8205. Identify backup personnel for "two deep" back office support & provide duplication of critical skills needed. Eng. Mgt. (Heitzenroeder) | After first MCHP | Heitzenroeder | "Two deep" back office support is now in place. Mark Smith has worked in all areas of back office support and will provide back-up for either Tom Brown, Art Brooks, or Bob Ellis as needed to handle over-loads, cover during vacations, etc. A new analyst, Han Zhang, has recently been hired and is providing support to Art Brooks. A new design engineer, Shri Avisarala, has been hired and is expected to start soon and will be working with Tom Brown to provide additional back-up in design integration. Design support has also been significantly increased: Gerald Paluzzi is supporting Bob Ellis his on non-NCSX tasks to help balance his workload ; Tod Cruickshank is working with Fred Dahlgren and Tom Brown on NCSX structures, and Richard Upcavage is working with Tom Brown on facilities and cryostat integration. . | VU | Significant | Low | Estimated impact is <2 months on the critical path. Cost impact covers up to 2 months of FPA/final assembly. | 0 | 2 |  | Opportunity | 2 | 1 | 3 | 3 | VU3
c | 8202 | Phil Heitzenroeder (PPPL) | Larry Dudek can step in to assume Phil's responsibilities as Engineering Manager for Design and Procurement. Erik Perry can step into Larry's role as Construction Manager. As time goes on (and the field period assembly is completed), Mike Viola can continue (with Erik's help) with final machine assembly. | After final machine design and major procurement activities are completed. | Williams | Larry Dudek, Erik Perry and Mike Viola are already intimately involved in NCSX design and construction activities and are able to assume varying responsibilities on short notice. | VU | Marginal | Low | Estimated impact is <0.5 months on the critical path. No impact on FPA cost because impacted personnel would be assigned to other activities. | 0 | 0.5 |  |  |  | 1 | 2 | 2 | VU2
d | 8101 | Ron Strykowsky | Develop a succession plan Business Ops. Dept. |  | E. Winkler |  | VU | Marginal | Low | Cost impact = 50% cost increment cost for 1 year spool-up time for another senior project controls person | 115 | 0 | Loaded estimated annual cost = $230k x 50% = $115k |  |  | 2 | 1 | 2 | VU2
e | 5301 5401 5501 5601 | Loss of staff with experience in specialized software delays operation of Central I&C system. | Staff have recently been brought on board in anticipation of growing NCSX I&C needs. The planned shutdown of NSTX after FY10 will increase the availability of similar resources for NCSX. | NSTX Shutdown (following FY10) | P. Sichta S. Baumgartner A. vonHalle | Staff are presently on-board and available to handle the FY08-10 work plan. More will be available following the shutdown of NSTX. | VU | Marginal | Low | Estimated impact is <0.5 months on the critical path. No impact on WBS 5 cost because impacted personnel would be assigned to other activities. | 0 | 0.5 |  |  |  | 1 | 2 | 2 | VU2
f | 1901 8203 | Design integration effort needs to increase to manage space allocations inside the cryostat and in the test cell | Staff has been increased recently. Periodically reassess adequacy. | Sept., 2008 | P. Heitzenroeder | Staff increases in progress. | VU | Marginal | Low | 1 person-year? | 300 | 0 |  |  |  | 2 | 1 | 2 | VU2
Mgmt-2 | 4501 | Loss of knowledgeable staff delays operation of legacy power supplies. | Train staff in legacy systems. Eng. Dept. | Power Systems ISTP | A. von Halle | Staff presently assigned to NSTX are available to backup the staff presently responsible for the NCSX power supply work scope | VU | Marginal | Low | Estimated impact is <0.5 months on the critical path. No impact on WBS 4 cost because impacted personnel would be assigned to other activities. | 0 | 0.5 |  |  |  | 1 | 2 | 2 | VU2
Mgmt-3 | 8101 | Labor rates may be significantly lower than projected Opportunity | None |  | Strykowsky | Current estimatesreflect latest labor rates. Will revisit in semi-annual EAC update. | U | Opportunity | Opportunity | Retirements / resignations replaced with younger lower-salaried staff | -1000 | 1 |  |  |  | #N/A | 3 | #N/A | #N/A
Mgmt-4 | 8101 | GPP projects not completed in time to support project needs | The crane and the HVAC systems are the main GPP projects that would need to be completed. The GPP projects have strong Lab and DOE oversight. Ample float is provided in the schedule so project delays due to GPP delays are not considered credible (P<1%). Eng. & Infrastructure Dept. | End of FY-09 | Perry | All GPP projects supporting the NCSX inhabiting the C-Site test cell are presently scheduled for completion prior to the end of FY09. | NC | Significant | Low |  | 0 | 1 |  |  |  | 1 | 3 | 3 | NC3
Mgmt-5 | 8101 | CR may delay funding to project. | None |  | Strykowsky | Current estimates reflect latest OFES guidance. Will revisit in semi-annual EAC update. | U | Significant | Moderate | Expected increase in FY-09 may be delayed by CR. | 0 | 2 |  |  |  | 1 | 3 | 3 | U3
TECHNICAL RISK - Generic Assembly Risks
Assy-1 | 1810 | Station 3: cost and schedule grows when Assembly Sequence Plan fully matures | Expedite Tooling Design and Assembly Sequence Plan Jobs 1803 / 8203 | When Station 3 Tooling FDR is complete | Brown | Future Risk | VL | Marginal | Moderate | 15% increase in time required for each F.P | 240 | 0.675 | Station 3 estimate of $1,579k x 15% plus schedule stretchout for the time station 3 is on the c.p (4.5mo x 15% (stretchout cost quantified and added separately) |  |  | 2 | 2 | 2 | VL2
Assy-2 | 1815 | Station 5: cost and schedule grows when Assembly Sequence Plan fully matures | Expedite Component Designs and Assembly Sequence Plan Jobs 1354, 1501, 1601, 8203 | Coil services PDRs | Brown | Future Risk | VL | Significant | High | 25% increase in time required for each F.P | 500 | 1.125 | Station 5 estimate of $1889k x 25% plus schedule stretchout for the time station 5 is on the c.p (4.5mo x 25% (stretchout cost quantified and added separately) |  |  | 3 | 3 | 3 | VL3
Assy-3 | 7503 | Station 6: cost and schedule grows when Assembly Sequence Plan fully matures | Expedite Component Designs, Plant Layout, and Assembly Sequence Plan Jobs 1701, 1702, 1803, 8215 | Cryostat PDR | Brown | Future Risk | VL | Significant | High | 15% increase in time required. | 650 | 2.175 | Station 6 estimate of $4,317k x 15%. plus schedule stretchout for the time station 6 is on the c.p (14.5mo x 15% (stretchout cost quantified and added separately) |  |  | 3 | 3 | 3 | VL3
Assy-4 | 1810/ 1815 7503 | Photogrammetry replaces laser tracker for some operations and saves time and money. (Opportunity) | Acquire equipment, develop experience, assess potential. New H/W in place & personnel being trained. 1810 / 1815 | ~Sept., 2008 | Dodson / Dudek | Future Risk | L | Opportunity | Opportunity | 33% reduction in metrology tasks? | -900.57 | -3 | 50% reduction in metrology crew labor cost =$2,729k x 50% . Reduction of metrology dependent tasks on the c.p. =172 days x .5 = 86 dyas = 4 months. (stretchout cost quantified and added separately) |  |  | #N/A | #N/A | #N/A | #N/A
Assy-5 | 1810/ 1815 7503 | Assembly delayed due to metrology equipment breakdowns or anomalies. | Maintain high availability via maintenance contracts, spares, and trained staff. F&OM Div. | Completion of FP#1, Station 5 | Priniski / Dudek | Have acquired new hardware and trained staff. | L | Significant | Moderate | 2 occurrences @ 0.5 month each. | 0 | 1 | (stretchout cost quantified and added separately) |  |  | 1 | 3 | 3 | L3
Assy-6 | 1810 1815 7503 | General purpose tooling/ lifting equipment (e.g. cranes) not available to support the schedule. | Budget lift equipment in FPA . Jobs 1810, 1815 | After Station 5? | Dudek | Lift equipment estimated in 1810 & 1815 WAF. | U | Marginal | Low | Up to 2 week impact on FPA and critical path. | 0 | 0.5 | (stretchout cost quantified and added separately) |  |  | 1 | 2 | 2 | U2
Assy-7 | 1302/1352 1354 | Permeability of components outside 3m from machine to test cell walls exceed the permeability limit of mu = 1.2. | Analyze existing conditions to determine if an issue exists. At worst case, may have to utilize more expensive low magnetic materials and/or utilize combination of rebiased trim and PF ring coils to mitigate field errors. | ~ May 1, 2008 | Brooks Kalish Chrzanowski | Brooks will work with Physics to determine issues and whether Project can accept mu > 1.2 cases. | U | Marginal | Low | Estimated cost of obtaining low magnetic materials. | 200 | 0 |  |  |  | 2 | 1 | 2 | U2
TECHNICAL RISKS - Station 2 Assembly
Stat2-2 | 1810 | Station 2: Unacceptable distortion in a field period when welding modular coil shims requiring rework and or chair installation. | Perform extensive welding R&D and careful monitoring during welding. Develop suitable weld procedures and train welders to minimize likelihood of unacceptable distortion. Job 1810 | After first MCHP | Viola | See response to RR #5. Current weld trials dealing with options to control distortion. | U | Significant | Moderate | Cut apart and re-weld two coils back together. Nominally a 2.5-man crew in 12 weeks. Fabrication and installation of chair nominally requires 2.5-man crew and ~3 weeks. | 135 | 1 | Risk has been reduced by mitigation (design and process changes) |  |  | 2 | 3 | 3 | U3
Stat2-3 | 1810 | Station 2. Unacceptable distortion in a field period when welding modular coil shims requiring complete disassembly and redesign and reassembly | Perform extensive welding R&D and careful monitoring during welding. Develop suitable weld procedures and train welders to minimize likelihood of unacceptable distortion. Job 1810 | After first MCHP | Viola | Weld trials should mitigate probability of occurance. | VU | Critical | Moderate | Cut apart and re-weld two coils back together. Nominally a 2.5-man crew in 12 weeks. | 150 | 3 |  |  |  | 2 | 4 | 4 | VU4
Stat2-5 | 1810 | Station 2. Risk of loss of weld equipment or trained personnel. | Procure more equipment & qualify more staff | After first MCHP | Viola | Future Risk | NC | Negligible | Low |  | 0 | 0.25 |  |  |  | 1 | 1 | 1 | NC1
Stat2-7 | 1810 | Station 2. Shim sets not adequate or fail - need to fabricate more shims and measure and test | Change to G10 design and fabricate more shims than needed Job 1810 | After first MCHP | Viola | Switched to G10 design | U | Significant | Moderate | Up to 3 week impact on FPA and critical path. | 0 | 1 |  |  |  | 1 | 3 | 3 | U3
Stat2-9 | 1810 | Station 2 - shim bag rupture & requires replacement | Pre-qulaify shim bags. Use wing chair in compression. Could require taking coil apart in worse case. Job 1810 | After first MCHP | Viola | Considered unlikely due to other mitigation plan options. | VU | Critical | Moderate | Rough assessment of cost and schedule impact of disassembling/re-assembling coils. 5 techs. X 3 months | 200 | 3 |  |  |  | 2 | 4 | 4 | VU4
Stat2-10 | 1810 | Station 2. Nose opens up while tightening outboard bolts | Change bolt tightening sequence Job 1810 | After first MCHP | Viola | Future Risk | U | Marginal | Low | Up to 2 week impact on FPA and critical path. | 0 | 0.5 |  |  |  | 1 | 2 | 2 | U2
Stat2-11 | 1810 | Station 2. Nose opens up while tightening outboard bolts. Change bolt tightening sequence is not adequate | Reexamine alignment criteria and potential impact Job 1810 | After first MCHP | Viola | Future Risk | U | Significant | Moderate | Up to 4 week impact on FPA and critical path. | 0 | 1 |  |  |  | 1 | 3 | 3 | U3
Stat2-13 | 1810 | Station 2. Modular coil damaged during assembly requiring significant rework to coil. (Complete coil re-fabrication excluded) | Equipment will be handled during FPA using carefully constructed procedures to minimize likelihood. Include provisions to guard against coil damage in FPA procedures. Job 1810 | After Station 2 | Viola | Station 2 assembly has just started. Repeated trial fits have served to benchmark processes. | L | Negligible | Low | Nominally repaired with a 2-man crew within 2 weeks. Cost: 3-4 occurrence. No schedule impact | 50 | 0 |  |  |  | 1 | 1 | 1 | L1
Stat2-14 | 1810 | Station 2. Modular coil damage requiring coil re-fabrication. | Extreme care will be taken when transporting and handling coils. Develop and follow appropriate procedures. Job 1810 | After Station 2 | Viola | Future Risk | N/A | N/A | N/A | High impact-low probability event that has been excluded as a bounding assumption. | [5 empty] | 1 | 1 | 1 | N/A1
Stat2-15 | 1810 7503 | Issues reported by W-7X: Loss of bolt tension with time. | Verify/monitor elongation w/ ultrasonic tester. May decide to instrument a limited number of bolts. Hot cracking of welds should not be an issue for NCSX. On W7-X, they cryocool their welds which promotes hot cracking. |  | Viola |  | VU | Negligible | Low | Assumes 2/hrs per flange x ~36 | 30 | 0 |  |  |  | 1 | 1 | 1 | VU1
TECHNCIAL RISKS - Station 3 Assembly
Stat3-1 | 1810 | Station 3: vertical weld distortion excessive. Have to take apart, modify design or procedure, re-weld. | Perform vertical welding R&D and careful monitoring during welding. Develop suitable weld procedures and train welders to minimize likelihood of unacceptable distortion. Refine welding capabilites on Station 2. Job 1810 | After first A-A weld | Viola | Future Risk | L | Significant | Moderate | 5 techs x 1 month | 70 | 1 |  |  |  | 1 | 3 | 3 | L3
Stat3-2 | 1810 | Station 3. Problems installing coils over vacuum vessel. Trajectory following scheme does not work like the concrete block. Have to re-invent. | R&D has been performed. Check in advance with trial dry fit. 1810 | After first MC-to-VV assembly | Viola | Future Risk | VU | Marginal | Low | 5 techs x .5 month | 35 | 0.5 |  |  |  | 1 | 2 | 2 | VU2
Stat3-3 | 1810 | Station 3. VV surface component (coolant tube, flux loop, or TC) damaged during FPA requiring significant rework. (Note: There is only 0.2" of clearance currently projected.) | Equipment will be handled during FPA using carefully constructed procedures to minimize likelihood. Include provisions to guard against coil damage in FPA procedures. Job 1810 | After Station 3 | Viola | Future Risk | VU | Marginal | Low | Nominally repaired with a 2-man crew within 2 weeks | 20 | 0.5 | Updated. |  |  | 1 | 2 | 2 | VU2
Stat3-4 | 1810 | Station 3. Interferences discovered during assembly; components don’t go together as planned. Assemblies have to be taken apart, components moved or re-worked, re-assembled. | CAD modeling with as-built dimensions to find interferences off critical path. Do simulations carefully Job 1901 & 8203 | After first MCHP assembled over VV | Cole | Future Risk | U | Marginal | Low | 0.5 months on C.P. | 0 | 0.5 |  |  |  | 1 | 2 | 2 | U2
Stat3-5 | 1810 | Station 3. Sag distortion while MCHP are vertical in station 3 | Our models have predicted acceptable amounts. Careful modeling contineus. Job 1810 | After first MC-to-VV assembly | Viola | Future Risk | U | Significant | Moderate | Fabricate and install bracing. Nominally a 2.5-man crew in 2 weeks. Up to 4 week impact on FPA and critical path. | 25 | 1 |  |  |  | 1 | 3 | 3 | U3
Stat3-6 | 1810 | Station 3. Assembly tooling allows too much deflection and has to be redesigned. | Exercise tooling off the critical path. Compensated by design, metrology, exercise tooling & follow demonstrated procedures Assy stesp allow for this. Demonstrated in Station 2 Job 1810 | By start of Station 3 | Viola | Future Risk | VU | Significant | Low | Rough assessment of cost and schedule impact of reinforcing or redesigning tooling. | 50 | 1 |  |  |  | 1 | 3 | 3 | VU3
TECHNICAL RISKS - Station 5 Assembly
Stat5-1 | 1815 | Station 5: Trim coils not available when needed in field period assembly sequence. Have to implement workaround. | Expedite design and procurement. Jobs 1354 | When 10% of coils are wound. | Kalish | Presently 200+ days of float in the schedule. Design of coils simplified to two coil types minimizing risk of late delivery | U | Marginal | Low | 2 weeks on CP | 0 | 0.5 |  |  |  | 1 | 2 | 2 | U2
Stat5-2 | 1815 | Station 5. TF Coils cannot be aligned | Reexamine alignment criteria and potential impact. Job 1810 | By start of Station 5 | Viola | Future Risk | U | Significant | Moderate | Up to 4 week impact on FPA and critical path. | 0 | 1 |  |  |  | 1 | 3 | 3 | U3
Stat5-3 | 1815 | Station 5. TF coils become warped and have to be racked to restore proper geometry. | Measure a sampling of coils to assess need for racking. Add hard points on the coils- Jim C. WBS 13 | After measuring 2 coils. | Kalish | Future Risk | U | Marginal | Low | 2 weeks on CP & some retrofit of clamsp. Have to do some re-design of clamps. Maybe 4 wweks of Fred & designer + hardware | 60 | 0.5 |  |  |  | 1 | 2 | 2 | U2
Stat5-5 | 1815 | Station 5. Problems installing ports due to interferences. Have to move components or modify ports. | CAD modeling with as-built dimensions to find interferences off critical path. Job 1901 | By start of Station 5 | Cole | Future Risk | L | Marginal | Moderate | Cost, not schedule 4 techs. X 2 weeks x 10 occurrences | 250 | 0 |  |  |  | 2 | 1 | 2 | L2
Stat5-6 | 1815 | Station 5. Interferences discovered during assembly; components don’t go together as planned. Assemblies have to be taken apart, components moved or re-worked, re-assembled. | Design integration during Title I & II design of components. Job 8203 | Coil Services PDRs | Brown | Future Risk | VU | Negligible | Low | Trim coil - port interferencese are biggest concer. Leads are a concern too?? 4 techs. X 2 weeks X 1 occurrence | 30 | 0 |  |  |  | 1 | 1 | 1 | VU1
Stat5-7 | 1815 | Station 5: Multiple vacuum leaks during initial pumpdown | Welds will be leak checked during FPA when leaks can be addressed without significantly impacting the critical path. Job 1810 | After leak check of first FP. | Viola | Future Risk | L | Negligible | Low | Impact of having only a few leaks is covered in estimate uncertainty with present mitigation plan | 25 | 0 |  |  |  | 1 | 1 | 1 | L1
Stat5-8 | 1815 7503 | Station 5. Rework/replacement of high permeability components | Expedite design & procurement of at-risk parts. Dudek | Coil structures FDR | Dahlgren | Assessing impact of annealing and machining on permeability | U | Marginal | Low | Initial impact assessment based on VVSA experience | 200 | 0 |  |  |  | 2 | 1 | 2 | U2
Stat5-9 | 1815 | Station 5. Field period damaged during loading, transport, or unloading from TFTR TC to NCSX TC | Extreme care will be taken when transporting a field period. Additional reviews including external reviewers will be performed. Develop appropriate procedures for transporting field periods. Arrange for a peer review of the procedures prior to transport. Will replace rollup door in CS test cell. Job 1815 | After first FP. | Viola | Future Risk | N/A | N/A | N/A | High impact-low probability event that has been excluded as a bounding assumption. | [5 empty] | 1 | 1 | 1 | N/A1
TECHNICAL RISKS - Station 6 Assembly
Stat6-2 | 7503 | Station 6. Original base structure vendor(s) unable to deliver on schedule; not available when needed in machine assembly sequence. Have to implement workaround. | Alternate vendors exist & sufficient float exists to engage an alternate vendor. We procure components and assemble on site. Job 1702 | Coil structures FDR | Dahlgren | Still in design phase - future risk | VU | Negligible | Low | Base supports must be in place prior to the 3-periord machine assembly | 50 | 0 |  |  |  | 1 | 1 | 1 | VU1
Stat6-3 | 7503 | Station 6. PF 5L & 6L not available when needed in machine assembly sequence. Have to implement workaround. | Expedite design and procurement. Could put FP#1 inplace if we had to. Could absorb 4 months delay Jobs 1302/1352 | When 1st coil is wound. | Chrzanowski | Future Risk | NC | Negligible | Low | Would impact CP. PF coils have ample float | 0 | 0.25 |  |  |  | 1 | 1 | 1 | NC1
Stat6-4 | 7503 | Station 6. PF coils out of round or not flat. Supports have to be modified. | Include adjustment provisions in coil structure designs. This is being done Job 1501 | Coil structures FDR | Dahlgren | Future Risk | NC | Negligible | Low | Addressed in base estimate | 0 | 0.25 |  |  |  | 1 | 1 | 1 | NC1
Stat6-5 | 7503 | Station 6. PF 4L, 4U, 5U, 6U not available when needed in machine assembly sequence. Have to implement workaround. | Expedite design and procurement. Jobs 1302/1352 | When 1st PF is wound. | Chrzanowski | Future Risk | NC | Negligible | Low | Would impact CP day for day, but PF coils have ample float | 0 | 0.25 |  |  |  | 1 | 1 | 1 | NC1
Stat6-6 | 7503 | Station 6: Trim coils not available when needed in machine assembly sequence. Have to implement workaround. | Expedite design and procurement. Jobs 1354 | When 10% of coils are wound. | Kalish | Presently 200+ days of float in the schedule. Design of coils simplified to two coil types minimizing risk of late delivery | NC | Negligible | Low | Would impact CP day for day, but risk mitigted by design and float. | 0 | 0.25 |  |  |  | 1 | 1 | 1 | NC1
Stat6-7 | 7503 | Station 6: Leads not available when needed in machine assembly sequence. Have to implement workaround. | Expedite design and procurement. Jobs 1601 | Electrical leads FDR | Goranson | Future Risk | NC | Negligible | Low | Would impact CP day for day, but risk mitigted by design and float. | 0 | 0.25 |  |  |  | 1 | 1 | 1 | NC1
Stat6-8 | 7503 | Station 6. High temperature Rogowski Loop damaged during installation resulting in loss of toroidal current measurement capability | Triple redundancy - 3 installed but only 1 required. Job 3101 | Rogowski loop FDR | Stratton | Starting installation in Feb 2008 | VU | Negligible | Low |  | 0 | 0 |  |  |  | 1 | 1 | 1 | VU1
Stat6-9 | 7503 | Station 6. Interferences discovered during assembly; components don’t go together as planned. Assemblies have to be taken apart, components moved or re-worked, re-assembled. | CAD modeling with as-built dimensions to find interferences off critical path. A Pro E model/sterolithography of the three period assemblies and mechanisum for positioning the FPA will be fabricated to evaluate the assembly of the coils. Job 1901 / 8203 | By start of Station 6 | Cole | Future Risk | L | Significant | Moderate | 1 month on C.P. 4 techs x 1 mont | 50 | 1 |  |  |  | 1 | 3 | 3 | L3
Stat6-10 | 7503 | Station 6. Problems making up vacuum vessel field joint. Have to re-machine spool piece. | Careful metrology in FPA, back office analysis and CAD modeling. Job 8202 (Eng. Mgr.) | After first VV joint successfully made up. | Perry | Future Risk | U | Critical | Moderate | 3 joints @ 1 month C.P. each | 0 | 3 |  |  |  | 1 | 4 | 4 | U4
Stat6-11 | 7503 | Station 6. Retainer and pucks do not stay on flange during assembly and moving of half field periods. Potential safety risk if individuals are under the machine. | Pucks will be held in place by Nomex felt and is being demonstrated to show feasiblity. Stud assembly sequence will be developed in model studies Job 1901 | By start of Station 6 | Cole | Future Risk | U | Significant | Moderate |  | 30 | 1 |  |  |  | 1 | 3 | 3 | U3
Stat6-12 | 7503 | Station 6. Problems making up C-C joint. Interferences, bolt access problems. | A Pro E model/sterolithography of the three period assemblies and mechanisum for positioning the FPA will be fabricated to evaluate the assembly of the coils. Also CAD modeling Job 1901 / 8203 | By start of Station 6 | Cole | Future Risk | U | Negligible | Low | Risk is mitigated in the estimate | 0 | 0.25 |  |  |  | 1 | 1 | 1 | U1
Stat6-13 | 7503 | Station 6. Pourable insulation installation problemss; can’t get what we need, don’t know if it fills all the voids, leaks out all over the place; have to invent methods to ensure complete fill and seal. | Perform R&D. Design special tooling for installation and verification. Job 7503 & 1901 | At least 1 year before start of Station 6 | Cole | Future Risk | U | Negligible | Low | Risk is mitigated in the estimate | 0 | 0.25 |  |  |  | 1 | 1 | 1 | U1
Stat6-14 | 7503 | Station 6. Modular coils are shorted across toroidal break between field periods causing problematic field errors | Ensure that required electrical breaks are not compromised. Check carefully during assembly. Job 1810, 1815, 7503 |  | Viola (FPA) Perry (MA) | Future risk - N/A | NC | Negligible | Low |  | 25 | 0.25 |  |  |  | 1 | 1 | 1 | NC1
Stat6-15 | 7503 | Station 6. Assembly sled for final assembly is not adequately stiff or does not provide repeatable motion | Functionality of sled will be determined with first FP. Ample time to make design modifications between arrival of the first and third FPs. Job 7503 | By start of Station 6 | Perry | Future risk - N/A | U | Negligible | Low | Nominal cost impact is 1 man-month of engineering design and up to half the fabrication cost of the sled | 75 | 0 |  |  |  | 1 | 1 | 1 | U1
Stat6-16 | 7503 | Station 6. Vacuum leaks occur. Takes time to locate and repair. | Leak check each field period independently in FPA. Job 1815 | After final VV weld | Perry | Future Risk | U | Negligible | Low | Risk is mitigated in the estimate | 0 | 0.25 |  |  |  | 1 | 1 | 1 | U1
Stat6-17 | 7503 | Welding of the Vacuum Vessel pieces to the spool pieces may require the addition of thin Inconel plates to bridge gaps caused by radial and/or angular out-of-tolerance consditions of either the VV or spool pieces. | Add Inconel plates to extend the vessel flange if radial out- of-tolerance and add flange plates ti soiil pieces and tehn bridge to vessel flange extension if angular out-of-tolerance. |  | Perry | Future Risk | VU | Critical | Moderate |  | 50 | 4 |  |  |  | 1 | 4 | 4 | VU4
Stat6-18 | 7503 | Friction shims in sizes needed for C-C joint not avaialble when needed. | Qualify sources for alumina shims; investigate use of G10 shims in some locations. Make measurements after Station 3 to determine needed thicknesses. | After Station 3 | Dudek | Future Risk | VU | Significant | Low | 6 weeks on CP | 0 | 1.5 |  |  |  | 1 | 3 | 3 | VU3
TECHNICAL RISKS - Startup
S/U-1 | 8501 | Unanticipated problems with cryostat penetrations (icing, excessive condensation). May require warming up the stellarator core to effect repair with consequent impacts to critical path activities. | Careful cryostat design, including consultation with experts and R&D. Job 1701 | Cryostat FDR | Raftopoulos | Future Risk | U | Significant | Moderate | Nominally repaired with a 4-man crew in 1 week with 3 weeks for warmup/cooldown (if required) | 30 | 1 |  |  |  | 1 | 3 | 3 | U3
S/U-2 | 8501 | Coil cooling system fails to cool coil structure down to cryogenic temperature | Robust design with excess capacity. Job 6201 | Cryostat PDR | Raftopoulos |  | U | Significant | Moderate |  | 0 | 1 |  |  |  | 1 | 3 | 3 | U3
S/U-3 | 8501 | Insulation on modular coil fails during initial cooldown and testing requiring in situ repair. | C1 tested at full current at cryogenic temperature. All modular coils will be tested at RT at elevated (50% higher) voltage for faults to ground. Job 1421 In addition, routine field tests will be performed on each assembly station to ensure that the electrical integrity is OK. Job 1810 | After Station 3 | Chrzanowski (MC) Viola (FPA) M. Viola & E. Perry - implement mitigation plan during field period and final assembly. | Future Risk | VU | Significant | Low | Insulation fault in lead area is considered the most likely failure scenario. Repair in situ is assumed recovery scenario taking 2-3 months. 1 month to warmup and cooldown the stellarator core. 3 techs/1 engr for duration of active repair )1-2 months). | 150 | 2 |  |  |  | 2 | 3 | 3 | VU3
S/U-4 | 8501 | Insulation on modular coil fails during initial cooldown and testing requiring stellarator core disassembly | C1 tested at full current at cryogenic temperature. All modular coils will be tested at RT at elevated (50% higher) voltage for faults to ground. Job 1421 In addition, routine field tests will be performed on each assembly station to ensure that the electrical integrity is OK. Job 1810 | After Station 3 | Chrzanowski (MC) Viola (FPA) M. Viola & E. Perry - implement mitigation plan during field period and final assembly. | 16 of 18 coils successfully wound. Remaining 2 coils in winding process. | N/A | N/A | N/A | High impact-low probability event that has been excluded as a bounding assumption. | [5 empty] | 1 | 1 | 1 | N/A1
S/U-5 | 7503 1352 1361 8501 | Insulation on TF/PF coil fails during initial cooldown and testing requiring in situ repair | 1st of each kind will be tested at cryogenic temperature at elevated (50% higher than routine field tests) voltage for faults to ground. All coils will be tested at RT at elevated (50% higher than routine field tests) voltage for faults to ground . Job 1361 Job 1352 | After 1st PF Coil | Kalish (TF) Chrzanowski (PF) | Mitgation plan being implemented during TF fab. There was an issue with TF Coil #3, but this has now been resolved. 6 TF coils shipped and/or received. 9TF Coils Received at PPPL and Tested | VU | Significant | Low | Insulation fault in lead area is considered the most likely failure scenario. Repair in situ is assumed recovery scenario taking 2-3 months. 1 month to warmup and cooldown the stellarator core. 3 techs/1 engr for duration of active repair )1-2 months). | 150 | 2 |  |  |  | 2 | 3 | 3 | VU3
S/U-6 | 7503 1352 1361 8501 | Insulation on TF/PF coil fails during initial cooldown and testing requiring dismantling stellarator core | 1st of each kind will be tested at cryogenic temperature at elevated (50% higher than routine field tests) voltage for faults to ground. All coils will be tested at RT at elevated (50% higher than routine field tests) voltage for faults to ground . Job 1361 Job 1352 | After 1st PF Coil | Kalish (TF) Chrzanowski (PF) | Mitgation plan being implemented during TF fab. There was an issue with TF Coil #3, but this has now been resolved. 6 TF coils shipped and/or received. 9TF Coils Received at PPPL and Tested | NC | Negligible | Low | High impact-low probability event. Exclude as a bounding assumption. | [5 empty] | 1 | 1 | 1 | NC1
S/U-7 | 8501 | Coils are hooked up with incorrect polarity | Ensure that coils are connected with correct polarity during final assembly by specifying testing in the assembly procedure. Job 7503 Test during ISTP and fix if necessary. Job 8501 |  | Perry | Future Risk | NC | Negligible | Low | Covered in estimate uncertainty with present mitigation plan | 0 | 0.25 |  |  |  | 1 | 1 | 1 | NC1
S/U-8 | 8501 | Ground faults delay coil testing. | Machine Techs will be trained to search out / identify and correct ground faults. Implement ground fault detection system before other systems are installed in test cell. WBS 4401 | Start of installation | Ramakrishnan | Allowances made in current S/U plans | VL | Negligible | Low | Experience on NSTX S/U | 10 | 0.25 |  |  |  | 1 | 1 | 1 | VL1
S/U-9 | 8501 | Loop faults delay coil testing. | Machine Techs will be trained to search out / identify and correct ground faults. Implement ground fault detection system before other systems are installed in test cell. WBS 4401 | Start of installation | Ramakrishnan | Allowances made in current S/U plans | L | Negligible | Low | Experience on NSTX S/U | 10 | 0.25 |  |  |  | 1 | 1 | 1 | L1
S/U-10 | 8501 | Control System problems delay testing | During the development of the ISTP specific ( first plasma ) waveforms will be tested to ensure that they will work. WBS 5 | Start of installation | Sichta | Allowances made in current S/U plans | L | Negligible | Low | Experience on NSTX S/U | 10 | 0.25 |  |  |  | 1 | 1 | 1 | L1
S/U-11 | 8501 | Loss of a key component or system delays testing - e.g., pump failure | Comprehensive PTP's will be conducted prior to implementing the ISTP. WBS 1-6 | Start of installation | Gentile | Allowances made in current S/U plans - replace pumps => suspend S/U unitl replaced/repaired. | U | Marginal | Low | Experience on NSTX S/U | 50 | 0.5 |  |  |  | 1 | 2 | 2 | U2
S/U-12 | 8501 | Islands detected in e-beam mapping require troubleshooting and repair; delay CD-4. | Control sources of field error and maintain inventory. WBS 8204 | Completion of e-beam mapping | Brooks | Allowances made in current S/U plans - if islands deemed to be unacceptable, would have to adjust coils. | N/A | N/A | N/A | High impact-low probability event that has been excluded as a bounding assumption. | [5 empty] | 1 | 1 | 1 | N/A1
S/U-13 | 8501 | Loss of a key component or system delays testing - e.g., turn to turn failure | Comprehensive PTP's will be conducted prior to implementing the ISTP. WBS 1-6 | Start of installation | Gentile | Allowances made in current S/U plans | N/A | N/A | N/A | High impact-low probability event that has been excluded as a bounding assumption. | [5 empty] | 1 | 1 | 1 | N/A1
S/U-14 | 3801 | E-beam mapping diagnostic is not installed and ready for use during start-up. Risk is possibly complex and challenging interface of hardware borrowed from Auburn University. | Start design of needed hardware early. Bring the work forward to mitigate the risk | Completion of installation | Stratton | Work has not yet started on job 3801. Start of work will be brought forward to January 2009. | VU | Significant | Low |  | 50 | 1 |  |  |  | 1 | 3 | 3 | VU3
TECHNICAL RISKS - Components & Systems
Sys-2 | 1352 | PF vendor produces a non-compliant coil requiring fabrication of an additional coil | Conductor for extra coil will be procured in advance and available to wind a new coil if required. Job 1352 Float in schedule appears adequate to avoid critical path impact. | Completion of Last Coil | Chrzanowski | Future Risk | VU | Negligible | Low | Increase PPPL Title III by ~1 man-month | 35 | 0 |  |  |  | 1 | 1 | 1 | VU1
Sys-3 | 1361 | TF vendor produces a non-compliant coil requiring fabrication of an additional coil | Conductor for extra coil already procured. Ample float in schedule to avoid critical path impact. No additional action required Job 1361 | Completion of Coil #18 | Kalish | Quality improving - production mode established. 9 TF Coils delivered 500 days of float from critical path | VU | Negligible | Low | Increase PPPL Title III by ~1 man-month | 35 | 0 |  |  |  | 1 | 1 | 1 | VU1
Sys-4 | 1451 | Failure of major piece of winding equipment (e.g., motor, gear box, etc.) resulting in extended downtime in a winding station | Use three remaining winding stations to continue MC fabrication while fourth station is being repaired. Job 1451 | Retired? | Chrzanowski | Future risk, has not occurred yet - N/A. Only 2 coils left. Redundant winding tooling mages this risk negligible. | U | Negligible | Low | ~$10K for equipment plus repair costs | 30 | 0 |  |  |  | 1 | 1 | 1 | U1
Sys-5 | 1451 | Damage or loss of modular coil during VPI or testing requiring the conductor to be stripped off and re-wound. | Continue to use same rigorous process used for first 14 coils during which there were no fabrication mishaps requiring re-winding a coil. Job 1451 | After last coil complete. | Chrzanowski | 16 of 18 coils successfully wound.Remaining 2 coils in winding process. | N/A | N/A | N/A | High impact-low probability event that has been excluded as a bounding assumption. | [5 empty] | 1 | 1 | 1 | N/A1
Sys-8 | 4301 | Legacy power supplies unexpectedly require modifications or additional protection as a result of failure modes analysis. | Complete failure modes analysis and/or testing. WBS 4401 | Power Systems PDR | Ramakrishnan |  | U | Negligible | Low |  | 50 | 0 |  |  |  | 1 | 1 | 1 | U1
Sys-9 | 4401 | Coil protection system costs grow when requirements fully mature. | Establish requirements Job 4401. | Power Systems PDR | Ramakrishnan |  | U | Negligible | Low |  | 35 | 0 |  |  |  | 1 | 1 | 1 | U1
Sys-10 | 1260 | NB Transition duct design is vintage and revisit could result in criteria changes, i.e. diagnostic requirements, number of ports, NB alignment, further design review, etc. | Schedule was made more aggressive with early start to assure ageement with design. |  | Goranson |  | U | Negligible | Low | Engineering hours to redo models and hold design review. | 60 | 0 |  |  |  | 1 | 1 | 1 | U1
Sys-12 | 1601-162 | Design of cables not firmly established, satisfying field error requirements could require more costly solutions and longer lead time. | Moving preliminary design into FY08 to give more lead time. |  | Goranson |  | L | Negligible | Low | Increased time for Engineering study of alternate configurations. | 60 | 0 |  |  |  | 1 | 1 | 1 | L1
Sys-13 | 1550 | Escalation of Stainless Sheet and Inconel higher than base escalation rates or due to foreign exchange rates. | None | After structure materials procured. | Dahlgren | Current estimates have "best" info on SS and Inconel prices. Will revisit in semi-annual EAC update. | VL | Marginal | Moderate | See separate sheet - assume 3% to 20% higher per year escalation rate | 495 | 0 | total cost of statinless components assuming 50% of which is material cost x 20% per year escalation rate. (see conr=tingency model tab esclation) |  |  | 2 | 1 | 2 | VL2
Sys-14 | 13XX 4, et al. | Escalation of Copper higher than base escalation rates or due to foreign exchange rates. | None | After all conductor procured. |  | Current estimates have "best" info on Cu prices. Will revisit in semi-annual EAC update. | VL | Marginal | Moderate | See separate sheet - assume 5% to 20% higher per year escalation rate | 225 | 0 | total cost of copper components assuming 50% of which is material cost x 20% per year escalation rate. (see conr=tingency model tab esclation) |  |  | 2 | 1 | 2 | VL2
Sys-16 | 1501 1353 | Coil structure designs have to be modified after FDR to accommodate chanes in interfaces with coil services or cryostat. | Expedite design of coil services and cryostat. | June, 2008 (before procurements placed) | Dahlgren | Some interfaces still not well defined - however, structure does have significant margin. | L | Negligible | Low | Cost: 20% impact on design & fab. Schedule: none | 95 | 0 |  |  |  | 1 | 1 | 1 | L1
Sys-17 | 1701 | Cryostat costs grow once design matures and requirements are better understood. | Adopt existing mature design concept if possible. (Downgrade consequences if so.) | October, 2008 (CDR) | Raftopoulos | Re-evaluating "old design" - expect decision by 4/1 | U | Marginal | Low | Cost: 50% impact on design & fab. Schedule: none | 150 | 0 |  |  |  | 2 | 1 | 2 | U2
Sys-21 | 1421 1431 | The C-C joint may need to be re-designed if it turns out that the 2T, high beta load case is not the worst-case operating condition for the friction shims. | The load cases defined in the modular coil SRD will be run to determine if the present analyses based on the 2T, high beta load case are worst case. If worst case operational conditions are found, develop mitigations and/or operational scenarios consistent with the operational limits defined by these analyses. | Sept., 2008 | Brooks/Fan | Load cases being run - expect results by mid-May | VU | Negligible | Low | Redefinition of some operating scenarios. | 50 | 0 |  |  |  | 1 | 1 | 1 | VU1
Sys-22 | 1501 1353 | Coil structure designs may have to be modified after FDR to accommodate fault modes. | Expedite failure modes analysis. | June, 2008 (before procurements placed) | Dahlgren |  | U | Negligible | Low | Cost: 20% impact on design . Schedule: none | 30 | 0 |  |  |  | 1 | 1 | 1 | U1
TECHNICAL RISKS - Research Operations (post-CD4) => NOT PART OF MIE PROJECT
Ops-1 | 8204 | The operational flexibility of the machine may be limited if it turns out that the 2T, high beta load case is not the worst-case operating condition for the friction shims. | The load cases defined in the modular coil SRD will be run to determine if the present analyses based on the 2T, high beta load case are worst case. If worst case operational conditions are found, develop mitigations and/or operational scenarios consistent with the operational limits defined by these analyses. | Sept., 2008 | Brooks/Fan | Load cases being run - expect recults by mid-May | U | Negligible | Low | Redefinition of some operating scenarios. | 50 | 0 |  |  |  | 1 | 1 | 1 | U1
Ops-2 | 7503 | Shield walls found to be inadequate. Limits operation conditions | Calculate doses, assess hazards and needed controls, peer review results. If necessary, re-grout open gaps. | 1 year before start of Station 5. | Perry | Impact of grouting gaps. | VU | Marginal | Low |  | 150 | 0 |  |  |  | 2 | 1 | 2 | VU2
Note on S3: Chris Gruber: Impacts evaluated using numbers for consequences and this column shows highest that is then used to set consequences description

## Retired Risks
[7 empty] | Likelihood: VL: P>80% L: 80%>P>40% U: 40%>P>10% VU: P<10% NC: P<1% | Consequences: Negligible: ≤$100k, ≤0.5 month Marginal: $100k-$500k, 0.5-1 month Significant: $500k-$1M, 1-3 months Critical: $1M-$5M, 3-6 months Crisis: >$5M, > 6 months
No. | Affected Jobs (absorb the impacts) | Risk Description | Mitigation Plan (& job where budgeted) | Deadline to Retire Risk or Absorb Impact | Responsibility (for reporting status monthly) | Current Status | Likelihood of Occurrence a | Consequences | Risk Class | Basis of Estimate | Cost Impact ($k) | Schedule Impact (mos)
Retired/Superceded Risks - Before February 2008
Management
19 |  | Loss or prolonged unavailability of certain key personnel from the project could substantially impact the schedule. | See mitigation plans for individuals listed below.
b | 8203 | Tom Brown (PPPL) | Bob Ellis has been budgeted along with a designer to provide support to Tom Brown in Design Integration during peak demands and pick up the slack for Brown if he became unavailable. |  | T. Brown | DELETED - SEE ITEM #8. | VL | Marginal | Low | Estimated impact is <0.5 months on the critical path. No impact on FPA cost because impacted personnel would be assigned to other activities. | 0 | 0.5
c | 8204 | Art Brooks (PPPL) | An EA/EM engineer has been budgeted to provide support to Brooks in Systems Analysis and Technical Assurance during peak demands and pick up the slack for Brooks should he became unavailable. |  | P. Heitzenroeder - assign EA/EM engineer as backup to Art Brooks. A. Brooks - provide training to TBD EA/EM engineer. | DELETED - SEE ITEM #8. | VU | Marginal | Low | Estimated impact is <0.5 months on the critical path. No impact on FPA cost because impacted personnel would be assigned to other activities. | 0 | 0.5
d | 8205 | Bob Ellis (PPPL) | An EA/EM engineer has been budgeted to provide support to Ellis in Dimensional Control Coordination during peak demands and pick up the slack for Ellis should he become unavailable. |  | P. Heitzenroeder - assign EA/EM engineer as backup to Bob Ellis. B. Ellis - provide training to TBD EA/EM engineer. | DELETED - SEE ITEM #8. | VL | Marginal | Low | Estimated impact is <0.5 months on the critical path. No impact on FPA cost because impacted personnel would be assigned to other activities. | 0 | 0.5
e | 1802 7401 | Mike Viola (PPPL) Erik Perry (PPPL) | Viola and Perry will be cross-trained such that each could do the other's job. |  | M. Viola & E. Perry | RISK RETIRED - Viola and Perry both have continuing project assignments which keep them involved at a level sufficient to maintain familiarity with each other's assembly management responsibilities in the event a handoff were needed. | VU | Marginal | Low | Estimated impact is <0.5 months on the critical path. No impact on FPA cost because impacted personnel would be assigned to other activities. | 0 | 0.5
38 | 1810 1815 7503 | 316LN Inboard Shim material is not available to meet project schedule | Alternate Material for Shim if vendor not found |  | Heitzenroeder/Dudek | RISK RETIRED - 10/30 Analysis shows that 316L will be adequate (See Engr Minutes of 10302007) | VL | Significant | High | Rough assessment of cost and schedule impact of delayed procurement. | 100 | 3
34 | 1810 1815 7503 8205 1355 | Intermittant instability has been noted in the metrology equipment and analysis software. | An 18 point study has been completed . This resulted in a number of software, hardware, and prodedural changes have been made. The level of accuracy and repeatability is now acceptable. |  |  | RISK RETIRED |  | Significant | High | Rough assessment of cost and schedule impact of slipping the FDR. | 1000 | 5
1 | 1354 7503 | Additional trim coils may be required to suppress field errors from n>1 modes | Analysis being performed to firm up requirements. Determine if additional trim coils need to be in MIE or if the configuration must accommodate a specific future set of coils. |  | M. Zarnstorff & M. Kalish | DELETED - Combined with Item #40. | U | Marginal | Low | Costs could more than double the present estimate | 400 | 0
4 | 1421 | Modular coil interface design needs to change significantly from the baseline for unforeseen technical reasons | Task forces formed to expedite resolution of feasibility issues. Development activities are underway - xxpedite completion of modular coil interface design. Complete preliminary design ASAP. |  | M. Cole | RISK RETIRED - Successful FDR realized this risk and cost & schedule impact being incoporated into updated baseline. | VU | Critical | Moderate | Design of the MC interface is on the critical path. Potential impacts include [1] additional design and development (4 engineers for 1-2 months) plus $100K M&S and [2] a change in the cost of field period and final assembly to a change in the design (+/- | 600 | 2
Retired/Superceded Risks - February 28, 2008
Stat2-1 | 1810 | Station 2. Welding the inboard shims could result in gaps opening up at the plasma-side end of the shims to an unacceptable degree. (Becasue it might introduce unacceptable cyclic loads on the weld. Gaps that open up when the outboard bolted joint assemblies are torqued also have this potential.) | Welded shim design has changed to include a tightly fitted limiter and flex shim to react shear loads; these ensure against relative motion of flanges during operation and minimize cylic loading of welds. Perform extensive welding R&D and careful monitoring during welding. Develop suitable weld procedures and train welders to minimize likelihood of unacceptable distortion. Job 1810 | After first MCHP | Viola | Risk retired by design and process changes. | L Do we agree? | Significant | Moderate | Rough assessment of cost and schedule impact of slipping the FDR. Obsolete. Cost & schedule impact on assembly work? | 600 | 3 | Likelihoods / impacts OK?
Stat2-4 | 1810 | Station 2. As a result of the development trials for weld distortion, the welding time increases significantly above present allowance | Welding time estimates consistent with time requirements for first R&D article which appeared to have very low distortion. Consider process improvements to minimize welding time w/o introducing additional distortion. Risk goes away at conclusion of ongoing weld development effort. | This risk is retired. | Viola | Risk resulted during welding trials. However, additional costs and schedule impacts have been incorporated into most recent updated ETC Retired | U | Negligible | Low | Nominal welding time may double. Estimate based on $300K/mo for FPA activities. Risk as stated is retired. | 600 | 2 | Retired?
Stat2-6 | 1810 | Station 2. Sizing shims will be challenging and will occur during tight schedule constraints. Any false starts will require immediate attention and resolution to solve problems quickly. | Continue trial assembly with hardware to explore potential problems. Adopt G10 sandwich design. Job 1810 | After first MCHP | Viola | Retired | ???? | ???? | ???? | Is this retired now? | ???? | ???? | Retired?
Stat2-8 | 1810 | Station 2. Unconstrained shim comes loose. | ???? |  | Viola | Retired by design | ???? | ???? | ???? | ???? | ???? | ???? | Likelihoods / impacts needed.
Stat2-12 | 1810 | Station 2. Interferences discovered during assembly; components don’t go together as planned. Assemblies have to be taken apart, components moved or re-worked, re-assembled. | Perform coil-to-coil fitup checks. Job 1810 | After first MCHP | Viola | Retired by having performed fitup checks of all coils and necessary re-work | NC |  |  | RETIRED.
Stat6-1 Erik | 7503 | Station 6. TC floor is not adequately rigid for present metrology plan | Copper sheet and spongy surface removed from TC floor. Fiducials will be placed. Concrete blocks will be placed to see if floor is adequately stiff. Assess adequacy of TC floor. Job 7503 | By start of Station 6 | Perry | Retired. Successfully mitigated | VU | Marginal | Low | Nominal cost impact is 2 man-months of engineering design and $50-150K for local reinforcement of building structures | 200 | 0
Retired/Superceded Risks - March 21, 2008
Sys-11 | 1601-161 | Change in scope, i.e. addition of cooling to trim coils. | Add one more designer for short term. |  | Goranson | RISK RETIRED. ADDITIONAL DESIGNER ASSIGNED. | VL | Negligible | Low | Increase proportional to increase in number of circuits. | 30 | 0 |  | 1 | 1 | 1 | VL1
Stat5-4 | 1815 | Station 5. PF & TF coil supports may have to change after FDRs to accommodate interfacing systems. | Push design integration of TF, PF, coil structures, coil services, & cryostat to resolve interfaes ASAP. Delay FDRs until integration adequately mature Job 8203 | Cryostat CDR | Brown | SUPERCEDED by Sys-11 | NC | Negligible | Low |  |  |  |  | 1 | 1 | 1 | NC1
S/U-15 | 1810 7503 | Station 2. Bolt preload could relax with time. | Will instrument some (~12?) bolts. Doing bolt tests with G10 shims. Retighten bolts/check periodically to verify that preload is okay. Job 1901 | After Station 5 | Viola | SUPERCEDED by Stat-15 | VU | Negligible | Low |  |  |  |  | 1 | 1 | 1 | VU1
Sys-1 | 1352 | No suitable PF coil vendor submits bid. PF coils need to be built in-house. | Issue sources sought advertisement. Job 1352 | After PF proposals received. | Chrzanowski | Six offerers attended pre-proposal confernce on 3/17/08 => Expect trwo or more vendors to bid. RETIRED. | VU | Marginal | Low | Cost impact estimated to be up to $300k (1/3 of fabrication costs) for potentially higher labor rates at PPPL. No impact on critical path expected. | 300 | 0 |  | 2 | 1 | 2 | VU2
Sys-6 | 1701 | Additional thermal analysis may be required to establish limits on temperature differences for cooldown. | Budget an approximate amount for thermal analysis support in WBS 82. Perform detailed evaluation of analysis needs to see if more is needed. Job 8204. | Cryostat PDR | Raftopoulos | RETIRED - included in Job 8204 estimate. | U | Negligible | Low |  |  |  |  | 1 | 1 | 1 | U1
Sys-7 | 2201 | Legacy vacuum pumps unexpectedly require modifications or additional protection as a result of failure modes analysis. | Complete failure modes analysis and/or testing. WBS 2101 | Vacuum pumping system | Blanchard | RETIRED - Backup TMPs are available. | NC | Negligible | Low |  |  |  |  | 1 | 1 | 1 | NC1
Sys-15 | 1354 | Trim coil performance requirements might have to increase to compensate for grater-than-expected assembly errors. | Design trim coil structures with adequate margin in case currents have to be increased by factor 2. | After first MCHP, implement mitigation plan if indicated by MCHP results. Job 1810 | Kalish | RETIRED - existing margin determined to be adequate. | U | Negligible | Low |  |  |  |  | 1 | 1 | 1 | U1
Sys-18 | 1701 | Cryostat sealing concept has to be revised. | Adopt less risky concept if possible. Expedite R&D | October, 2008 (CDR) | Raftopoulos | COVERED IN Sys-17 | L | Negligible | Low | Cost: 100% impact on seal design costs, 20% on fab. |  |  |  | 1 | 1 | 1 | L1
Sys-19 | 62 | Cryostat cooling performance inadequate to reach cryogenic temperatures. | Investigate cooling of structures with liquid not gas | October, 2008 (CDR) | Raftopoulos | COVERED IN S/U-2 | L | Negligible | Low | Cost: 100% impact on cryostat cooling, 20% on fab. |  |  |  | 1 | 1 | 1 | L1
Sys-20 | 15, 13, 4 | Escalation of material costs due to increased foreign exchange rates. (Model after Sys-13 & -14) |  | After structure materials and conductor procured |  | COVERED IN Sys-13 & Sys-14 | U | Negligible | Low |  |  |  |  | 1 | 1 | 1 | U1
Stat5-10 | 1815 | Shield walls found to be inadequate. Remediation impacts assembly operations | Calculate doses, assess hazards and needed controls, peer review results. | 1 year before start of Station 5. | Perry | SUPERCEDED BY OPS-2 | VU | Marginal | Low |  | 150 | 0 |  | 2 | 1 | 2 | VU2

## Ranking Lookup
Risk Ranking Lookup Table
L1 | Low
L2 | Moderate
L3 | Moderate
L4 | High
L5 | High
NC1 | Low
NC2 | Low
NC3 | Low
NC4 | Low
NC5 | Low
U1 | Low
U2 | Low
U3 | Moderate
U4 | Moderate
U5 | High
VL1 | Low
VL2 | Moderate
VL3 | High
VL4 | High
VL5 | High
VU1 | Low
VU2 | Low
VU3 | Low
VU4 | Moderate
VU5 | High