NCSX Near term task list for WBS 1 June 26, 2002

| WBS | Task | Lead | Support | Start Date | Finish Date | % complete |
| --- | --- | --- | --- | --- | --- | --- |
| 11 | Modify PFC boundary/limits to accommodate plasma, divertor, RF launchers, etc | Cole | Mioduszewski, Majeski, Nelson |  |  |  |
| 12 | Develop "B" spec (SRD) for VV | Goranson | Nelson | June 26 |  |  |
| 12 | Update draft VV specification | Goranson |  | June 26 |  |  |
| 14 | Develop "B" spec (SRD) for modular coils | Williamson | Nelson |  |  |  |
| 14 | Evaluate mod coil options for engineering parameters | Williamson |  |  |  |  |
| 14 | Analyze re-design of modular coil cooling configuration (rods and clamps) | Fan | Fogarty, Goranson | June |  |  |
| 14 | Define shell joints, bolts, shims, insulators | Dahlgren | Fan, Designer |  |  |  |
| 14 | shell geometry mods to correct thin sections | Cole | Williamson |  |  |  |
| 14 | Finalize procurement strategy for castings | Heitzenroeder | Nelson |  |  |  |
| 14 | Update draft mod coil specification | Heitzenroeder | Chrzanowski |  |  |  |
| 14 | Winding R&D | UT (Nelson) | Chrzanowski |  |  |  |
| 19 | Develop schedule for WBS 1 through FY02 | Nelson | Williamson, Cole, Goranson | May 24 | July 1 | 90% |
| 19 | Perform systematic coil tolerance study | Brooks | Nelson, Cole |  |  |  |
| 19 | Develop scope and concept for coil protection system | Nelson | TBD |  |  |  |
| 19 | Re-draft design criteria for struct, coils, etc., include existing data, identify holes in data | Zatz |  |  |  |  |
| 19 | Evaluate space requirements for soft x-ray tomography cameras | Cole | Johnson |  |  |  |
| 19 | migrate to new version of Pro-E | Cole, Brown |  |  |  |  |
| 19 | map cost, other documents to new WBS structure | Strykowsky Simmons |  |  |  |  |