NCSX Near term task list for WBS 1 September 4, 2002

| WBS | Task | Lead | Support | Start Date | Finish Date | % complete |
| --- | --- | --- | --- | --- | --- | --- |
| 11 | Modify PFC boundary/limits to accommodate plasma, divertor, RF launchers, etc | Cole | Mioduszewski, Majeski, Williamson | June 30 | Sept 15 |  |
| 12 | Develop "B" spec (SRD) for VV | Goranson | Nelson | June 26 |  |  |
| 12 | Update draft VV specification | Goranson |  | June 26 |  |  |
| 14 | Develop "B" spec (SRD) for modular coils | Williamson | Nelson | July 22 | Sep 16 | 25% |
| 14 | Evaluate mod coil options for engineering parameters | Williamson |  | June 19 | Sep 27 | LOE |
| 14 | Analyze re-design of modular coil cooling configuration (rods and clamps) | Fan | Fogarty, Goranson | June | Sept 1 |  |
| 14 | Define shell joints, bolts, shims, insulators | Dahlgren | Fan, Designer | July 1 | Aug 14 |  |
| 14 | shell geometry mods to correct thin sections | Cole | Williamson | July 8 | Sept 1 |  |
| 14 | Update draft mod coil specification | Heitzenroeder | Chrzanowski, Williamson |  |  |  |
| 14 | Prepare SOW for winding form casting R&D | Heitzenroeder | Williamson, Nelson, Chrzanowski | July 1 | Aug 14 (Draft) | 90% |
| 14 | Winding R&D (first oblong coil) | UT (Nelson) | Chrzanowski | Jan 2 | Sept 21 | 50% |
| 19 | Develop resource loaded schedule and WAFs for WBS 1 through FY03 | Nelson | Williamson, Cole, Goranson, et al | July 31 | Aug 23, 28 Oct 1 | 80% |
| 19 | Perform systematic coil tolerance study | Brooks | Nelson, Cole |  |  | 75% |
| 19 | Develop scope and concept for coil protection system | Nelson | Neumeyer | July 17 | Sept 15 | 25% |
| 19 | Re-draft design criteria for struct, coils, etc., include existing data, identify holes in data | Zatz |  |  |  |  |
| 19 | Evaluate space requirements for soft x-ray tomography cameras | Cole | Johnson |  | On hold |  |
| 19 | map cost, other documents to new WBS structure | Strykowsky Simmons |  |  |  |  |
| 19 | Comment on GRD and update “spec tree” | Nelson | All | Aug 13 | Sep 6 |  |