## Sheet1
Task Description | Start | End | Duration | M&S | M&S
| Date | Date | days | w/o G&A | w/G&A
Keystone R&D Activities
Fabricate Keystone winding form | 2003-06-02 | 2003-06-11 | 8
Wind 0.5 x 0.625 conductor both directions on Keystone winding form | 2003-06-12 | 2003-06-20 | 6
Develop conductor bender | 2003-06-23 | 2003-06-27 | 5
Test conductor bender | 2003-06-30 | 2003-07-03 | 4
Design twisted racetrack casting | 2003-06-02 | 2003-06-13 | 10
Procure casting | 2003-06-16 | 2003-08-04 | 35 | 8000 | 9680
Wind and VPI twisted racetrack | 2003-08-05 | 2003-08-15 | 10
Section and evaluate coil turns | 2003-08-18 | 2003-08-22 | 5
CTD Epoxy Samples
Complete Bundle assy. and VPI | 2003-06-02 | 2003-06-27 | 20
Prepare additional samples as req'd | 2003-07-14 | 2003-08-01 | 15
Racetrack Coil
Final Design Review | 2003-06-11 | 2003-06-11 | 1
Fabricate chill plates and clamps | 2003-06-02 | 2003-06-20 | 15
Wind coil | 2003-06-16 | 2003-06-27 | 10
Bag Mold and VPI Test Coil | 2003-06-30 | 2003-07-11 | 10
Setup test | 2003-07-14 | 2003-07-18 | 5
Perform Tests | 2003-07-21 | 2003-07-25 | 5
Place contract for Tee return molds | 2003-06-23 | 2003-08-15 | 40 | 12000 | 14520
Machine tee return molds | 2003-08-18 | 2003-09-05 | 15
Autoclave | 2003-06-09 | 2003-09-30