## Sheet1
|  | March |  |  | April |  |  | May | June | July | August | September
Straight Tee Section
VPI | H = | I = | L =
Twisted Tee
Machine casting | M = 80 hrs
Insulate/Assemble/VPI turns |  |  |  | H = | I =
Keystone Activities
Setup & Winding | J = 120 hr | K = 120 hr | L = 120 hrs | H = 80 hrs | I = 80 hrs
Demo Coil
Setup | H = | I = |  | H = | I = |  | H = | I =
Wind coil | H = | I = |  | H = | I = |  | H = | I =
Mold and VPI | H = | I = |  | H = | I = |  | H = | I =
Test
Crossover Joint Development
Fabricate samples
Test samples
Tooling Design
Autoclave
Turning Fixture
Winding Clamps
VPI System Details
Facility Layout
| ID | KEY | Name | Rate | Total Hrs | Total $
| A | EAEM | Chrzanowski
| B | EAEM | Raftopoulos
| C | EMEM | Parsells
| D | EMSM | Meighan
| E | EADM | Jones
| F | EADM | Morris
| G | EADM | Paul
| H | EMTB | Kearns
| I | EMTB | Hause
| J | EMTB | Anderson
| K | EMTB | Gifford
| L | EMTB | Benchoft
| M | EMSM | Machinist
| N | EMTB | Welder
| O | EMTB | Technician

## Sheet2
Name |  | June | July | August | September | Total | Rate | ToTals
1405/06/07 | [5 empty] | Hours | per hour
Chrzanowski | EAEM | 80 | 100 | 100 | 80 | 360 | 155 | 55800
Raftopoulos | EAEM | 80 | 80 | 80 | 80 | 320 | 155 | 49600
Parsells | EMEM | 0 | 0 | 0 | 0 | 0 | 155 | 0
Meighan | EMSM | 120 | 40 | 40 | 40 | 240 | 101.5 | 24360
Jones | EADM | 0 | 0 | 0 | 0 | 0 | 101.38 | 0
Morris | EADM | 160 | 80 | 0 | 0 | 240 | 101.38 | 24331.2
Paul | EADM | 24 | 0 | 0 | 0 | 24 | 101.38 | 2433.12
Kearns | EMTB | 160 | 160 | 160 | 160 | 640 | 74 | 47360
Hause | EMTB | 160 | 160 | 160 | 160 | 640 | 74 | 47360
Anderson | EMTB | 160 | 0 | 0 | 0 | 160 | 74 | 11840
Gifford | EMTB | 160 | 160 | 160 | 160 | 640 | 74 | 47360
Benchoft | EMTB | 160 | 0 | 0 | 0 | 160 | 74 | 11840
Desandro | EMTB | 160 | 160 | 160 | 160 | 640 | 74 | 47360
Machinist | EMSM | 120 | 120 | 120 | 160 | 520 | 101.5 | 52780
Welder | EMTB | 0 | 0 | 0 | 0 | 0 | 74 | 0
Technician | EMTB | 80 | 80 | 0 | 0 | 160 | 74 | 11840
[7 empty] | Labor | 434264.32
[6 empty] | w/20% G&A | M&S | 18150
452414.32
Name |  | June | July | August | September | Total | Rate | ToTals
1801 | [5 empty] | Hours | per hour
Chrzanowski | EAEM |  | 20 |  | 20 | 40 | 155 | 6200
Raftopoulos | EAEM | 80 | 80 | 80 | 80 | 320 | 155 | 49600
Morris | EADM |  | 80 | 160 | 120 | 360 | 101.38 | 36496.8
[7 empty] | Labor | 92296.8