20 December 2004

To: Distribution

From: Wayne Reiersen

Subject: Minutes of 20 December Critical Activities Meeting

The weekly Critical Activities Meeting was held on 20 December at 10am.  Attendees included Tom Brown, Brad Nelson, Jim Chrzanowski, Phil Heitzenroeder, Mike Kalish, Bob Simmons, and Wayne Reiersen.  The purpose of this weekly meeting is to review those ongoing activities that are on or near the critical path, identify and expeditiously resolve any issues, and to review what needs to be done in the coming week.  Critical activities are listed and discussed below.  The meeting time is limited to one hour so some follow-up reported herein was done after the fact.

- Twisted Racetrack Coil Design (part of Job 1403) and Fabrication (part of Job 1410).  Good progress continues to be reported on the TRC.  Application of cladding on one side is ¾ done.

  - WP distortion and shim requirements. Nelson has the lead in determining the winding pack distortion and the required shimming.  Nelson has constructed Pro/E models from the measurements but needs the ball measurements in order to reference the reconstructed winding to the reference winding.  Nelson to get ball measurements from Raftopoulos and establish shim requirements.  It is imperative that the distortion be quantified ASAP so the optimum shimming can be done as part of the winding process which will start as soon as the cladding is complete.  Nelson is planning to address this subject at the WBS 1 telecon on Wednesday 22 December.

  - Shim design.  Chrzanowski proposed using hard shims between one or two layers instead of distributing soft fiberglass cloth between every layer.  The motivation for using the hard shims is two-fold: to improve dimensional control and facilitate fabrication.  There was considerable discussion of this option.  It was agreed that this option should be pursued.  Nelson will coordinate thermal and structural analysis of the hard shim option and provide guidance re how many shim layers will be required.  Assuming there are no showstoppers, we would need to have the shims fabricated.  Chrzanowski will provide Dudek with a table of standard shim sizes and thicknesses that we be used for fabricating these parts.

  - Fabrication of piece parts.  Following the 13 December meeting, Dudek reported that it was critical that fabrication of the chill plates and fringe commence immediately if they are to be available on time.  Fabrication drawings of these parts were sent by ORNL on 17 December.  No additional action required.

  - Cost and schedule control.  Fabrication of the TRC is schedule critical.  The application of the cladding and winding will be done on an extended working schedule.  The technicians working on the straight tee have stopped to help prep the cladding so the pieces are ready when Anderson and Terlitz need them.  Because of the schedule critical nature of this job and the uncertainty in how long each step will take, Chrzanowski agreed to develop a more detailed schedule that he will use to report progress and forecast when the TRC will be finished.  Because we plan to use OT to get this job done within the time allowed, Chrzanowski will provide Strykowsky with updated cost and schedule information consistent with this revised plan.  This information should explicitly identify any outside procurements that need to be placed, e.g. the cladding and chill plates for the production coils.

Application of the cladding and chill plates/cooling tubes are the things that most worry the technicians responsible for manufacturing the modular coils.  Cognizant design and manufacturing personnel really need to stay on top of the problems they encounter as they do these operations and strive to make refinements where dictated by the problems they encounter.  Chrzanowski is encouraged to pursue refinements in the winding station design and tools that might speed up the winding time and provide improved ergonomics for the technicians.  Annealing the copper cladding has proven to be a big win.  Chrzanowski is also looking into getting an accelerator to speed the curing of the adhesive used to hold the cladding to the winding form.  ORNL is looking into whether parts standardization (a dozen rather than hundreds of different parts) could be achieved for the cladding and chill plates.

Brooks has investigated and alternate cooling concept that avoids the need for cladding and chill plates.  Specifically, he has investigated an option that uses copper inserts that would be placed in a manner similar to hard shims.  These would be flat pieces of copper perhaps 1 1/2” wide and the depth of the winding pack.  The cooling tube would run straight across the top of the clamp (where it is now) without any serpentines.  The copper tabs could be connected to the cooling tube via a copper strip that is attached with pop rivets.  Brooks has documented the performance of this alternate concept and it appears to work satisfactorily.  The main concern is the potential risk introduced by placing the copper inserts within the ground wrap (although the copper inserts are wrapped in Kapton to provide adequate voltage standoff capability.)  There is no plan to implement this alternate design unless we run into substantial problems with the reference design in the fabrication of the TRC.

There was confusion at this week’s status meeting about whether the drawings for the production clamps (not the winding clamps) had the right dimension for the vertical legs.  Chrzanowski to fit the production clamps and determine if they are the correct length.

- TF Design and Procurement.  Continuing down the path of procuring the TF coils from an outside vendor places a burden on us to assure that the TF coils are built to exacting quality standards while staying within our budget and meeting our schedule objectives.  Kalish to update design data on Manufacturing Web (see Tyrrell) to reflect current design and notify potential suppliers (foreign and domestic) of the update.

Kalish is planning on conducting an information meeting for potential suppliers for Conventional Coils (WBS 13).  Current plans are to conduct the information meeting following the PDR.  Kalish to finalize arrangements for information meeting.

Kalish is planning to test a straight beam using conductor that is representative of the conductor used in the conventional coils.  He would subject the conductor to repeated thermal stresses and perform mechanical and electrical tests to verify that the insulation performance does not degrade under repeated thermal cycling.  Plans are to fabricate and test the specimen right after straight tee specimen is fabricated to test modular coil VPI process.  The straight beam would be fabricated in January.  The results will be needed for the FDR.  Kalish could use some support coordinating the fabrication and testing of the straight beam.  This topic will be addressed at the TF meeting scheduled for 22 December at 9am.

The change in the insulation design has pushed back the PDR date.  Steps leading to the PDR as follows:

07 Jan		Analysis of the TF design updated

TF SRD signed (Reiersen)

Scope sheets in place for all interfaces

12 Jan		Models and drawings updated

Design basis analyses posted as draft Analysis Reports

Cost basis documentation updated

Cost and schedule baselines updated to reflect procurement plan

Review panel selected, charge issued, agenda set

19 Jan		TF models and drawings reviewed/promoted to PD Release Level

Design Description for Conventional Coils and Structures updated

Design review package posted for reviewers

21 Jan		Dry runs of PDR presentations

26 Jan		TF PDR

Kalish to coordinate PDR preparations meeting the above schedule.  It is imperative that the preliminary design for the TF coils be completed and successfully reviewed in January.

- VV Field Weld Joint R&D (Job 1206).  Additional samples have been welded.  Dudek reported last week that [1] there is little hope of avoiding a crack when welding from only one side and [2] it was difficult with the current weld prep to get the tungsten to the root of the weld.

Nelson suggested that a one-sided V-groove would provide better access than a one-sided J-groove and avoid the fit-up problems introduced by a 2-sided weld prep.  He also thought that a deeper weld would decrease the load eccentricity and reduce stresses.  Nelson and Dudek to resolve final weld configuration.

Tensile samples have been prepared from the plates that were welded together.  Dudek reported (via e-mail) on an initial pull test that was very positive, showing a strength of 10x the design stress.  Nelson tempered the optimism with the observation from Freudenberg’s analysis that the tensile load is eccentric with the tensile stresses being substantially higher than the average section stresses where the weld is located.  Subsequent to the meeting, Goranson provided more detailed guidance on the mechanical loading at the weld.  Analysis indicates that a tensile load on the weld sample in the range of 1725-1860 lbs per inch of perimeter (thickness of sample) will give an equivalent stress to the results predicted by the ANSYS model. This assumes a weld depth of 0.44 inches and an offset in the pull specimen of 0.155 inches, which is pulling symetrically on the ¾” wide section.  These loads are basically due to the vacuum vessel being under vacuum.  I was unable to find any requirement for the expected number of vents and pumpdowns.  I think 500 is generous number.  This is basically once per week for 10 years.  The fatigue requirement (which does not strictly apply due to the low number of cycles) calls for a factor of 2 on stress and 20 on life.    20 on life would be only 10,000 cycles.  Kozub reported that the initial tests were suspended after almost 250,000 cycles which seems way more than needed.  Dudek to report on testing plans and progress.  We should address whether any fracture analysis and testing is needed.

The requisition of the full scale test article was cancelled because of the protracted deliberations for finalizing the weld joint configuration.  The full scale test article would be quite expensive to procure, with a contract (unloaded) price tag of $125K.  Cheaper alternatives might exist such as [1] just welding flange pieces together cut from Inconel plate or [2] replacing the rolled Inconel sheet with stainless steel.  ORNL (Nelson/Goranson) and Dudek are asked to propose lower cost alternatives.

ORNL has proposed exploring the possibility of MTM doing the field welding at PPPL and perhaps even using an automated welder that ORNL currently has to do the final assembly welds.  Viola to consider this proposal and possibly broach subject with MTM on whether they would be interested in such an arrangement.

- VV port extensions welds.  MTM reported a concern that when they weld the large, thick (1/2”) port extensions for the NB ports and the adjacent large ports (Port #4) to the thinner (3/8”) shell, the shell will locally pucker in.  In addressing this risk, MTM identified two options for producing the tooling and fixturing and asked the project to provide guidance.  (Click here for MTM’s risk mitigation synopsis.)  The first option would be to produce the tooling and fixturing to the “nominal” profile.  This option would have a higher risk that the VVSA may protrude on the inner limit of the desired tolerance band.  The second option was to produce the tooling and fixturing to the “high limit” profile, with a higher risk of protruding on the outer limit of the tolerance band.  Protruding on the outer limit may affect our ability to assemble the machine whereas protrusions on the inner limit would encroach on the plasma-wall separation and diagnostic/heating access.  The former condition would clearly be less manageable so Viola was instructed to provide guidance that the first option would be preferred.

MTM also requested a change in the weld configuration for attaching the large vertical ports, the NB ports, and the large ports adjacent to the NB ports (port 4).  (Click here for marked up drawings showing the proposed change.)  MTM would like for the port extensions to penetrate the shell rather than butt up against the shell.  ORNL explained why the weld was oriented the way it was and asked Viola to get further clarification from MTM.  Subsequent to the meeting, Viola reported the following:

- The proposed weld configuration change allows for back grinding of various amount depending on the distortion that the inside weld created.

- The machining of the port holes and then welding the ports on provides better access. Also allows for accurate inspection and better finishing of the inside welds.

- There is a plan to keep the drop outs on the smaller ports and tack them back in to maintain some rigidity while placing the majority of the weld on from the outside.

- Large ports openings will probably be done in steps – cut out a hole, tack it back in, then weld the port on, then remove the drop out and finish the hole, then reinsert the drop out with strips to make up the gap, then finish the inside edge.

- The segmentation scheme and segment weld design account for expected shrinkage to arrive at Nominal profile.  The localized distortion at the attachment points of the large ports would be an additive effect and may or may not pull the vessel profile inside the current tolerance.

- I discussed the possibility of providing language to answer their concerns but MTM would like us to revise the drawings at our convenience.

- Besides the proposed weld change there may be an error on the part callout for the NB weld port detail but Doug noted that this .pdf’d markup is not using the current version of this drawing.

Viola is planning to tell MTM that the project will provide formal guidance re the proposed weld configuration by 12 January.  ORNL to provide guidance to Viola by 05 January.

MTM felt that adopting the proposed changes in the weld configuration plus producing the tooling and fixturing to the “nominal” profile would provide the least risk, with the primary risk being that the VVSA may protrude on the inner limit of the desired tolerance band in the vicinity of the large ports (particularly the large vertical port and Port 4).  If the vessel moves towards the plasma in the vicinity of the NB ports, the NB access could be compromised so there a clear limits on how much we could relax tolerances in this area.  However, for the other large ports which are further away from the plasma (and which MTM is more concerned about), we may be able to relax the tolerances so they can be readily met with no impact on performance.  Brown and Cole are asked to review the tolerance specifications (specifically with Diagnostics) for these ports and propose a revision if appropriate.

MTM requested that all of the seal grooves be put on the port cover side.  Goranson provided a compelling argument that the seal grooves all be on the flange side (with the exception of the NB port).  This was communicated to MTM by Viola and they concurred that the current design was appropriate.

Goranson was concerned about the fit-up of the port extensions after they are cut off.  We may have failed to provide any requirements to assure that the fit-up is adequate for re-welding.  Goranson is asked to review the drawings and specifications and determine if changes are in order.

- Modular Coil Testing

  - Conductor Testing (Job 1406).  Kozub has reportedly pulled the long racetrack coil to failure – it failed at 23,000 lbs.  This information will be used to set the parameters for additional cyclic testing to be performed in January.  Chrzanowski reported that torsion tests are done, but problems were encountered with transverse compression test.  Kozub provided the results of the torsion testing on 15 December.  The results are posted on the Web and can be found by clicking here.  Chrzanowski to provide update on transverse compression tests.  The NSTX work that Kozub was planning on doing appears to be slipping.  Chrzanowski suggested to Kozub slipping the NCSX cyclic tests forward to right after the holidays.

  - Beam Testing (Job 1403).  ORNL reported on the 3-point bending tests at least week’s Wednesday telecon.  The results are being analyzed by Fan.  Torsion testing of the beam is next on the agenda.  Nelson to expedite testing at ORNL and report on how Fan’s results should be used in the analysis effort.

  - MCWF Fracture Analysis (Job 1404).  The data from the NHFML had seven orders of magnitude of scatter with some points better and some worse than our reference CF8M data.  The pedigree of the data has been sorted out.  It was determined that the samples were cut from risers and other places not representative of the high stress regions.  Additional samples will be cut from the EIO prototype coil (around port openings) and tested.  Heitzenroeder to work with Strykowsky to add this additional testing to our plans and work with EIO to get the samples for the testing.  Subsequent to the meeting, Heitzenroeder provided an update on progress in this area which can be read by clicking here.

- Modular Coil Design (Job 1403).  A recent study by Brown suggested that reaming all of the holes for assembling the modular coils into a shell may be very difficult.  It was not clear that reaming all of the holes was necessary.  It was also clear that a means of positively locking the bolts was required. Nelson reported that Williamson is adding a model of a commercially available reamer to the Pro/E model to determine which holes would be feasible to ream.

Analysis efforts in modular coils are taking more time than budgeted.  Nelson and Williamson met with Fan, Freudenberg, Brooks et al and established an analysis end game.  Plans need to be updated accordingly (Williamson)

The loop between testing and analysis needs to be closed.  We have done a lot of tests for the purpose of establishing material properties and design allowables.  However, we need to go one step further and document what values we want the analysts to use.  HM Fan has tabulated the results of tests related to material properties which tend to be multi-valued.  We need to document reference material properties and use them in the design basis calculations.  Nelson to coordinate documentation of reference material properties for stellarator core systems.

- Vacuum Vessel Final Design (Job 1203).  This is a mirror of the analysis issue in modular coils.  Analysis efforts are taking more time than budgeted.  Nelson met with Goranson, Freudenberg, Dahlgren, Brooks et al this week to establish analysis end game.  Plans should be updated accordingly (Goranson).

- PF Solenoid Make, Buy, or Scavenge.  There has been discussion lately about making the solenoid coils in-house in the first part of CY05 ore even re-using the excessed PF1A coils from NSTX.  Reiersen did a study which indicated that the PF1A might be used in place of PF1-3.  Zarnstorff to perform simulation modeling to confirm conclusions.  If we choose to go this way, Kalish will have to add a PF1A refurbishment task to his scope and Ramakrishnan will have to revise his plans accordingly.

Neilson concluded that there is insufficient management reserve available to commit to building the solenoid coils in house at this time, so that option has gone away.  We still need to decide between re-using the PF1A coils and buying new solenoid coils, but the urgency of that decision has abated.

- Test Cell Preparations and Machine Assembly (WBS 7 jobs).  In discussions regarding machine assembly, a question arose regarding when we would know what the upgraded crane capacity would be.  It is expected that the “break point” for the upgraded crane capacity will be between 40 and 45 tons, but we will likely not know for a year or so.  It would be prudent therefore to plan on 40 tons.  Cole to update our assessment of the maximum weight of a FPA to determine what margins exist.

- STEP file creation.  Brown previously reported a problem with updating STEP files, but that this problem could be overcome by using commercially available PowerGrip software.  STEP files have been successfully downloaded and read by MTM so apparently this problem has been overcome.  No additional action required.

- Upcoming Design Reviews.

  - TF PDR – 26 Jan 05.

  - MC Turning Fixture PDR – 23 Dec 04. Brown to update projection.

  - Base Support Structure and Cryostat PDR.  Gettelfinger to re-schedule for January to accommodate designer crunch in December and allow more time for design review prep.

The next meeting is scheduled for 10am next Monday, 03 January in the Engineering Conference Room.

Cc: Neilson, Strykowsky, Brown, Heitzenroeder, Chrzanowski, Nelson, Dudek, Perry, Kalish, Gettelfinger, Viola, Tyrrell, Brooks, Zarnstorff, Williams, Williamson, Cole, Goranson, Simmons