## Sheet1
Week Ending… | Sample Preparation | Fixtures Completed | Tests Performed | Properties and Criteria | Other
2004-03-19 | All single conductor samples prepared | Fixtures for compression testing and axial prepared | Flexure tests | Load-deflection curve (flexure) Flexure modulus [all of the above for RT and cryo] | The old, full-scale T-section will be shipped to ORNL for flexure testing
2004-03-26 | 1st Long Racetrack Coil (LRC1) 1st Short Racetrack Coil (SRC1) | Fixtures for cyclic testing prepared | Axial shear tests Compression tests | Axial shear modulus Load-deflection curve (compression) Compression modulus (axial) Compression modulus (transverse - based on single conductor) [All of the above for RT and cryo] | FEA models of single turn samples developed with and w/o insulation. Flexure tests modeled and compared with test results.
2004-04-02 | 2nd LRC (LRC2) 2nd SRC (SRC2) |  | Single cycle tension tests on LRC1 (RT) and SRC1 (cryo) | Cure shrinkage Load-deflection curve (tension) Tension modulus Electrical resistance [all of the above for RT and cryo] | FEA model of SRC developed.
2004-04-09 | 3rd LRC (LRC3) 3rd SRC (SRC3) |  | Fatigue tests (load condition 1) on LRC2 (RT) and SRC2 (cryo) | Cure shrinkage Load-deflection curve (tension) Tension modulus Electrical resistance (Ncycles) Fatigue behavior (load condition 1) [all of the above for RT and cryo] | Comparison between FEA model and SRC load-deflection test results compared. Final conductor due to arrive this week
2004-04-16 | Single conductor samples prepared with new conductor Straight, full-scale T-section started |  | Fatigue tests (load condition 2) on LRC3 (RT) and SRC3 (cryo) | Cure shrinkage Load-deflection curve (tension) Tension modulus Electrical resistance (Ncycles) Fatigue behavior (load condition 2) [all of the above for RT and cryo]
2004-04-23 | Straight, full-scale T-section completed | Flexure test fixture for straight full-scale winding | Flexure tests with new conductor | Load-deflection curve (flexure) Flexure modulus [all of the above for RT and cryo with new conductor] | FEA model of flexure tests with full-scale windings (Sides 1 and 2) completed.
2004-04-30 | 2x5 Article for Transverse Compression Tests | Torsion test fixture | Flexure testing of Side 1 (w/o leads) and Side 2 (with leads) | Load-deflection curves for full-scale windings (with and w/o leads) | Design criteria documented updated. Draft material test report generated.
2004-05-07 |  |  | Transverse compression tests on 2x5 array Torsion tests on single samples | Compression modulus (transverse - based on multiple conductors) Shear modulus [all of the above for RT and cryo] | CABLE CONDUCTOR MATERIAL PROPERTIES AND DESIGN CRITERIA PEER REVIEW - 03 MAY Comparison between predicted (FEA) results and measured results completed.
2004-05-14 |  |  |  |  | Final test report and updated Design Criteria Document provided.
Formulas:
Week Ending… = [Week Ending…, row above]+7