## Wind MC
| 2005-08-26 | Start Modular Coil Winding Checklist
Latest Developments [1] EIO advised NCSX that the expected shipping date is still holding at mid-September. Chrzanowski plans to use a 2-4 man crew on one shift for Station 1 activities instead of going to two shift operation. Winding operations would be done with two shifts. The expected completion date is now November 23. [2] Test plan is now as follows: Power testing of the TRC starting August 26, magnetic measurements to follow, cutting up the TRC on or about September 15, with dimensional inspections done by September 30.
Forecast | Scheduled | Timeline [1], [2] | Responsibility
PRC and TRC Testing
√ |  | CTF accommodations for RT magnetic measurements complete Accommodations include 6V PS and coil cooling. Safety issues must also be resolved (container, procedures, etc.). | Gettelfinger
√ |  | TRC thermal and structural analyses updated to predict thermocouple and strain gage responses per prescribed test plan Freudenberg is updating analysis. | Freudenberg
√ |  | Finish PRC testing PRC testing was finished July 29. The PRC was cooled to LN2 temperature, passed hi-pot when cold, and demonstrated single phase cooling. | Gettelfinger
| 2005-08-01 | Start NSTX maintenance week
√ |  | Finalize TRC Test Plan Needs to be consistent with Freudenberg analysis | Nelson
√ |  | Develop PPPL procedure for TRC testing Use TRC Test Plan as an attachment to define technical parameters for the procedure | Gettelfinger
| 2005-08-05 | End NSTX maintenance week
√ |  | Cryostat built, TRC loaded and connected, ready for testing | Gettelfinger
| 2005-08-26 | Start TRC testing | Gettelfinger
| 2005-08-29 | Start NSTX maintenance week
| 2005-09-02 | Procedure for cutting TRC apart developed; resources arranged Needs input from Brooks on where cuts should be made | Raftopoulos
| 2005-09-02 | End NSTX maintenance week
| 2005-09-06 | Resume TRC qualification testing
| 2005-09-09 | TRC qualification testing in CTF complete | Gettelfinger
| 2005-09-12 | Begin magnetic measurements and winding pack reconstruction | Nelson
| 2005-09-14 | Magnetic measurements complete | Nelson
| 2005-09-15 | Start cutting TRC apart | Dudek
| 2005-09-12 | Develop Kickless Cable Test Plan | Nelson
| 2005-09-14 | Develop procedure for kickless cable testing | Gettelfinger
| 2005-09-16 | Kickless cable and PRC installed in cryostat | Gettelfinger
| 2005-09-19 | Start kickless cable testing | Gettelfinger
| 2005-09-22 | Kickless cable testing complete | Gettelfinger
| 2005-09-22 | Dimensional inspections completed on cut sections of TRC | Raftopoulos
| 2005-09-28 | Winding pack reconstruction from magnetic measurements complete Required to confirm methodology for post-winding validation - cannot be done with coil in handling fixture | Nelson
Plans, Procedures, Specifications, and Assembly Drawings
Dimensional control plans and metrology procedures
√ |  | Metrology procedure for Stations 1 and 2 updated, sent out for review | Raftopoulos
√ |  | Complete initial lacing trials, define implementation | Stratton
√ |  | Tensioner for glass straps designed and built | Heitzenroeder
√ |  | Metrology training for technicians completed | Raftopoulos
| 2005-08-01 | Raftopoulos vacation starts
| 2005-08-05 | Raftopoulos vacation ends
√ |  | Lacing trials repeated using tensioner | Raftopoulos
| 2005-08-26 | Revised metrology procedure approved, ready for use No changes needed based on lacing trials unless the lacing option changes | Raftopoulos
| 2005-08-26 | Dimensional control plan (DCP) updated and approved Update reflects final outcome of lacing trials No changes needed based on lacing trials unless the lacing option changes DCP should be placed under revision control | Stratton
| 2005-09-06 | Pro/E surfaces required for Station 1 generated and checked | Williamson
| 2005-09-29 | Pro/E surfaces required for Stations 2 and 4 generated and checked | Williamson
| 2005-09-29 | Clamp side leg positions established for coil winding Required for coil winding | Brooks
Winding procedures
√ |  | Coil prep (Station 1) procedure updated, issued for review | Chrzanowski
√ |  | Coil winding (Station 2) procedure updated, issued for review | Chrzanowski
√ |  | Coil prep (Station 1) procedure approved | Chrzanowski
√ |  | Coil winding procedure (Station 2) approved | Chrzanowski
Lift procedures
√ |  | Lift procedures for raw casting and finished coil sent out for review | Chrzanowski
√ |  | Lift procedures for raw casting and finished coil approved | Chrzanowski
Specifications and drawings
| 2005-08-26 | Issue complete draft of MC Type-C assembly spec for review | Reiersen
√ |  | Terminal drawings released for fabrication | Williamson
| 2005-08-26 | Stud assembly drawing approved for fabrication All of the delivery dates should be updated to be consistent with the detailed schedule Williamson presented on August 19 telecon | Williamson
| 2005-08-26 | Cladding assembly drawing released for fabrication | Williamson
√ |  | Chill plate DXF files released for fabrication | Williamson
| 2005-09-02 | Terminal assembly drawings released for fabrication | Williamson
| 2005-09-02 | Chill plate assembly drawings approved for fabrication | Williamson
| 2005-09-02 | Spec approved and under revision control | Williamson
| 2005-09-09 | Winding assembly drawing (including lead block assembly) released for fabrication | Williamson
| 2005-09-16 | Production clamp drawings released for fabrication | Williamson
Parts and Materials
Cladding
| 2005-08-26 | Cladding prepped for installation | Chrzanowski
Lead blocks
√ |  | Lower lead blocks ordered | Dudek
| 2005-08-12 | Lower lead blocks received | Dudek
√ |  | Upper lead blocks ordered | Chrzanowski
| 2005-08-19 | Upper lead blocks received | Chrzanowski
Terminals
| 2005-08-19 | Terminals fabricated at PPPL | Chrzanowski
Chill plates
| 2005-07-15 | Copper for chill plates ordered | Chrzanowski
| 2005-07-29 | Copper for chill plates received | Chrzanowski
| 2005-08-05 | Chill plates fabricated at PPPL | Chrzanowski
| 2005-08-26 | Chill plates prepped for installation | Chrzanowski
Terminal assembly
| 2005-09-09 | Stereolithography (STL) parts ordered for terminal assembly | Williamson
| 2005-09-16 | STL parts received | Williamson
| 2005-09-23 | Terminal assembly parts fabricated at PPPL | Chrzanowski
Production clamps
| 2005-09-23 | RFQ issued for production clamps | Chrzanowski
| 2005-09-30 | Production clamps ordered | Chrzanowski
| 2005-09-30 | Miscellaneous clamp hardware ordered | Chrzanowski
| 2005-10-14 | Miscellaneous clamp hardware received | Chrzanowski
| 2005-11-11 | Production clamps received | Chrzanowski
Studs
√ |  | Studs received | Chrzanowski
| 2005-09-09 | Stud adapters fabricated | Chrzanowski
Co-wound loops
√ |  | Wire ordered | Stratton
| 2005-08-12 | Wire received | Stratton
√ |  | Teflon sleeving ordered | Stratton
| 1900-01-12 | Teflon sleeving received | Stratton
√ |  | Teflon sleeving qualified for operation at 80K | Stratton
| 1900-01-26 | Sleeving installed on wire. Loops ready for installation | Stratton
Monuments and gage blocks
√ |  | Monuments have been fabricated and are ready for installation. Two types have been made. One type will be installed in precision holes provided by MTM. The other type will be temporarily installed to facilitate measurements during the winding process. | Raftopoulos
| 2005-08-12 | Range of gage blocks established based on input from Brooks; gage blocks ordered from PPPL shop | Stratton
| 2005-08-26 | Gage blocks received | Stratton
MCWF
√ |  | Resolve Type-C design issues: poloidal break, attachment of lower lead block, and interruption of O-ring groove under lead block | Heitzenroeder
| 2005-09-05 | Complete part manufacture | MTM
| 2005-09-15 | Complete dimensional inspections | MTM
| 2005-09-16 | MCWF shipped | MTM
| 2005-09-20 | MCWF arrives at PPPL | MTM
All else...
| 2005-08-12 | All other supplies on hand (glass, epoxy, Kapton tape, nuts, bolts, winding clamps, adhesive, mold release, shim washers, ground wrap, etc.) Meighan to develop complete list of miscellaneous materials required | Meighan
Facility Preparations
√ |  | Stations 1 and 4 operational | Chrzanowski
√ |  | Stud welder modifications complete | Chrzanowski
| 2005-08-12 | Whisker detector installed, conductor feed modifications complete Whisker detector not mounted on frame yet | Chrzanowski
√ |  | ACC review of Stations 1, 2 and 4 | Chrzanowski
| 2005-08-12 | Implement ACC recommendations [1] Station1B - Approve operating procedure and JHA prior to operation [2] Station 1A -Lift engineer to verify 1/2 ton hoist prior to lift operation [3] Station 4 - Delineate walkway from back exit | Chrzanowski
|  | Start winding C1 Coil |  | Shifts | Shift/Day | Days
| 2005-09-21 | Start coil prep (mount coil in ring, perform receipt inspection, cleaning, cladding, studs) on Station 1 | Chrzanowski
| 2005-10-13 | Finish coil prep on Station 1 | Chrzanowski | 16 | 1 | 16
| 2005-10-31 | Coil installed in turning fixture in Station 2, preparations for coil winding complete | Chrzanowski | 12 | 1 | 12
| 2005-11-10 | Side A wound | Chrzanowski | 15 | 2 | 8
| 2005-11-11 | Coil repositioned in turning fixture | Chrzanowski | 1 | 1 | 1
| 2005-11-23 | Side B wound | Chrzanowski | 15 | 2 | 8
Watch List
|  | Magnetic measurements. Nelson has pulled a plan together to get the system for making magnetic measurements operational. ORNL will bring a turn-key system (Romer arm, Hall probe, and laptop computer) and test it on the TRC following power testing in the CTF. Gettelfinger has a suitable power supply and coil cooling available in the TFTR test cell and will address any safety issues related to people working around an energized coil. | Nelson
|  | Material properties. We have done a lot of testing on NCSX but have never established reference material properties and allowables for analysts to use which are consistent with our test results. The testing is nearing completion. Beam tests are still being done at ORNL. Fracture parameters have been determined at the NHFML. The results of all the testing need to be organized, reference material properties and allowables established, and design basis calculations updated. | Nelson
|  | Qualification of the modular coil design. The plan is to qualify the modular coil design by operating the TRC. If the TRC behaves as expected (based on modeling of the TRC), then we have increased confidence that the production coils will behave as expected. In order to qualify the design in this way, we need to model the TRC and predict its performance. We also need to instrument it so its performance can be adequately measured and have a well defined test plan. ORNL to provide [1] test plan [2] predictive modeling of TRC tests and [3] strain gage and thermocouple locations. Fiber optic strain gages will not be used. | Nelson
|  | Dimensional control. The plan for maintaining winding pack dimensions during ground wrapping, chill plate installation, and bag mold installation is still being worked. A peer review was conducted on May 13. The central remaining issue is how to maintain dimensional control after we start applying the ground wrap, chill plates, and bag mold. Bench tests are being performed to resolve remaining dimensional control issues. | Stratton
Lessons learned from TRC bag molding and VPI. We experienced two leaks when we started filling with epoxy. The first was discovered when epoxy was seen leaking from around a sprue. The second was discovered upon hearing a whistling sound. The cause was later traced to a sharp point on the epoxied felt. Upon fixing the leak, the vacuum in the coil dropped from the 16 torr value prior to the first epoxy fill down to 5 torr. It was reasoned that a tighter spec should be adopted based on the pressure rate of rise. There was also considerable discussion as to whether the epoxy fill should proceed with the autoclave under vacuum (like it was when the first leak was observed) or whether there should be positive pressure across the bag mold. With the autoclave under vacuum, the chances of an epoxy leak are greater, but the chances of drawing air into the coil are diminished.
More lessons learned from TRC bag molding and VPI. The tubing exited downward from the uppermost sprue making it difficult to ensure that the coil was filled. Design mods in the epoxy feed system are planned to correct this deficiency but the temperature at the top of the autoclave is an issue. An electrical short was discovered between the cladding and tee because of a punch through the Kapton - should be corrected.
4th quarter Joule milestone. The 4th quarter Joule milestone is completion of winding the 1st Type C coil. Given that we are not even going to receive the coil until mid-August, this will require extraordinary effort to accomplish. We will need to go to double shifts (where beneficial) with extended hours. Vacations will need to be coordinated to ensure that we have crews available to work two shifts when needed. Material, equipment, and procedures needed to fabricate the coil must be available when needed.
Notes
| [1] | Max field levels at PPPL are (a) 100 gauss for 8 hours per day (b) 1000 gauss for 1 hour per day and (c) 5000 gauss for 10 minutes per day. The energy in a fault also needs to be considered.
Formulas:
Scheduled = WORKDAY([Scheduled, row above],3,0)
Scheduled = [Scheduled, row above]

## TF Design
| 2005-08-26 | TF Design Close-out Checklist
Timeline
√ |  | TF winding tests at ORNL complete
√ |  | TF Conductor FDR FDR was conducted May 17. All chits have been closed.
√ |  | TF Conductor procurement package approved (spec, drawings, SOW) TF conductor spec and SOW are approved. TF conductor drawing is released for fabrication.
| 2005-06-03 | TF Conductor RFP released Requisition approved but not on Procurement Web site yet
| 2005-06-08 | Arrangements for TF Wedge Plate FDR complete
| 2005-06-15 | TF Wedge Plate FDR
| 2005-06-22 | TF Wedge Plate procurement package approved (spec, drawings, SOW)
| 2005-06-29 | TF Wedge Plate RFP released
| 2005-07-01 | Arrangements for Comprehensive TF FDR complete
| 2005-07-08 | Comprehensive TF FDR
| 2005-07-15 | TF Coil fabrication and assembly package approved (spec, drawings)
Deliverables
TF Wedge Plate FDR
TF Wedge Plate product specification (ready for signature)
TF Wedge Plate fabrication drawings (ready for signature)
TF Wedge Plate Statement of Work (ready for signature)
Comprehensive TF FDR
TF Coil Fabrication and Assembly specification (ready for signature)
TF Coil models and drawings (ready for signature)
Master bill of materials checked, approved, and posted
All prior chits closed (closure approved by RLM, tracking log updated)
R&D results documented in R&D report and posted
Design basis analyses documented, checked, and posted
FMECA documented, checked, and posted
Instrumentation & control design complete and documented
Piping and instrumentation diagrams (P&IDs) developed
Electrical schematics for TF circuit developed
ICDs signed and posted
SDD updated and posted
Performance Measurement Baseline (PMB) updated to reflect detailed plans in the Fabrication, Assembly, Integration, and Test phase
Estimate to Complete (ETC) updated to idnetify differences between the budgets in the PMB and what we expect the final costs to be
Watch List
Re-design of TF lead area to reduce peak stresses
Resolution of TF support requirements at top of coil
Resolution of clearance issue with modular coil leads
Resolution of TF bundle properties (ORNL testing)