03 January 2005

To: Distribution

From: Wayne Reiersen

Subject: Minutes of 03 January Critical Activities Meeting

The weekly Critical Activities Meeting was held on 03 January at 10am.  Attendees included Tom Brown, Brad Nelson, Jim Chrzanowski, Phil Heitzenroeder, Mike Kalish, Bob Simmons, Larry Dudek, and Wayne Reiersen.  Critical activities are listed and discussed below..

- Twisted Racetrack Coil Design (part of Job 1403) and Fabrication (part of Job 1410).  Good progress continues to be reported in winding the TRC.  The cladding on the tee portion has been competed on one side.  Applying the cladding to the base has been halfway done on one side.

  - WP distortion and shim requirements. ORNL is still trying to make Pro-E models from the data points to figure this out.  The outside of the winding pack has been modeled.  Raftopoulos has sent the data needed to model the winding form surface.  ORNL reported at the Wednesday telecon that the measurements had been taken and that a Pro/E model had been generated from it.  However, characterizing the winding pack distortion (deviation from nominal geometry) and the optimal shimming remain to be done.

  - Shim design.  Chrzanowski proposed using hard shims between two layers (evenly spaced from the ends) instead of distributing soft fiberglass cloth between every layer.  The motivation for using the hard shims is two-fold: to improve dimensional control and facilitate fabrication.  Fan investigated the structural impact of using a single hard shim and there were no apparent drawbacks.  Nelson did not see any drawback to using two layers of hard shims.  Chrzanowski provide Dudek with a table of standard shim sizes and thicknesses, so these can now be fabricated.  No further tracking of this activity is planned.

  - Fabrication of piece parts.  Following the 13 December meeting, Dudek reported that it was critical that fabrication of the chill plates and fringe commence immediately if they are to be available on time.  DXF files of these parts were sent by ORNL on 17 December.  Nelson (RLM) provided authorization for Dudek to fabricate the parts per the DXF files in the absence of fabrication drawings (e-mail dated 22 December 2004).  Brown will confirm that all of the drawings (including those for the chill plates and fringe) have been received.  No changes to these parts are anticipated. Any changes that are required will be made in the field.  No further tracking of this activity is planned.

  - Cost and schedule control.  Fabrication of the TRC is schedule critical.  The application of the cladding and winding will be done on an extended working schedule.  Because of the schedule critical nature of this job and the uncertainty in how long each step will take, Chrzanowski agreed to develop a more detailed schedule by 10 January that he will use to report progress and forecast when the TRC will be finished.  Because we plan to use OT to get this job done within the time allowed, Chrzanowski will provide Strykowsky with updated cost and schedule information consistent with this revised plan.  This information should explicitly identify any outside procurements that need to be placed, e.g. the cladding and chill plates for the production coils.

  - Design and process refinements.  Application of the cladding and chill plates/cooling tubes are the things that most worry the technicians responsible for manufacturing the modular coils.  Cognizant design and manufacturing personnel really need to stay on top of the problems they encounter as they do these operations and strive to make refinements where dictated by the problems they encounter.  Chrzanowski is encouraged to pursue refinements in the winding station design and tools that might speed up the winding time and provide improved ergonomics for the technicians.  Specific changes noted thus far include the following:

    - Annealing the copper cladding has proven to be a big win.

    - Accelerating the cure time for the adhesive.  Chrzanowski has received an accelerator to speed the curing of the adhesive used to hold the cladding to the winding form.  Currently, this is the biggest time consumer (3-5 minutes per piece for the adhesive to set up).  With the accelerator, the adhesive now cures in seconds.

    - Modified cladding/chill plate/cooling design.  Application of the cladding has been hampered by insufficient space between adjacent pieces.  This sometimes requires filing or removal of copper “fingers” to resolve interferences.  Part of the problem may be due to the cladding on the tee being bent up (in the direction of the tee) during winding – this configuration was never modeled and checked for interferences in the design process.  Cladding design in the production coils should allow for increased space between adjacent cladding pieces (Williamson).

ORNL has looked into whether parts standardization (a dozen rather than hundreds of different parts) could be achieved for the cladding and chill plates and it does not look promising – no further work in this area is anticipated.

The other place where there is a problem is in the base cladding.  It needs to be pre-folded flat to avoid interfering with the winding clamps.  When pre-folded, the tab extends above the base of the tee, interfering with the winding process.  Shortening the tab would resolve this interference (see picture below).  This should be done for the production coils.  Chrzanowski agreed to provide guidance to ORNL on how much shorter the base cladding should be.

Dudek raised the question as to how these changes which affect the design of the production coils are being tracked.  He suggested that we write an NCR for each change as a means of tracking.  Chrzanowski was going to talk to Hinman (PPPL QA) about generating NCRs for tracking purposes.  However, later in the week, it was decided that a Request for Deviation (generated for approval in advance of fabrication) would be more appropriate for the procurements as well as in this instance.  Simmons to work with Chrzanowski to generate an RFD to document proposed in-process design changes.

  - Revised cooling design concept.  Heitzenroeder presented a revised cooling concept at a follow-up meeting at 3:30pm on 03 January.  The essence of the concept is to solder “straight” cooling tubes to individual fingers in the outer chill plate.  It is expected that this will be easier and cheaper to fabricate and provide improved performance.  A plan was laid out to establish the viability of this option with the following steps:

- Confirm that we can solder with pre-tinned tubing and chill plates (adding solder to fill gaps) without flux using Silvabrite (Chrzanowski).

- Check with JLAB on the solder (Heitzenroeder).

- Re-run analyses with the outer corner clamped to 80K to get Tmax in winding (Freudenberg).

- Change thickness of top and outer chill plates from 0.040” to 0.060” thick and re-run analysis (Freudenberg)

- Determine heat load at each cooling tube (Freudenberg)

- Re-layout coil cross section to determine if clamp needs to be modified to fit the two tubes through the corner region (Fogarty)

- Make chill plate mock-ups 0.040” and 0.060” and determine how to form the bends around the copper tubing (Chrzanowski).

- Make tubing solder trials using mock-ups, forming tools, and pre-tinned tubing – not sure if this can be done without the cladding being pre-tinned.  Maybe use flux core solder. (Chrzanowski)

If the results of the analysis and R&D look promising, the next step would be to use the straight T sample for a mockup.  If that was successful, the concept could be applied to the TRC.  Freudenberg provided an updated thermal analysis at the Wednesday telecon on 05 January.  An additional run is required with an 0.060” outer chill plate.  Fogarty, Chrzanowski, and Heitzenroeder should report on plans and progress at the CA meeting next week on 10 January.

  - Production clamp design.  There was confusion at this week’s status meeting about whether the drawings for the production clamps (not the winding clamps) had the right dimension for the vertical legs.  Chrzanowski to fit the production clamps and determine if they are the correct length.

- TF Design and Procurement.  TF activities were addressed in a separate meeting with Kalish at 1:30pm.  Preparations for the PDR appear on track.  The schedule is as follows:

07 Jan		Analysis of the TF design updated

TF SRD signed (Reiersen)

Scope sheets in place for all interfaces

12 Jan		Models and drawings updated

Design basis analyses posted as draft Analysis Reports

Cost basis documentation updated

Cost and schedule baselines updated to reflect procurement plan

Review panel selected, charge issued, agenda set

19 Jan		TF models and drawings reviewed/promoted to PD Release Level

Design Description for Conventional Coils and Structures updated

Design review package posted for reviewers

21 Jan		Dry runs of PDR presentations

26 Jan		TF PDR

An information meeting is still planned between the PDR and FDR.  Kalish needs to update the Manufacturing Web (see Marianne Tyrrell) in advance of the information meeting and finalize arrangements for that meeting.

The FDR is currently scheduled for 24 February 2005, about one month after the PDR.  For the FDR, the results of the beam test need to be available; analyses have to be checked; interfaces documented; models and drawings checked, promoted to final design release level, and ready for signature; and product specifications generated as required to support subsequent procurements.  Conducting the FDR on this schedule will be a challenge.

The long pole in the tent may be the beam test.  The straight T modular coil sample will be completed by 14 January, which means that fabrication of the beam can commence on 17 January.  That means that the mold has to be fabricated and materials ordered within the next two weeks.  The beam can be fabricated in the following two weeks, being completed around 28 January.  Torsion testing of the modular coil beam at ORNL should be done by then, so testing of the TF beam at ORNL could start at the beginning of February.  The point is that there is no time to waste.

Kalish has enlisted Raftopoulos to expedite the beam testing.  Nelson will make arrangements for beam testing at ORNL.  Brooks will provide the calculation checking.  Kalish will provide a detailed schedule for when the FDR deliverables will be completed, similar to the one developed for the PDR.

- VV Field Weld Joint R&D (Job 1206).

  - Weld prep geometry.  Nelson and Dudek appear to be converging on a one-sided beveled J-groove that provides adequate access to get the tungsten to the root of the weld.  Subsequent to the meeting, Nelson provided Dudek with a spreadsheet describing the proposed weld joint configuration (a MMES standard).  Dudek to perform trial welds using the proposed weld configuration.

  - Responsibility for field welding.  The current plan is to make the field welds at PPPL manually by PPPL welders.  ORNL has proposed exploring the possibility of MTM doing the field welding at PPPL.  The potential advantage is that MTM has a lot of experience welding Inconel.  The potential disadvantage is the coordination of their time with related expenses.  Viola to consider this pros and cons of this proposal and broach subject with MTM on whether they would entertain such an arrangement.

  - Design and requisitioning of final test article.  The requisition of the full scale test article was cancelled because of the protracted deliberations for finalizing the weld joint configuration.  The full scale test article would be quite expensive to procure, with a contract (unloaded) price tag of $125K.  Cheaper alternatives might exist such as [1] just welding flange pieces together cut from Inconel plate or [2] replacing the rolled Inconel sheet with stainless steel (as suggested by Viola).  Nelson to finalize design of full-scale test article pending resolution of the weld prep geometry and if MTM will do the field welding.

  - Tensile tests of weld joint.  Tensile samples have been prepared from the plates that were welded together.  Initial tests were performed at nominal stress levels for 250,000 cycles.  (The objective was to test them to failure.) Additional tests are required at higher load levels corresponding to perhaps twice the nominal stress, so a fatigue curve can be generated.  Dudek to coordinate completion of tests.

- VV port extensions welds.

MTM requested a change in the weld configuration for attaching the large vertical ports, the NB ports, and the large ports adjacent to the NB ports (port 4).  MTM would like for the port extensions to penetrate the shell rather than butt up against the shell.  Viola told MTM that the project will provide formal guidance re the proposed weld configuration by 12 January.  ORNL to provide guidance to Viola by 10 January re the proposed weld configuation.  Brown and Cole are asked to review the tolerance specifications (specifically with Diagnostics) for these ports and propose a revision if appropriate, also by January 10.

Goranson was concerned about the fit-up of the port extensions after they are cut off.  We may have failed to provide any requirements to assure that the fit-up is adequate for re-welding.  Goranson to consider adding a requirement to add temporary, internal frames to minimize distortions after cutting off the port extensions.

- Modular Coil Testing

  - Conductor Testing (Job 1406).  Kozub has reportedly pulled the long racetrack coil to failure – it failed at 23,000 lbs.  This information will be used to set the parameters for additional cyclic testing to be performed in January.  Chrzanowski reported that torsion tests are done, but problems were encountered with transverse compression test.  Kozub provided the results of the torsion testing on 15 December.  The results are posted on the Web and can be found by clicking here.  The transverse compression tests did not work out the first time through.  Chrzanowski noted that the NSTX work that Kozub was planning on doing appears to be slipping and that a window to complete the NCSX testing appears to exist.  Nelson provided guidance to Kozub on 07 January that the transverse compression tests should be postponed indefinitely and that cyclic testing of the long racetrack coil and LN2 temperature should be performed with a load of 20,000 lbs.  Chrzanowski to expedite completion of NCSX conductor testing.

  - Beam Testing (Job 1403).  ORNL reported on the 3-point bending tests at least week’s Wednesday telecon.  The results are being analyzed by Fan.  Torsion testing of the beam is next on the agenda.  Nelson to expedite testing at ORNL and report on how Fan’s results should be used in the analysis effort.  It is critical that this be completed by the end of January so the fixture can be used for testing the TF beam.

  - MCWF Fracture Analysis (Job 1404).  The data from the NHFML had seven orders of magnitude of scatter with some points better and some worse than our reference CF8M data.  The pedigree of the data has been sorted out.  It was determined that the samples were cut from risers and other places not representative of the high stress regions.  Additional samples will be cut from [1] the shim stock from the prototype [2] the EIO prototype coil (around port openings) and [3] the first production coil (around the port openings) and tested.  Heitzenroeder has developed a plan that will be implemented.  No additional tracking at this weekly meeting anticipated.

- Modular Coil Design (Job 1403).  A recent study by Brown suggested that reaming all of the holes for assembling the modular coils into a shell may be very difficult.  It was not clear that reaming all of the holes was necessary.  It was also clear that a means of positively locking the bolts was required. Nelson reported that Williamson is adding a model of a commercially available reamer to the Pro/E model to determine which holes would be feasible to ream.

The loop between testing and analysis needs to be closed.  We have done a lot of tests for the purpose of establishing material properties and design allowables.  However, we need to go one step further and document what values we want the analysts to use.  HM Fan has tabulated the results of tests related to material properties which tend to be multi-valued.  A group will need to review the data and the NCSX structural design criteria and arrive at material properties to be used for analysis.  There will in all likelihood be a range of properties to be used in the analysis to get the possible range of structural response.  This needs to start as soon as possible, so it may be the topic for the WBS 1 meeting on Jan 5.  Nelson to arrange for group review of test data.

- PF Solenoid Make, Buy, or Scavenge.  There has been discussion lately about making the solenoid coils in-house in the first part of CY05 ore even re-using the excessed PF1A coils from NSTX.  Reiersen did a study which indicated that the PF1A might be used in place of PF1-3.  Zarnstorff to perform simulation modeling to confirm conclusions.  If we choose to go this way, Kalish will have to add a PF1A refurbishment task to his scope and Ramakrishnan will have to revise his plans accordingly.

Neilson concluded that there is insufficient management reserve available to commit to building the solenoid coils in house at this time, so that option has gone away.  We still need to decide between re-using the PF1A coils and buying new solenoid coils, but the urgency of that decision has abated.

- Test Cell Preparations and Machine Assembly (WBS 7 jobs).  In discussions regarding machine assembly, a question arose regarding when we would know what the upgraded crane capacity would be.  It is expected that the “break point” for the upgraded crane capacity will be between 40 and 45 tons, but we will likely not know for a year or so.  It would be prudent therefore to plan on 40 tons.  Cole to update our assessment of the maximum weight of a FPA to determine what margins exist.

- Upcoming Design Reviews.

  - TF PDR – 26 Jan 05.

  - MC Turning Fixture PDR – 23 Dec 04. Brown to update review schedule.

  - Base Support Structure and Cryostat PDR – 17 Feb 05.  Gettelfinger to provide schedule for completing PDR deliverables consistent with the new PDR date.

The next meeting is scheduled for 10am next Monday, 03 January in the Engineering Conference Room.

Cc: Neilson, Strykowsky, Brown, Heitzenroeder, Chrzanowski, Nelson, Dudek, Perry, Kalish, Gettelfinger, Viola, Tyrrell, Brooks, Zarnstorff, Williams, Williamson, Cole, Goranson, Simmons