Jim Anderson

- Presentation for the Lehman review went well

- Problem are not behind us we have to balance

- Be overly positive for FY 08

- Need to enhance communication for our success

- Will start to send PPPL engineers to ORNL to help out

- Ideas needed on how to move forward with the project?

- Question to be answered by close of business today or latest Monday

- What things would you do to prepare early?

Bob Simmonds

- Can’t identify things in FY 09

- Waif will be posted on the web

- Lehman team might drill down to your costs; have the documentation to back it up.

- Specification C & GRD processed and needs signature

- CCB meeting on Friday

Ron Strykowsky

- Go forward & be proactive, have that message come through get the design behind us

Mike Viola

- VV on schedule

- Trials slightly ahead of schedule

- Finished up gross fits and found interference that are be further measured and analyzed

- Metrology support good

- Need Crane operator [This is an issue]

- Be proactive staffing techs

- Need real-estate by January time frame

Jim Chrzanowski

- Moving forward

- Finished Chill Plates

- Potting will happen after Labor Day.

- Back to two shifts

- Two techs borrowed need to be returned

- 14th coil will be impregnated.

Larry Dudek

- Are the Blue sheets approved for new hires?

- Studs to arrive by August 15th

Brent Stratton

- Faulty measuring meter (fluke meter was used)

Mike Kalish

- Everson visit the TF coil went into the oven and going to the cryostat today

- Question? Where to put TF coils when they arrive? Coil might show up next week

- QA support has been good, need to finish up final NCR’s

- Will need more QA support

Bob Ellis

- Friday wrapped B-1 coil

- Flange scanned and finalized tool bolt flanges

- Waiting for tools on order to move forward

- A-6 and B-6 are being measured

Hutch Neilson

- Deliverables are promised for release our data by August 3rd

- After Dry Run presentation for Lehman review please add commits immediately, need quick turn around.

- Mike, Erik and Tom presentations need to be looked at one more time

- Finish up by Friday for Lehman review

- Work package managers need up-to-date presentations from the Coward review, may be needed upon request by Lehman review.

Phil Heitzenroeder

- Prepare to cut up samples and send out is reasonable without process weld.

Wayne Reiersen

- Reminder: two upcoming Design Review; Weld Shim and C to C next Tuesday

Mike Cole

- Drawing status: responded to what ORNL needed

- ECN documentation to be closed out

- July milestones were fulfilled

- Bolts – need short one to do the shear test milestones

Tom Brown

- Working on Station 3

- Vacation next week

Fred Dahlgren

- Coil Support PDR successful

- Thermal stresses currently still designing lower structures.

Jim Lyon

- Finished slides and needs our revised Org. chart

- Jim Anderson will close that loop regarding the Org. chart update