Jim Anderson

- Don Rej will be here this Thursday and Friday with his wife

- Don Rej agenda is still tentative, will email out and if you have a conflict please let Jim know

- Upcoming review is a very big deal and should treated as such

Hutch Neilson

- A meeting was held yesterday regarding the Dry Runs for the Construction Feasibility review

- Dry Runs will be held October 26 and 27

- Bob Simmons is working with Mike Viola to construct a chart of the Assembly Sequence (if plan A doesn’t work, then what is plan B)

- Fred Dahlgren working on the Structure Plan

- Mike Kalish is working on the TF coil plan

Mike Kalish

- TF 3 & 4 is in house

- Working with Tom on the electrical testing

- Visited Everson on Monday and discuss the BPI of the coils

- TF 6 winding still needs the last layer

- Next Thursday, Everson will visit the lab to discuss our quality controls and cleanliness

- Mark Smith & Red are measuring the coils with the Romer Arm; they still need work requests, which will be taken care of.

- Working on Trim Coil PDR, to be scheduled November 1 or later

Tom Brown

- Station 5 analysis is still being worked on, need to get with Mike Viola and Bob to finish

Jim Chrzanowski

- HR is involved with hiring an additional designer to work on the TF coils

- Modular Coil B5 is on it’s second side

- C-6 will be flipped on Friday

- The surface of B6 measurements are done

- Thermal Couples arrived, still need specification from Larry Dudek

Bob Simmons

- CCB was postponed

- New B specification is being prepared

- Updated Risk  Register will be posted today

Judy Malsbury

- QA Audit of the TF coils was postponed till after Construction Feasibility review

Larry Dudek

- Two batches of 428 shims arrived

- Thermal Couples arrived for Jim Chrzanowski

- Permeability is high on 40 shims, 10 shim will be tested and the other 30 can become production shims

- Add 2 or 3 weeks for production shims

- Weld test C02 pelts need rice pelts

- Needed and found special bottle of C02 for C02 gun

- The C02 gun is a smaller version of the gun used on W7X weld tests

Fred Dahlgren

- Mike Zarnstorff concluded that the PF 1A coil can run at higher levels than original designed, 47 Kilo Amp

- Put spherical bearings on the base support

- FDR will be scheduled at the end of November or early December

Steve Raftopoulos

- Mark Smith is working on weld test metrology

- A requisition was put into the system for a third laser tracker

Bob Ellis

- Pre-measuring is going along ok

Mike Viola

- The critical path for pre-measuring is ahead of schedule for TF coil A1 and B1 and Station 2

- Nose weld design PDR is this Thursday at 1:30 PM

- Alumina shims have not arrived