Jim Anderson

- Ron, Hutch and I are working hard with Rich and Rob on the report to Ray Funk as to why NCSX should go forward.

- Ray will then report to Ray Orbach

- Safety First, going forward at the Wednesday meeting we will have one person talk about the safety processes/precaution in their jobs at the lab.

Ron Strykowsky

- Mike Viola still needs to give me his costs and schedule for his job.

Don Ray

- I accepted the position with NCSX that would replace Jim Anderson

- I will still be a Los Alamos employee and will live here in Princeton for 2 yrs.

Hutch Neilson

- The Construction Feasibility review went very well.

- There were 17 recommendations, which will be log just like the Lehman reviews

- The status meeting yesterday, still need information for the Field Period Assembly 2-5 cost and schedule from Mike Viola

Phil Heitzenroeder

- FDR for Welded Interface will be on November 27, 2007

- Kevin is working on analysis, the stress are looking good, we need to adjust the shim plates

- Statement of Work was submitted for Edison welding to do the independent welding

Jim Chrzanowski

- Modular Coil C-6 and B-5 are bundled, adjusted and wound

- Coil C-6 will be in the autoclave by December, coil B-5 early January

- Coil A-6 is mounted in the ring

Mike Kalish

- TF-5 is almost done at Everson, they are sending two TF coil at a time, so Everson will send TF-5 and TF-6 together, to be delivered week after next

- We to assign someone responsibility for storage space for the TF coils

- The TF coils will be stored in the NCSX test cell after the floor is finished

- TF-3 is now on the weld bench, will be moved Friday

- Trim Coil review we need resources to work out the chits

Judy Malsbury

- Audit for the Field Period Assembly, Station 1 will be in December

Mike Viola

- A-1, B-1, C-1, A-2, B-2, and C-2 are completed, the critical path is restored

- C-2 Coil is completed Field Period Assembly

- Shim and alumina material still needed for the nose

- C-2 will be replaced today

- I need Larry Dudek to expedite the port insulation and heat tape, and thermal couples to keep work on going.

- Station 2, 3, and 5 of the sequence plan is done

Bob Simmons

- NCR for the VVSA is still needs to be resolved by Paul Goranson

Mike Cole

- Drawings are fine and still improving

- Still need to give Ron analysis results

Steve Raftopoulos

- The Photogrammetry vendor were at the lab for two days

- C-2 coil took a few hours

- Photogrammetry is better than the laser tracker

- There is a requisition in the system for hardware, we already have the software

Fred Dahlgren

- Coil Structure design is completed

- Building material is still needed

- We have located 304 L stainless steel, which has102 -103 permeability

Larry Dudek

- Trial batches were sent to White Engineering for flame spraying

- The rest of the shims will be annealed and picked up and re-ground, turn around time less than two weeks

- Found a source of 316 L and it in Procurement and should be here soon

- We found a European vendor with 316 LN and could have it here in one or two weeks.

- Miller was here for Mig welding, the shim welding came out very nice

- We should purchase the simple welding machine and not the complex one due to programming difficulties.

- Bob Parsells is working on the casting weld procedure

- Welding procedure calls for one qualified welder

- QA will do the inspection, which is included the welding procedure.

Bob Ellis

- Working on the Dimensional control plan for the Coil 2