Jim Anderson

- Hutch, Rob and Rich are at the APS meeting.

- Ron, Hutch and myself are working on whether we have additional money for NCSX

- The question Ray Orbach has about NCSX, Can we get good physics from this machine?

- A request for another designer to help Tom Brown has been expedited.

Mike Viola

- Assembly has begun and A1 is on the wedge

- We have a draft of the MITQA Plan and the procedure

- Metrology laser trackers has racked in 3 to 4 thousands

- We will use regular steel shim (shim are custom ground to the correct shape) for A& B coil to practice and learn.  There will be a  three weeks of trails

- We will be welding the nose the second week of December

- Sheer plates and pucks will be two weeks after the nose, we need alumina shims

Tom Brown

- An email we sent Tuesday night regarding the B to C fit up, the chill plates are 1/16th out of tolerance.

Phil Heitzenroeder

- We are moving forward with pre-preparations for the welded interface, working with Peter Titus, he agreed from an engineering point of view, what was down on the fatigue side

- Erik Perry suggested to have secondary review, preliminary feedback due by next Thursday

- Mike Kalish is moving forward with TF Coils, coil 5 & 6 will be shipped; Everson is shipping two coils at a time.

Red Delany

- C1 is in the shop ready to start grinding the repair for the interfaces

- Mike Anderson is working on the repair of the chill plates

Bob Simmons

- MITQA plan was sent out for Station 2 & 5 were revised, comments needed

- Tom Brown gave test Station 2 drawing to me

Mike Cole

- Mike Voila asked for a draft version to the station 2 assembly specification and I sent a copy this morning.

- Primary activity is preparing for the 27 Nov FDR for the inboard interface

- Drawings have been issued for comments

- Kevin is preparing documentation for analysis.  We meet with Pete Titus to do a preliminary review before the FDR

- Tom Brown asked if we could check – 25 drawings before Thanksgiving and I agreed to check the drawings.

Hutch Neilson

- NCSX coil structure should we use aluminum or stainless steel material, this was discussed with Peter Titus.  Aluminum cool down is faster

- The Structure FDR will be the first week of December, Fred Dahlgren

Paul Fogarty

- Two technicians are needed for the lower bolts, which are still being made

Ron Strykowsky

- We have a open hole with the Field Period Assembly

- Assembly sequence $100,000 impact in two months and I need to talk with Mike Viola regarding this issue.

Jerry Levine

- Safety Forum is on Tuesday, Nov 20, from 8:30 -3:30 in the MBG auditorium

Larry Dudek

- Thermal couples is out for quote

- All shim were annealed and are not out for grinding

- 316 L will be here Friday for the inboard shims

- On November 29th two or three welders will visit the vendor Miller, we will bring our own material to weld

- White Engineering has a batch of shims to be flame sprayed

Steve Raftopoulos

- The coil guys are spread out, short on manpower

- Modular Coil B-5 is on hold

- The two Romer are back from repair and the one failed and other one is down/broken

- Modular Coil A-6 is in the ring

- The requisition for the Photogrammetry system will be a best value procurement

Art Brooks

I had a question regarding moving forward with tolerance recovery?