Mike Kalish

- Coil #2 and Coil #3 complete and ready to ship, except for the dry spots.

- Everson quoted a price for the crates $500.00 for each crate and the will speak to Rod regarding the changes to contract.

Mike Viola

- Metrology has stopped all measurements due to technical problems.

- Phil, Larry and Mike spoke regarding the shim test

- VV needs more clips (name of clips unknown)

- Chain fall failure last week poor quality, made in China

- Chain falls will be exchanged, working with Arlene White to resolve this issue.

Hutch Neilson

- All but a few responses were sent back to Hutch regarding the Lehman Review questions. Please send in responses if you have already done so.

- NCSX Science Review is September 15-16

- Hutch will send out draft agenda for Science Review

- Mike Cole and Dave Williamson to meet up with Phil to discuss the interface.

Ron Strykowsky

- Statusing Meeting is tomorrow (Thursday) and will start early due to Mike Kalish schedule.

- Risk Register is a living document please add increased risks or decrease risks to document

Jim Chrzanowski

- Modular Coil A5 putting outer epoxy, should Auto Clave on Friday

- B5 cladding and B-4 stripping off mold

Bob Delany

- A5 and A6 to shop

- Waiting for C coils and metrology is holding up work

- Need C’s to drill holes

- Storage problem in shop resolved

Steve Raftopoulos

- Trouble with two laser trackers working with Bill Sands and Mark Smith to resolve noise and other problems.

- May have to bring Leica or Verisurf in to fix problems.

Paul Henderson

- Have wireless cards for Parallel laptop and Leica computer

- Working out network problems for Metrology computers

John Edwards

- VV (2) 50% done loop termination

- Lock on A & B

Brent Stratton

- Diagnostics has slowed down on the Rogowski work.

- Work will resume in October when two PPPL’ers are caught with NSTX work.

Mike Cole

- Weld Test distortion in the wing area

- September 11 milestone has been rescheduled

- Welds need to be made and verified AA, BB and CC