Jim Anderson

- Will be on vacation from Sept 27-Oct 8, 2007, Phil will be filling in while Jim away

- Received a memo from Greg Pitonak that NCSX needs a Technical review sometime in the beginning of November to answer the question can we build NCSX with the tolerances and if the machine will operate from a physics point of view.

- Possible dates for review will be Nov10-13

- Working on putting together a review team for Technical review

Hutch Neilson

- Regarding the Technical review we need to answer the questions with confidence.

- Three key items to worked on;

  - Follow modular coil interface design

  - Assembly & dimensional controls with high confidence

  - Trim coils – what is there role on the machine, cost, how many and where do they belong?

Ron Strykowsky

- Next Wednesday the monthly meeting, be prepared!

- Job managers check all your cost pressures

Mike Cole

- Shims for Shear test needed, we already have the bolts

- Drawings for Station 2 still need commits from everyone except for Tom Brown.

Larry Dudek

- Gettelfinger shims should be here this week

- Production shims are 75% done, won’t ship for two weeks

- Station 3 fixture out for bid

- Keilbach to look at welding plan with the help of Parsells, they will be here next Tuesday

- Looking for new Weld Engineer, Bob Keilbach retired (

- Bat insulation is in house and just waiting for thermocouples

- Strain gauges to go on the last field period

Phil Heitzenroeder

- Welded interface and shim designs with the help of many

- Mike Viola did the bushing tests

- Analyzes Peer Review by next week

- Working with Brookhaven to help with Metrology issues, conference call is this morning.

Mike Viola

- Major Tool gave us valuable information regarding Metrology

- Determined the problems were common and they use the old software and not to listen to the noise and just keep measuring

- Critical path for modular coil A1 used more days then allotted, 13 days were allotted for each modular coil.

- A2 & A1 moving along with two teams and already back on track

- VV support weld trials are ongoing

- A 1 nearly done and thermocouple still waiting for delivery

- October 22 to start Assembly design procedure, which is a A to A fit-up

- First A & B to start November 27, 2007

Steve Raftopoulos

- Learned new techniques working with Metrology with the help of Major Tool.

- The one Romer arm is back from repair

Bob Simmons

- The Risk register is now posted on the NCSX website

Tom Brown

- PDR needed for Station 5 by the end of next week

- Redoing Sequencing Plan Rev. 8

Jim Lyon

- Hired new project support person to work with Mike Cole

Tom Meighan

- VPI of modular coil A5 is completed and still working on the others

Jerry Levine

- Be aware of the safety hazards with repetitive stresses

- Injuries can shut down any project

Mike Kalish

- TF 4 shipping Friday

- Contract Amended, purchased 15 crates

- TF 5 ground wrapping

- TF 3 path 1/2 lap layer and cryo tested

- Requested cryo tests for TF 5 & 6 for a data point

- Requested spot checking with our Romer arm

- Getting together with Art Brooks to complete the Trim Coil estimate