Don Rej

- Rob and Rich were at the FESAC meeting with Ray Fonck and Dan Lehman, and Rob & Rich did not reveal the new baseline number.

- Pam Hampton has posted a website for the Princeton University review hold on March 13 & 14, 2008.

- Lutz Wegener, Peter Titus, George Coward and Dan Lehman will expect the judgment and the overall confidence and the staffing for NCSX.

- Thank you to Bob and Ron for working on the WAF’s

- The two key documents for this review will be the resource loaded schedule and the WAF’s and you must have supporting documentation with a level of maturity.

- April 8-10 will be the Lehman review, we need to focus on the best final baseline and not the why the new Baseline changed.

- May 21-23 will be the Construction Review

- There will be no Dry Runs for the Princeton University Review, but the Lehman review will have Dry Runs.

Ron Strykowsky

- The Princeton University review will be a tabletop review, including the scope, WAF’s, schedules, drawing and any other information.

Bob Parsells

- We are two weeks away from the approved tension test, and had friction problems with the shims, samples were shipped out to Edison.

Jim Chrzanowski

- This Thursday we will VPI coil C-6 which is the 15th coil and today will we shell and bag.

- The B-5 coil will be in the autoclave on Friday and VPI on Friday

- A-6 is the last coil

- B-6 still needs to be wound, measured and adjusted.

Bob Simmons

- All job managers need to look at the categorization and clarify and check the Risk Manager A

- The timeline excel version was sent to Paul Goranson for jobs 1204 and 1260.

- Each and every number should have information and back-up to justify the numbers and that will make the reviewer very happy.

Charlie Gentile

- I am working on accelerating the documentation, the Technical Safety, Safety Assessment documentation.

- If something is out of the box we will find out right away

- I met with Al von hall and Cheryl Such regarding the FMEA procedure.

Mike Kalish

- The TF #4 is in the metrology table last week, there was a discrepancy in the back leg.  There is more effort maching than measuring.

- We should stand the coil up to measure in the future, we should measure the coils ahead of time and this should be put on the Risk Register.

- Tom has looked at the tight fit of the trim coil and to same time with assembly the coil should be split in the middle.

Hutch Neilson

- We need work on the design maturity and progress

- I need the forecast of FDR and PDR from the following people Goranson, Brown, Kalish, Raftopoulos, Chrzanowski, by the end of business today.

Jerry Levine

- There is a concern with the Ventilation system in the Test cell?

- Henry Carnevale is working on this issue; this not yet fully designed, but should be completed this business year.

Raki Ramakrishnan

- The Coil Protection review is this Friday at 10:00 and all concerned should attend to move forward.

- The cables should be terminated by the end of the month.

Larry Dudek

- The bare metal shims have arrived and 170 are onsite.

- The plan studs are in house as well.

- The friction test was good .25 and .35 and after a 25 cycles it go to .4

- The 22 shims are ground down to size; we will shift to G-10 material.

- The G-10 for the sandwich assembly and the G-10 thickness is .035 and there will be 3 or 4 different thickness by next week.

Al vonHalle

- Heads up, there will be over 100 people from the Regional Science Bowl visiting the laboratory at 3-5.

Tom Meighan

- The TF #7& #8 will ship from Everson to PPPL this week.

- The TF #9 is at Atlas for maching to the wedge

- We are ground wrapping TF #10 next week and then we will VPI next week.

- The TF 11 is on layer number 2

Fred Dahlgren

- The Base Support drawings are being checked and added the floor structure and should have this analysis by next week.

- Joe Rushinski is working on the Field Coil Support and not having good progress with that.

- The TF mounting brackets and TF coil disconnect molded surfaces should be done early on.

Mike Cole

- The drawings were issued on the Formica and will have a discussion with Phil

- The leads for the MC designs will be looked at with Tom and Art.

- I am working with Phil to resolve the chits for C to C.

Jeff Harris

- We need to reduce of our risks with the R&D

- I know comments are needed and I may need to run over people to get the rough estimate and maybe we should put a place holder.

Phil Heitzenroeder

- The Shims Peer Review will take place on this Thursday afternoon.

- Kevin is doing the friction analysis with conservative results.

- The two end bolts have no movement; the ECN will be done next week.

Pam Hampton

- There will be a Project Management Review calendar for job managers, it will be available to offsite people in a public folder, and the idea came from Brent Stratton.