Jim Anderson

- Meeting tomorrow in Washington with Pat Daimler, Ray Orbach’s deputy to discuss the status and key points of the NCSX project.

- If anyone has any breaking news regarding the NCSX project, please let me know by via email or phone.

- I will be out this Friday and Phil will be acting Project manager.

- Brian Dandrea and Don Trost from Tech Source will visit the today at 10:45.

- A meeting is scheduled today at 3:00 with Rich and Rob to discuss what will be discussed with Ray Fonch and Pat Daimler.

Jeff Makiel

- Safety first is Key; no short cuts should be taken in the field to help pull the NCSX Project back on schedule.

- PPE Equipment must be available to all field crews.

Phil Heitzenroeder

- Bob Parsells is working on the welding qualifications.

- Mike Viola ACC review went very well.

Mike Kalish

- The trim coils design is still being worked on; it is unlikely that the requirements will change.

- Monday, January 21st there will be a meeting to discuss the trim coil designs

Tom Brown

- The final drawings for Station 2 still need to be signed by Mike Viola and Larry Dudek

- Jerry Siegel has signed/stamped the drawings and is printing them out this morning.

- Working on the lead routing drawings for the machine

- Geoff Gettelfinger has informed us that the commercial flex cable failed

Hutch Neilson

- The cost and job estimates updates are needed for the critical path for the Field Period Assembly.

Bob Simmons

- The construction documents were moved over to the NCSX website.

- Please complete the Ethic’s form for Cyber Security, first save the results in a word form and then send, otherwise the information will be lost.

Steve Raftopoulos

- The Photogrammetry bids are final and Arlene White will notify the winner and the options that are needed.

- The third Laser Track arm is needed in the field

- The monthly calibrations (field checks) will be the my responsibility

- TF coil measurements are still needed for Mike Kalish

Ron Strykowsky

- The staffing for the Cryostat and Metrology areas are still needed.

Don Raj

- I will be visiting PPPL on February 4th

Mike Cole

- The Station 2 drawing were approved

- The drawings Gary McGinnis completed are out for signature

- Re-baseline information was sent Ron

- The Station 2 specification still needed to be completed

- Gary and Kevin C to C meeting regarding the status of the shim,

- Final Design Review will be held on February 4th.

Jim Chrzanowski

- We are still in the market for a designer for NCSX, one designer declined our offer, and one is ready to start immediately.

- C6 and B5 VPI bag was installed

- I will be out of the office all next week Jan 21-25, 2008

- Field Period Conductor spec went out yesterday for comments and they are needed back ASAP.

- The Field Period FDR will be held February 11th.

Judy Malsbury

- The Station 1 audit debriefing was held last week.

- QA is down to one inspector, due to Colin Phelps leaving PPPL

Jerry Levine

- The ACC review for Station 2 went well on Tuesday

John Edwards

- The first shipment of coated shims arrived

- When the rest of the shims arrive we can move forward on a steadier pace.

Tom Meighan

- The TF coils 7 is at Everson, Coil 8 is in the mold and then into the oven

- The wedges are slipping behind schedule

- The winding for coil 10 will begin today, Wednesday

Mike Viola

- The Field Period Assembly is going well, and will accept the testing of the shims first thing on Monday, Jan 21st.

- I have reviewed Hutch’s email regarding metrology and shift work, the schedule is not realistic as of now and this needs to be discussed.

- Ron Strykowsky has concerns with the use of the crane on the NCSX project

- TF coil will only taking a couple of days and the crane work will only take a few hours.

Larry Dudek

- The 115 shims were delivered and the remainder will be done at 25 per run, the vendor will send 100 batches at a time.

- The 105 rough shims will be annealed and then sent back to the vendor, there is a total of 550 shims

- Station 3 Assembly Fixture arrived and will be stored in the NCSX test cell.

- The heater tape for the port extensions can be used for fill in work

- The regional representative for Miller will re-visit the lab to work with the welders, per Bob Parsells suggestion.