Jim Anderson

- Stew Smith , Rob, Rich and myself are working on a  dates for the upcoming Lehman review

- Dan Lehman will be available the whole month of April.

Jim Lyon

- I will be retiring from NCSX and the position will be given Jeff Harris.

Mike Cole

- I am working with Gary McGinnis and Mike Viola on the inboards shims and the pucks.

- C to C FDR will be held on February 4th, 2008

- Working on the final specifications for the half period assembly design which is behind schedule.

Mike Viola

- The FP assembly B & A coil are 34 thousand and the required is 60 thousands

- Bob Parsells developed a slide table to help the process

- The alumina shim friction is .55 and will drop to .42 is used, if filed down it will drop to .35.

- The shim lumps are 1000 thick, which is problem

- The vendor produced more than dozen shim that were usable

- The computer in the field had a problem with Art Brooks excel calculator, problem being addressed by Harry Towner.

- The tool crib and Roland Snead old office is being converted to a tool shop.

- Each station will outfitted with there own toolbox, cost $3500 per toolbox.

- Two new machine are being purchased, a 3 axis machine and a grinder

- The ACC Review was successful.

Larry Dudek

- The 88 out of 115 shim were rejected, so 26 are usable

- The shim will sent back to the vendor (White).

- There are 74 bare shims from Sinox that will arrive sometime today.

- White Engineering process of the shim is automatic and the A&A’s process is done manually.

- Sinox is working on a new batch of shims and will have by next week.

Phil Heitzenroeder

- The major issue is with the shims and I will talk to Geoff Gettelfinger regarding the thickness of the shims

- The first shims specimens were 24 mil thickness

Hutch Neilson

- We need to update our tracking log from the Lehman and Construction Feasibility reviews, the following people comments are needed; Larry Dudek, Steve Raftopoulos, Paul Goranson, and Erik Perry for open items.

- The General Requirement document needs input from the follow people; Mike Kalish, Mike Zarnstorff, and Art Brooks

Ron Strykowsky

- A reminder that all WAF inputs are due by this Friday

- A WAF is the only appropriate document that show estimates

- Monday - the Interface cabling and INC systems

Tom Brown

- A new designer started last week

- I need to give Mike Viola the information for Station 5

Don Rej

- We are grateful to have opportunity to be asked by DOE to present a re-baseline for NCSX.

- I will be at the laboratory in two weeks

Judy Malsbury

- The QC inspector position has been posted and if you know of anyone, please let us know.

Tom Meighan

- The MC winding is on schedule

- The TF coils are a different story, TF 8 was VPI, TF 9 is being ground wrapped and TF 10 is on its third layer.

- B5 is ready to be have the bag hold put on

- C6 has the final lead and still doing the prep work

Al vonHalle

- Question regarding the TF Coil power supply?

- There are 48 coils and 48 circuits

- INC interface Erik Perry has taken Ray Gernhardt estimates and will move follow.

Paul Henderson

- I will attend Harry Towner 11:00 meeting this morning to discuss the megabits and the change to terabits, similar to what NSTX uses.