|  | SC Project Review of NCSX April 8-10, 2008 J.H. Chrzanowski- page 1 |  |
| --- | --- | --- |

Modular Coil Manufacturing Update

J. H. Chrzanowski for the NCSX Project

|  | SC Project Review of NCSX April 8-10, 2008 J.H. Chrzanowski- page 2 |  |
| --- | --- | --- |

|  | Requirements, Design & Interfaces |  |
| --- | --- | --- |

Requirements:

– Manufacture 18 modular coils that meet the design requirements

as defined in the GRD and SRD.

- Maintain Stellerator symmetry

- Maintain tight current center tolerances [+/-0.5 mm accuracy]

- Operate at liquid nitrogen temperatures

- Design:

– Design documents are complete

- SRD, Specifications, drawings, manufacturing procedures

- Interfaces:

– MC interfaces with numerous systems as outlined in SRD

- These interfaces are continuing to evolve as machine assembly is

completed

- Vacuum vessel, TF coils Cryo-systems, FPA, etc.

Modular Coil Status

|  | SC Project Review of NCSX April 8-10, 2008 J.H. Chrzanowski- page 3 |  |
| --- | --- | --- |

Progress at last Project Meeting- August 16, 2007 : – 13 Coils have been Vacuum Pressure Impregnated (VPI) and 14

through the winding process

- Today's Status [April 8, 2008] – 16 Coils have been VPI’d and 17 are through the winding process

| MC ID Number | VPI Date | VPI Status | Post VPI Completion Date | Post VPI Status |
| --- | --- | --- | --- | --- |
| A5 | 9-20-07 | Complete | Complete | Complete |
| C6 | 2-14-08 | Complete | 4-18-08 | In progress |
| B5 | 2-28-08 | Complete | 5-9-08 | Not started |
| B6 | 5-15-08 | Bag Mold Prep | 6-23-08 | Not started |
| A6 | 7-15-06 | Pre-winding | 9-1 7-08 | Not started |

- The last modular coil will be VPI’d by July 15, 2008

- All Post VPI work will be completed by September 17, 2008

Tracking Punch List Items

SC Project Review of NCSX April 8-10, 2008 
J.H. Chrzanowski- page 4

• Majority of punch list items have been completed.

• Remaining items include: Strain gages, additional

thermocouples, flange interface modifications [as req’d]

Cost and Schedule

|  | SC Project Review of NCSX April 8-10, 2008 J.H. Chrzanowski- page 5 |  |
| --- | --- | --- |

• Modular Coil cost estimate is based upon detail task breakdown and

actual in-field times to complete coils

– Based on: 17 coils wound and 16 VPI’d

- Budget increased for procurement and installation of additional

thermocouples that were added to the design

- Budget increased additional shop hours - unidentified work associated

with modifications of winding forms during fit-up in support of FPA

- Last Modular Coil will be VPI’d by 7/15/08 [target date]

- Post VPI items complete by 9/17/08

- Punch list items complete by 11/6/08

VPI

Las

SC Project Review of NCSX April 8-10, 2008 
J.H. Chrzanowski- page 6

Schedule

Schedule-continued

Post VPI items comple

items com

Punch list

plete

e

|  | SC Project Review of NCSX April 8-10, 2008 J.H. Chrzanowski- page 7 |  |
| --- | --- | --- |

Present

Schedule

0

1

2

3

4

5

6

7

8

9

10

11

145 
145

12

13

14

15

16

• MC Manpower Plan:

– Presently working single shift x 5 days a week

– We have a plan for the orderly down sizing of modular coil

manufacturing team

– Size of production team will vary as required to complete modular

coils [Peak 18 technicians	today 8 technicians]

Manpower Down Sizing Plan

SC Project Review of NCSX April 8-10, 2008 
J.H. Chrzanowski- page 8

SC Project Review of NCSX April 8-10, 2008 
J.H. Chrzanowski- page 9

|  | Manufacturing Area |  |
| --- | --- | --- |

• We have begun transferring real estate to FPA teams as MC stations

are shut down.

- Station 2 winding station was transferred to FPA on 3/1/08

- By 7/31/08 all areas except for Station 4 and the autoclave will be

transferred to FPA

Uncertainty of Estimate

|  | SC Project Review of NCSX April 8-10, 2008 J.H. Chrzanowski- page 10 |  |
| --- | --- | --- |

High level of confidence in estimate

Results in highest impact [7.5 months to replace coil]

[14 coils have been electrically tested]

2-3 month impact on project schedule [If coil 18 had to be replaced]

Residual Impact

SC Project Review of NCSX April 8-10, 2008 
J.H. Chrzanowski- page 11

|  | SC Project Review of NCSX April 8-10, 2008 J.H. Chrzanowski- page 12 |  |
| --- | --- | --- |

|  | In Summary.... |  |
| --- | --- | --- |

17 modular coils have been wound and 16 VPI’d

- Have begun down sizing of coil manufacturing team from peak

level of 18 technicians to today’s level of 8 technicians

- Have begun transferring manufacturing real estate to FPA teams

- Successfully addressed all of the technological challenges.

- Safety continues to be in the forefront of all planning and

performance of field activities

- The NCSX Project is committed to completing the manufacturing of

the Modular coils by September 2008. (inc. final electrical tests)