## TF BOM
REV 9-14-05
Part Number | Rev | Description | NEXT ASSY | Type Name | Qty | Order Qty | Material | Procurement Method | Procurement Package | Authorization Notification | Requisitioner | Specification | Status | Activity ID | Forecast Start | Forecast Finish | Budgeted Cost | Expected Cost
se131-003 | 0 | TF COIL ASSEMBLY |  | Assembly | 18 |  | SEE DETAILS |  | N/A |  | N/A | NCSX-CSPEC-131-01
se131-085 | 0 | TF COIL NOSE CASTING | se131-003 |  | 36 | 36 | NCSX-CSPEC-131-03 | PO | RE403108 | 2005-08-03 | Kalish | NCSX-CSPEC-131-03 | Requisition Approved Req 403108 RFQ is on the street |  |  | 2005-12-19 |  | 198000
se131-077 |  | WET WRAP GLASS / RESTRAINING COLLAR & WEDGE CASTING SUPPORT | se131-003 | Material | 36 | AR ft | WET WRAP GLASS | CC | TFInsulation2 |  | Meighan
se131-013 | 0 | COOLANT TUBE FITTING (MODIFIED SWAGELOK) | se131-003 | Fab Part | 36 | 40 | b-600-9-6w | On Site Fab | N/A |  | Kalish
b-600-9-6w |  | SWAGELOK FITTING | se131-013 | Purchased Part |  | 38 | SWAGELOK #B-600-9-6W | CC | TFMisc |  | Meighan
se131-005 | 0 | TF COIL ASSEMBLY GROUNDWRAPPED | se131-003 | Assembly | 18 |  | SEE DETAILS |  | N/A |  | N/A
se131-069 | 0 | TF COIL GROUNDWRAP | se131-005 | Assembly | 18 | AR ft | SGlass 2" Wide .015" Thick Build to 1/8" thick in front Build to 3/8" thick in back | CC | TFInsulation |  | Meighan
se131-035 | 0 | TF COIL ASSEMBLY (NO GROUNDWRAP) | se131-005 | Assembly | 18 |  | SEE DETAILS |  | N/A |  | N/A
se-131-042 |  | G11 Dowel Pin For Lead Spur Area | se131-035 | Part | 90 | 90 | G-11 CR | On Site Fab | N/A |  | Kalish
Dowel Pin Material |  | G11 Dowel Pin For Lead Spur Area | Dowel Pin 1/2 diameter x 3" long | Material | 27ft | 27ft | G-11 CR | CC | TFDowel |  | Kalish
se131-031 | 0 | TF COIL TRANSITION FILLER CENTER | se131-035 | Part | 18 | 20 | G-11 CR | PO | RE403203 |  | Kalish |  | Requisition Approved In Procurment, RFQ on Street
se131-032 | 0 | TF COIL TRANSITION FILLER LEFT/RIGHT | se131-035 | Part | 36 | 38 | G-11 CR | PO | RE403203 |  | Kalish |  | Requisition Approved In Procurment, RFQ on Street
se131-039K | 0 | TURN TO TURN LEAD INSULATION | se131-035 | Material | 18 | AR ft | Kapton: 1" Wide .0035" Thk turn to turn 2 half lap layers | CC | TFInsulation |  | Meighan
se131-039G | 0 | TURN TO TURN LEAD INSULATION | se131-035 | Material | 18 | AR ft | SGlass: 1" Wide .007 Thk turn to turn 3 half lap layers | CC | TFInsulation |  | Meighan
se131-039E | 0 | TURN TO TURN LEAD INSULATION / EPOXY | se131-035 | Material | 18 | AR Gal | Epoxy Resin | CC | TF Epoxy Resin |  | Meighan
se131-041 | 0 | LEAD FILLER | se131-035 | Part | 36 | 38 | G-11 CR | PO | RE403203 |  | Kalish |  | Requisition Approved In Procurment, RFQ on Street
se131-047 | 0 | TF COIL LEAD BLOCK SUPPORT | se131-035 | Part | 18 | 20 | G-11 CR | PO | RE403203 |  | Kalish |  | Requisition Approved In Procurment, RFQ on Street
se131-053 | 0 | LEAD LONG (BENT) Style A | se131-035 | Part | 9 | 10 | se131-088 | On Site Fab | TFlead |  | Kalish
se131-081 | 0 | LEAD LONG (UNBENT) Style A | se131-035 | Material | AR | AR | .75" THICK COPPER C107 PLATE Qty=2 at 100" Long X 36" Wide Qty=1 at 36" Long X 36" Wide | PO | RE403122 |  | Kalish |  | Order Placed |  |  | 2005-10-31 |  | $16K
se131-054 | 0 | LEAD SHORT (BENT) Style A | se131-035 | Part | 9 | 10 | se131-089 | On Site Fab | TFlead |  | Kalish
se131-082 | 0 | LEAD SHORT (UNBENT) Style A | se131-035 | Material | AR | AR | Qty identified for 131-081is total for "RE403122" procurement | PO | RE403122 |  | Kalish |  | Order Placed |  |  | 2005-10-31 |  | $16K
se131-057 | 0 | LEAD LONG (BENT) Style B | se131-035 | Part | 9 | 10 | se131-088 | On Site Fab | TFlead |  | Kalish
se131-088 | 0 | LEAD LONG (UNBENT) Style B | se131-035 | Material | AR | AR | Qty identified for 131-081is total for "RE403122" procurement | PO | RE403122 |  | Kalish |  | Order Placed |  |  | 2005-10-31 |  | $16K
se131-058 | 0 | LEAD SHORT (BENT) Style B | se131-035 | Part | 9 | 10 | se131-089 | On Site Fab | TFlead |  | Kalish
se131-089 | 0 | LEAD SHORT (UNBENT) Style B | se131-035 | Material | AR | AR | Qty identified for 131-081is total for "RE403122" procurement | PO | RE403122 |  | Kalish |  | Order Placed |  |  | 2005-10-31 |  | $16K
se131-078 | 0 | LEAD SUPPORT LOCKING BLOCK TYPE"A" | se131-035 | Part | 18 | 20 | G-11 CR | PO | RE403203 |  | Kalish |  | Requisition Approved In Procurment, RFQ on Street
se131-079 | 0 | LEAD SUPPORT BLOCK LOCKING | se131-035 | Part | 18 | 20 | G-11 CR | PO | RE403203 |  | Kalish |  | Requisition Approved In Procurment, RFQ on Street
se131-084.prt | 0 | LEAD SUPPORT BLOCK LOCKING | se131-035 | Part | 18 | 20 | G-11 CR | PO | RE403203 |  | Kalish |  | Requisition Approved In Procurment, RFQ on Street
se131-087.prt | 0 | SPACER FILLER BLOCK | se131-035 | Part | 18 | 20 | G-11 CR | PO | RE403203 |  | Kalish |  | Requisition Approved In Procurment, RFQ on Street
se131-033 | 0 | Ferrule for braze joints 7/16 OD X 5/16 ID X 1 1/2 LG | se131-035 | Part | 90 | 110 | COPPER TUBE C107? | CC? | TFMisc |  | Kalish
se131-014 | 0 | TF COIL CONDUCTOR | se131-035 | Part | 72 | 77 | NCSX-CSPEC-131-02 | PO | PE005935 | 2005-06-28 | Kalish | NCSX-CSPEC-131-02 | On Order OutoKumpu PE005935 |  |  | 2005-10-21 |  | 89000