## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 12
WBS Title: Vaccum Vessel
Job Number: 1260
Job Title: NBI Port Extensions
Job Manager: Paul Goranson
Description:
This element covers the efforts to designand fabricate the NBI Port Extensions.
Schedule:
See Attached
Approvals:
____________________________________ ___________________
Job Manager Date
____________________________________ ___________________
Responsible Line Manager Date
____________________________________ ___________________
Project Manager Date
____________________________________ ___________________
Engineering Department Head Date

## Table I - Dsn Labor
WBS Number: 12
WBS Title: Vaccum Vessel
Job Number: 1260
Job Title: NBI Port Extensions
Job Manager: Paul Goranson
Description:
This element covers the design of the NBI Port Extensions
Task ID |  | ORNL E/D | ORNL RM | EMEM |  | Basis of Estimate | Category | Amount (Hrs)
Title I an II Design
| Peer Review to Establish Requirements | 80 |  |  |  | Based in recent MDL & NCSX experience | 8 | 80
| Review and Update Assbly Dwgs | 80 |  |  |  | Assume 2 drawings @ 40 hr each - based on recent MDL & NCSX experience | 8 | 80
| Prepare for PDR Neutral Beam Transition Duct | 40 |  |  |  | Based in recent MDL & NCSX experience | 8 | 40
| PDR for NBTD | 0 |  |  |  | Milestone - no resources | 8 | 0
| Resolve PDR Chits | 40 |  |  |  | Based in recent MDL & NCSX experience | 8 | 40
| Review and Update Port Mod Dwg | 40 |  |  |  | Assume 1 drawing @ 40 hr each - based on recent MDL & NCSX experience | 8 | 40
| Review and Update Large Rect Port Dwg | 40 |  |  |  | Assume 1 drawing @ 40 hr each - based on recent MDL & NCSX experience | 8 | 40
| Review and Small Large Rect Port Dwg | 40 |  |  |  | Assume 1 drawing @ 40 hr each - based on recent MDL & NCSX experience | 8 | 40
| Review and Update Weldment Dwgs | 120 |  |  |  | Assume 3 drawings @ 40 hr each - based on recent MDL & NCSX experience | 8 | 120
| Review and Update Misc Det & Cuts Dwgs | 40 |  |  |  | Assume 2 drawings @ 20 hr each - based on recent MDL & NCSX experience | 8 | 40
| Review of Drawings | 40 |  |  |  | Assume 2 people for ~1/2 Weeks - based in recent MDL & NCSX experience | 8 | 40
| Stress analysis | 160 |  |  |  | Based in recent MDL & NCSX experience | 8 | 160
| Prepare for FDR Neutral Beam Transition Duct | 40 |  |  |  | Based in recent MDL & NCSX experience | 8 | 40
| Final Design Review | 0 |  |  |  | Based in recent MDL & NCSX experience | 8 | 0
| Resolve PDR Chits | 40 |  |  |  | Based in recent MDL & NCSX experience | 8 | 40
Subtotal Title I & II Design
|  | 800 | [5 empty] | 800
Title III
Disposition of deviation requests and non-conformances |  | 40 |  |  |  | Based in recent MDL & NCSX experience | 8 | 40
Update of drawings as Needed |  | 80 |  |  |  | Based in recent MDL & NCSX experience | 8 | 80
Procurement coordination |  | 20 |  |  |  | Based in recent MDL & NCSX experience | 8 | 20
Subtotal Title III Design |  | 140 | [5 empty] | 140
[7 empty] | Category | Amount (Hrs) | % of ETC
CATEGORIZATION CODES:
[5 empty] | 1 - National Standards |  | 1 | 0 | 0%
[5 empty] | 2 - Engineering Judgement/Experience |  | 2 | 0 | 0%
[5 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.) |  | 3 | 0 | 0%
[5 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.) |  | 4 | 0 | 0%
[5 empty] | 5 - Prototype Data/Test Results |  | 5 | 0 | 0%
[5 empty] | 6 - Catelogue Price/Vendor Quote |  | 6 | 0 | 0%
[5 empty] | 7 - Placed Contracts |  | 7 | 0 | 0%
[5 empty] | 8 - Actual experience for NCSX Work |  | 8 | 940 | 100%
[5 empty] | 9 - Other |  | 9 | 0 | 0%
[6 empty] | Totals |  | 940 | 100%

## Table II - M&S
WBS Number: 12
WBS Title: Vaccum Vessel
Job Number: 1260
Job Title: NBI Port Extensions
Job Manager: Paul Goranson
Materials and Supplies |  |  | Basis of Estimate | Category | Amount ($)
Costs reflects recent significant increase in Inconel price.
Lateral supports added.
Man Access ports should be removed from the estimates if they were included on other estimates.
This element consists of the port duct, seals, and all cover flanges
weight of shell assembly, with ports | 1400 | lbs
$/lb for fabrication | 51 | $/lb | Includes recent vendor Inconel quotes of $43/lb.
subtotal, fab cost shell | 71400 |  |  | 6 | 71400
Ports
8" o.d. flange, 6" tube | 225 | $/ea | MDC catalog 10
8" o.d. rotatable cover flange | 125 | $/ea | MDC catalog 10
no. of 8" ports | 7 | ea
cost for 8" ports | 2450 |  |  | 6 | 2450
14.5" x 16.5" flange with tube(ss) | 1500 | $/ea | NCSX/MDL experience | 8
blank 14.5" x 16.5" flanges(ss) | 1000 | $/ea | NCSX/MDL experience | 8
no. of 14.5" x 16.5" ports | 2 | ea
cost for 14.5" x 16.5" ports | 5000 |  |  | 8 | 5000
16.5" o.d. flange, 14" tube | 1000 | $/ea | MDC catalog 10
16.5" o.d. rotatable cover flange | 710 | $/ea | MDC catalog 10
no. of 16.5" ports | 2 | ea
cost for 16.5" ports | 3420 |  |  | 6 | 3420
large square flange cover, ss | 4000 |  | NCSX/MDL experience | 8 | 4000
o-ring seals for diamond flange and square flange | 2530 |  | based on actual procurement | 7 | 2530
subtotal, ports | 17400 |  |  |  | 17400
Fabricate and install lateral support | 8000 | $/ea | Ref drawing SE124-073. Estimate based on MDL fabrication of similar parts for QPS.
number of supports | 2 | ea
subtotal for support | 16000 |  |  | 6 | 16000
Total, each nbi port duct extension | 104800 |  |  |  | 104800
no. of nbi duct extensions | 3
total, 3 extensions | 314400
None of the above includes an interface to the cryostat.
|  |  |  | Category | Amount ($) | % of ETC
CATEGORIZATION CODES:
| 1 - National Standards |  |  | 1 |  | 0%
| 2 - Engineering Judgement/Experience |  |  | 2 |  | 0%
| 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.) |  |  | 3 |  | 0%
| 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.) |  |  | 4 |  | 0%
| 5 - Prototype Data/Test Results |  |  | 5 |  | 0%
| 6 - Catelogue Price/Vendor Quote |  |  | 6 | 279810 | 89%
| 7 - Placed Contracts |  |  | 7 | 7590 | 2.414%
| 8 - Actual experience for NCSX Work |  |  | 8 | 27000 | 8.588%
| 9 - Other |  |  | 9 |  | 0%
|  |  | Totals |  | 314400 | 100%

## Table III Fab & Assy
WBS Number: 12
WBS Title: Vaccum Vessel
Job Number: 1260
Job Title: NBI Port Extensions
Job Manager: Paul Goranson
Fabrication and Assembly
Description:
INSTALLED AS PART OF FIELD PERIOD ASSEMBLY

## Table IV - Conting & Risk
WBS Number: 12
WBS Title: Vaccum Vessel
Job Number: 1260
Job Title: NBI Port Extensions
Job Manager: Paul Goranson
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  | X
-10%/+15%
| Design Complexity |  |  | X
Other Comments:
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
[8 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan | Basis of estimate | Low | High | Low | High
1260 | Design is vintage and revisit could result in criteria changes, i.e. diagnostic requirements, number of ports, NB alignment, further design review, etc. |  |  |  | U | Schedule was made more aggressive with early start to assure ageement with design. | Engineering hours to redo models and hold design review. | 200 hrs ORNL EM | 400 hrs ORNL EM | 0 | 0
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is reponsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)

## Table V - Dwg Tree
se122-068 | NB assy
se122-073 | Flange | [5 empty] | NB Assy SE122-068
se122-077 | Port base weldment
se122-078 | Port upper weldment
New port weldment | Port weldment
se122-075 | Port weldment
se122-093 | Cover
se122-184 | Cover | FLANGE SE122-073 |  |  | Port Base Weldment SE122-077 |  | Port Upper Weldment SE122-078 |  |  | PORT WELDMENT SE122-075 |  |  | PORT WELDMENT SE122-094
se122-090 | Port weldment
se122-094 | Port weldment
se122-042 | Block
se122-045 | Bracket
new assy 094 & 093 | Cover Flange weldment |  | PORT WELDMENT NEW PORT WELDMENT |  |  | BRACKET SE122-0045 |  |  | BLOCK SE122-0042 |  |  | BRACKET SE122-0045
|  |  |  | PORT WELDMENT SE122-090 |  |  |  | COVER SE122-184 |  |  | COVER FLANGE WELDMENT SE122-093
COVER SE122-093
COVER FLANGE WELDMENT SE122-094