## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 135
WBS Title: Central Solenoid Support Structure
Job Number: 1353
Job Title: CS Support Structure Procurements
Job Manager: Fred Dahlgren
Description:
This effort covers manufacturing of the MIE central solenoid support structure and integration of the PF1aU&L, with the structure. The pieces of structure are procured via one or more fixed price contracts. This structure is for MIE day-1 operations using the old salvaged PF coils from NSTX. A new structure will be required, if necessary, for operations with the original baseline PF1,2&3 coils.
Schedule:
See Attached
Approvals:
________________________________________________________
Job Manager
_______________________________________________________
Responsible Line Manager
_______________________________________________________
Project Manager
_______________________________________________________
Engineering Department Head

## Table I - Dsn Labor
WBS Number: 135
WBS Title: Central Solenoid Support Structure
Job Number: 1353
Job Title: CS Support Structure Procurements
Job Manager: Fred Dahlgren
Description:
Title I and II Engineering for PF Support Structure and Title III Support of Fabrication Effort.
|  |  | $ |  |  |  |  | HOURS
Task ID |  | Comments | 41MS | 48MS | 37STK | 35TRVL | 31OT | ORNL EM | ORNL DSN | EMEM | EMSM | EMSB | EMTB | EAEM | EASB | EEEM | Basis of Estimate | Category | Amount ($) | Amount (Hrs)
TITLE I AND TITLE II DESIGN COMPLETED
Title III Design
Design PF1a Upper to lower interconnect bus | [14 empty] | 140 |  | Based on prior experience with similar jobs - See Note below. | 4 | 0 | 140
Engr. & analysis of interconnect bus | [13 empty] | 100 |  |  | Based on prior experience with similar jobs - See Note below. | 4 | 0 | 100
[19 empty] | 0 | 0
Vendor Oversight, Inspection |  |  | 2000 | [6 empty] | 40 | [6 empty] | Verbal quote from Construction Manager based on recent experience by shops in fabricating similar parts. | 2 | 2000 | 40
Disposition of deviation requests and non-conformances | [9 empty] | 20 | [6 empty] | Verbal quote from Construction Manager based on recent experience by shops in fabricating similar parts. | 2 | 0 | 20
Coordination of Procurement Actions | [9 empty] | 40 | [6 empty] | Verbal quote from Construction Manager based on recent experience by shops in fabricating similar parts. | 2 | 0 | 40
| Subtotal Title III Design |  | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 100 | 140 | 0 |  |  | 2000 | 340
Note: Estimates are based on verbal and written budgetary quotes from vendors, in-house shop estimates, current catalogue prices where available, and previous experience which includes designing similar magnets, neutral beams, diagnostics, structures, and supports for the following machines - PLT, PDX, S1, MRX, CNT, and TFTR.
[18 empty] | Category | Amount ($) | Amount (Hrs) | % of ETC ($) | % of ETC (Hrs)
CATEGORIZATION CODES:
[8 empty] | 1 - National Standards | [9 empty] | 1 | 0 | 0 | 0% | 0%
[8 empty] | 2 - Engineering Judgement/Experience | [9 empty] | 2 | 2000 | 100 | 100% | 29.41%
[8 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.) | [9 empty] | 3 | 0 | 0 | 0% | 0%
[8 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.) | [9 empty] | 4 | 0 | 240 | 0% | 70.59%
[8 empty] | 5 - Prototype Data/Test Results | [9 empty] | 5 | 0 | 0 | 0% | 0%
[8 empty] | 6 - Catelogue Price/Vendor Quote | [9 empty] | 6 | 0 | 0 | 0% | 0%
[8 empty] | 7 - Placed Contracts | [9 empty] | 7 | 0 | 0 | 0% | 0%
[8 empty] | 8 - Actual experience for NCSX Work | [9 empty] | 8 | 0 | 0 | 0% | 0%
[8 empty] | 9 - Other | [9 empty] | 9 | 0 | 0 | 0% | 0%
[17 empty] | Totals |  | 2000 | 340 | 100% | 100%

## Table II - M&S
WBS Number: 135
WBS Title: Central Solenoid Support Structure
Job Number: 1353
Job Title: CS Support Structure Procurements
Job Manager: Fred Dahlgren
Materials and Subcontracts (M&S) | [7 empty] | Basis of Estimate | Category | Amount ($) | % of ETC ($)
Description:
This effort covers manufacturing of the interim central solenoid support structure and integration of the PF1aU&L, with the structure. The pieces of structure are procured via one or more fixed price contracts. This structure is for MIE day-1 operations using the old salvaged PF coils from NSTX. A new structure will be necessary for operations with the baseline PF1,2&3 coils.
Purchased parts:
upper and lower interface hub | 133488 | see notes below | [5 empty] | Includes Material surcharge as of May'07
brackets to TF structure | 32232 | [6 empty] | Includes Material surcharge as of May'07
spacers and tie rods | 25071.5041 | [6 empty] | Includes Material surcharge as of May'07
subtotal, purchased parts | 190791.5041
outside engr rate = | 130 | $ per hour | [5 empty] | Not used in this estimate - build to print
outside fab rate = | 92 | $ per hour | [5 empty] | Based on SLAC internal rate & web survey
outside inspection/technician rate = | 75 | $ per hour | [5 empty] | Based on Lab shop rate & web survey
Worksheet:
Center solenoid upperr interface hub
Fabrication / parts costs
Item / description |  |  | Value | Unit | Cost $/unit | No. | Cost $
Center hub Weldment |  |  | 92 | lbs | 28 | 1 | 2576 | Based on similar parts fabr. cost | 4 | 2576
Upper solenoid hub weldment Assy |  |  | 236 | lbs | 28 | 1 | 6608 | Based on similar parts fabr. cost | 4 | 6608
Machining of upper hub weldments, 2 setups |  |  | 64 | hrs | 92 | 1 | 5888 | Based on Lab Shop estimate | 2 | 5888
Inspection |  |  | 8 | hrs | 75 | 1 | 600 | Based on Lab Shop estimate | 2 | 600
Insulation and shims between weldments |  |  | 1 | interface | 1500 | 12 | 18000 | Based on similar parts fabr. cost | 4 | 18000
misc bolts and assembly hardware-upper |  |  | 1 | lot | 10000 | 1 | 10000 | Based on B&G quote for Inconel 718 h'dware - See Table V | 6 | 10000
lower solenoid hub weldment Assy |  |  | 236 | lbs | 28 | 1 | 6608 | Based on similar parts fabr. cost | 4 | 6608
Machining of lower hub weldments, 2 setups |  |  | 64 | hrs | 92 | 6 | 35328 | Based on Lab Shop estimate | 2 | 35328
Inspection |  |  | 8 | hrs | 75 | 6 | 3600 | Based on Lab Shop estimate | 2 | 3600
Insulation and shims between castings |  |  | 1 | interface | 1500 | 12 | 18000 | Based on similar parts fabr. cost | 4 | 18000
misc bolts and assembly hardware-lower |  |  | 1 | lot | 10000 | 1 | 10000 | Based on B&G quote for Inconel 718 h'dware - See Table V | 6 | 10000
Package & Shipping | [6 empty] | 5000 | Based on past experience on similar projects | 4 | 5000
|  |  |  | subtotal Integrated TF structure fab./matl |  |  | 117208 |  |  | 117208
Material Surcharges & delta: 316L - Inconel 601 |  |  | 564 | lbs | 20 |  | 11280 | Based on Huntington verbal Quote for Inconel 601 | 6 | 11280
[5 empty] | Adjusted Total |  | 133488
Brackets to TF structure
Fabrication / parts costs
Item / description |  |  | Value | Unit | Cost $/unit | No. | Cost $
Upper tie plate to TF coil structure |  |  | 500 | lbs | 8 | 1 | 4000 | Based on similar parts fabr. Cost | 4 | 4000
Machining of upper and lower crown segment casting |  |  | 40 | hrs | 92 | 2 | 7360 | Based on Lab Shop estimate | 2 | 7360
lower brackets to TF coil structure |  |  | 30 | lbs | 8 | 6 | 1440 | Based on similar parts fabr. Cost | 4 | 1440
machining of lower brackets |  |  | 16 | hrs | 92 | 6 | 8832 | Based on Lab Shop estimate | 2 | 8832
|  |  |  | subtotal brackets to TF coil fab./matl |  |  | 21632
Material Surcharges & delta: 316L - Inconel 601 |  |  | 530 | lbs | 20 |  | 10600 | Based on Huntington verbal Quote for Inconel 601 | 6 | 10600
[5 empty] | Adjusted Total |  | 32232
Center Solenoid assembly hardware
Item / Description |  |  | Value | Unit | Cost $/unit | No Units | Cost $
1"OD, 96" long Tie Rods |  |  | 90.4779 | lbs | 25 | 6 | 2261.9467 | Based on cost of threaded rod | 7 | 2261.9467
G-10 separation discs & misc. |  |  | 150 | lbs | 20 | 7 | 21000 | Based on similar parts fabr. Cost | 4 | 21000 |  |  | 2 | 61608 | 32.29%
|  |  |  | subtotal of assembly hardware |  |  | 23261.9467 | [5 empty] | 4 | 83232 | 43.62%
Material Surcharges & delta: 316L - Inconel 601 |  |  | 90.4779 |  | 20 |  | 1809.5574 | Based on Huntington verbal Quote for Inconel 601 | 6 | 1809.5574 |  |  | 6 | 43689.5574 | 22.9%
[6 empty] | Total: | 25071.5041 | [5 empty] | 7 | 2261.9467 | 1.186%
190791.5041
Center Solenoid PF1a Upper to Lower interconnect Bus Fabrication / parts costs | [7 empty] | These estimates are based on prior job experience and quotes received for Inconel hardware from B&G and Solon Washers - Braze alloy-Mcmaster-Carr
Item / description |  |  |  | lbs/ft. | $/lb | No. of Units
Copper OFHC extrusion 3/4"sq. w/.38dia hole |  |  | 10 | 1.75 | 4.25 | 2 | 74.375 |  | 6 | 74.375
CTD-112 (or equiv.) Epoxy/Glass pre-preg. Insulation 1" rolls |  |  |  | per roll | 98 | 4 | 392 |  | 6 | 392
Bend return & supply bus segments |  |  | 12 | hrs | 81 | 2 | 1944 |  | 4 | 1944
Wrap & cure bus segments |  |  | 40 | hrs | 81 | 1 | 3240 |  | 4 | 3240
Machine & assemble (braze) LN2 fittings |  |  | 8 | hrs | 81 | 4 | 2592 |  | 4 | 2592
Cut & bend Cu Jumpers |  |  | 12 | hrs | 81 | 2 | 1944 |  | 4 | 1944
Silver-braze & clean-up jumper lead-stem mtg. plates |  |  | 8 | hrs | 81 | 8 | 5184 |  | 4 | 5184
Cut & machine jumper/lead-stem mtg. plates |  |  | 16 | hrs | 81 | 8 | 10368 |  | 4 | 10368
Cut & Machine G11 clamps |  |  | 12 | hrs | 81 | 3 | 2916 |  | 4 | 2916
Hardware B'ville washers -Inconel718 |  |  |  |  | 38.5 | 64 | 2464 |  | 6 | 2464
Hardware Inconel hex nuts 1/2-13 |  |  |  |  | 32 | 32 | 1024 |  | 6 | 1024
Hardware Inconel 718 hex bolts 1/2-13 x 2" |  |  |  |  | 42 | 32 | 1344 |  | 6 | 1344
Silver brush plate all bolted bus surfaces |  |  |  |  | 20 | 8 | 160 |  | 4 | 160 |  |  | 4 | 5408.205 | 16.02%
Handy-Harman Silver braze BAg-1 easy-flo-45 filler alloy |  |  | 5 | oz. | 109.83 | 1 | 109.83 |  | 6 | 109.83 |  |  | 6 | 28348 | 83.98%
|  |  |  | subtotal of assembly hardware |  |  | 33756.205
TOTAL JOB 1353 | [6 empty] | 224547.7091
[5 empty] | JOB 1353 TOTALS: |  | 190791.5041
Notes:
Labor for parts assembly should be in Job 1352
Labor for installation in Machine Assembly Job (7501/7503) | [8 empty] | Category | Amount ($) | % of ETC ($)
CATEGORIZATION CODES:
[7 empty] | 1 - National Standards |  | 1 | 0 | 0%
[7 empty] | 2 - Engineering Judgement/Experience |  | 2 | 61608 | 27.44%
[7 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.) |  | 3 | 0 | 0%
[7 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.) |  | 4 | 111580 | 49.69%
[7 empty] | 5 - Prototype Data/Test Results |  | 5 | 0 | 0%
[7 empty] | 6 - Catelogue Price/Vendor Quote |  | 6 | 49097.7624 | 21.87%
[7 empty] | 7 - Placed Contracts |  | 7 | 2261.9467 | 1.007%
[7 empty] | 8 - Actual Costs/Schedule for NCSX Work |  | 8 |  | 0%
[7 empty] | 9 - Other |  | 9 |  | 0%
[9 empty] | Totals | 224547.7091 | 100%

## Table III - FabAssy & Instl
WBS Number: 135
WBS Title: Central Solenoid Support Structure
Job Number: 1353
Job Title: CS Support Structure Procurements
Job Manager: Fred Dahlgren
In-house Fabrication and Assembly and Installation
Description: N/A Assembly covered in job 1352
Worksheets
Labor for parts assembly should be in Job 1352
Labor for installation should be in Machine Assembly Task

## Table IV - Conting & Risk
WBS Number: 135
WBS Title: Central Solenoid Support Structure
Job Number: 1353
Job Title: CS Support Structure Procurements
Job Manager: Fred Dahlgren
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity | X |  |  |  | Design complete
-5%/+10%
| Design Complexity |  |  | X |  | Simple weldments
Other uncertainties not considered:
(1) Material cost escalation higher than prediceted. Perhaps 10% increase in material costs, but alternate materials are possible. (10% increase in mat'l $ relatively small, ~1400lbs x $3 = 4.2k$ ∂)
(2) Fabrication delays due to material availability. Huntington has quoted 13 weeks ARO. Alternate vendors possible, but very low consequence since could be assembled as part of last subassembly.
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Risks
[8 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan | Basis of estimate | Low | High | Low | High
NONE
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is reponsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)

## Table V - Basis of Estimate
WBS Number: 135
WBS Title: Central Solenoid Support Structure
Job Number: 1353
Job Title: CS Support Structure Procurements
Job Manager: Fred Dahlgren
Basis of Estimate
Material Escalation Information
B&G Inconel Hardware Quote
Inconel 625 Quote