## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 133
WBS Title: External Trim Coils
Job Number: 1354
Job Title: Trim Coil Design and Procurement
Job Manager: Mike Kalish
Description:
The external trim coil set is intended to provide low poloidal mode number (m=2,3) field error correction. These will be conventionally wound coils in a windowpane configuration. They are provided at the top, bottom, and outside perimeter of the Coil Support Structure (WBS 151) primarily to reduce low poloidal mode number (m) resonant errors that may result from manufacturing or assembly errors in the modular coil geometry.
Schedule:
See Attached
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Responsible Line Manager
____________________________________________________________
Project Manager
____________________________________________________________
Engineering Department Head

## Table I - Dsn Labor
WBS Number: 133
WBS Title: External Trim Coils
Job Number: 1354
Job Title: Trim Coil Design and Procurement
Job Manager: Mike Kalish
Description:
Title I and II Engineering for Coils and Title III Support of Fabrication Effort.
|  | FY07$K |  |  | $ |  | HOURS |  |  |  |  | Hours
Task ID |  | 41MS | 48MS | 37STK | 35TRVL | 31OT | ORNL EM | ORNL DSN | EMEM | EMSM | EMSB | EMTB | EAEM | EADM | Basis of Estimate | Category | Amount ($) | Amount (Hrs)
TRIM COILS and TRIM COIL SUPPORTS
Title I & II Design
| Complete Coil SRD | [11 empty] | 24 |  | Based on NCSX actual experience for PF & TF coils | 8 | 0 | 24
| Preliminary Trim Coil Concept and Requirements | [11 empty] | 120 |  | Based on NCSX actual experience for trim coils to date. | 8 | 0 | 120
| Analysis | [11 empty] | 160 |  | Based on NCSX actual experience for PF & TF coils | 8 | 0 | 160
| Layout / Design Coils & Supports | [11 empty] | 80 | 312 | Based on Estimate from Designer who is 50% through with scope of work | 8 | 0 | 392
| Modifications to allow for mid-plane coils | [11 empty] | 40 | 80 | Engineering judgement based on layouts of upper Trim coils | 2 | 0 | 120
| Prepare for PDR | [11 empty] | 40 | 24 | Based on NCSX actual experience for PF & TF coils | 8 | 0 | 64
| PDR | [11 empty] | 8 | 4 | Based on NCSX actual experience for PF & TF coils | 8 | 0 | 12
| Prepare Procurement Coil Spec, Four Coils | [11 empty] | 40 | 8 | Based on NCSX actual experience for PF & TF coils | 8 | 0 | 48
| Detailed Drawings Coils and Supports | [11 empty] | 68.4 | 228 | 38 Drawings avg. 6 hrs/ drawing, 30% eng support | 8 | 0 | 296.4
| Assembly Drawings and Parts Lists | [11 empty] | 36 | 120 | Based on Experience with PF TF Coil Support job, and 30% eng support | 8 | 0 | 156
| Prepare for FDR | [11 empty] | 40 | 24 | Based on NCSX actual experience for PF & TF coils | 8 | 0 | 64
| FDR | [11 empty] | 8 | 4 | Based on NCSX actual experience for PF & TF coils | 8 | 0 | 12
| Disposition FDR Chits | [11 empty] | 24 |  | Based on NCSX actual experience for PF & TF coils | 8 | 0 | 24
Title III Design | [15 empty] | 8 | 0 | 0
| Coil Procurement Support | [11 empty] | 80 | 16 | Past experience in procuring simple coils | 4 | 0 | 96
| Fabrication Support | [11 empty] | 288 | 80 | 9months, 1day per week, +drafting support for vendor coordination and ECNs - Minimal oversight due to simple conventional coil design, based on experience supporting manufacture of TF Coils | 4 | 0 | 368
| Bracket Procurement Support | [11 empty] | 80 |  | 4 visits to a vendor + on going support | 4 | 0 | 80
| Material Procurement Support | [11 empty] | 40 |  | procurement of fasteners and material for in house fabrications | 4 | 0 | 40
| In house Fabrication Support | [11 empty] | 24 |  | Engineering judgement based on discussions with shop | 2 | 0 | 24
| Fabrication Support Travel |  |  |  | 10000 | [7 empty] | 48 |  | Two trips to west coast assuming vendor is in Ca (worst case assumption) | 4 | 10000 | 48
| Incoming Inspection | [10 empty] | 144 | 72 |  | For electrical testing and handling of Coil | 8 | 0 | 216
Sub-Totals |  |  |  |  | 10000 | [6 empty] | 144 | 1320.4 | 900 |  |  | 10000 | 2364.4
SUPPORT BRACKETS - DELETED - INCORPORATED ABOVE
Trim Coil Structure, Materials & Fabrication
Order Materials
Trim Coil Structure, Design & Analysis
Structure Detail
Trim Coil Structure, Part Procurement and Fabrication
[17 empty] | Category | Amount ($) | Amount (Hrs) | % of ETC ($) | % of ETC (Hrs)
CATEGORIZATION CODES:
[13 empty] | 1 - National Standards |  |  |  | 1 | 0 | 0 | 0% | 0%
[13 empty] | 2 - Engineering Judgement/Experience |  |  |  | 2 | 0 | 144 | 0% | 6.09%
[13 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.) |  |  |  | 3 | 0 | 0 | 0% | 0%
[13 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.) |  |  |  | 4 | 10000 | 632 | 100% | 26.73%
[13 empty] | 5 - Prototype Data/Test Results |  |  |  | 5 | 0 | 0 | 0% | 0%
[13 empty] | 6 - Catelogue Price/Vendor Quote |  |  |  | 6 | 0 | 0 | 0% | 0%
[13 empty] | 7 - Placed Contracts |  |  |  | 7 | 0 | 0 | 0% | 0%
[13 empty] | 8 - Actual experience for NCSX Work |  |  |  | 8 | 0 | 1588.4 | 0% | 67.18%
[13 empty] | 9 - Other |  |  |  | 9 | 0 | 0 | 0% | 0%
[15 empty] | Totals |  |  | 10000 | 2364.4 | 100% | 100%

## Table II - M&S
WBS Number: 133
WBS Title: External Trim Coils
Job Number: 1354
Job Title: Trim Coil Design and Procurement
Job Manager: Mike Kalish
Materials and Subcontracts (M&S) | [7 empty] | Basis of Estimate | Category | Amount ($)
|  | Trim1 | Trim2 | Trim3 | Trim4
Winding geometry
radius | m | 0.52194 | 0.52194 | 0.52194 | 0.52194
bundle dr | mm | 28.8 | 28.8 | 28.8 | 28.8
bundle dz | mm | 28.8 | 28.8 | 28.8 | 28.8
no. of turns |  | 4 | 4 | 4 | 4
packing fraction |  | 0.75 | 0.75 | 0.75 | 0.75
length per turn | m | 4.6175 | 3.0775 | 3.0775 | 3.0775
total length of cu per coil | m | 18.47 | 12.31 | 12.31 | 12.31
turn height | mm | 13 | 13 | 13 | 13
turn width | mm | 13 | 13 | 13 | 13
coolant hole dia. | mm | 0 | 0 | 0 | 0
corner radii | mm | 1.016 | 1.016 | 1.016 | 1.016
conductor area | mm^2 | 168.1139 | 168.1139 | 168.1139 | 168.1139
calculated coil Cu wt. | kg | 26.6414 | 17.7562 | 17.7562 | 17.7562
Cu density | 8.58e-06
Trim Coil Material Estimate
|  | Trim1 | Trim2 | Trim3 | Trim4 | Total # Coils
II. Materials M&S
Number of Coils |  | 6 | 12 | 6 | 24 | 48
Conductor With Insulation Cost Per LB |  | 11.65 | 11.65 | 11.65 | 11.65 |  |  | Vendor quote
Conductor With Insulation Cost Per Coil | $ | 684.3722 | 456.1246 | 456.1246 | 456.1246
Epoxy volume reqd. (15% void fraction) | l | 0.57449 | 0.38289 | 0.38289 | 0.38289
Epoxy cost/liter | $/l | 79.2 | 79.2 | 79.2 | 79.2 |  |  | $300 per gallon as paid for Modular coils. Vendor under Contract
Epoxy cost per coil | $ | 45.4997 | 30.3249 | 30.3249 | 30.3249
Material Costs Epoxy all Coils |  | 272.9981 | 363.8989 | 181.9494 | 727.7978
Material Costs Conductor with Insulation all Coils |  | 1637.9884 | 4366.7866 | 1091.6967 | 17467.1464
Material Costs Total |  | 1910.9865 | 4730.6855 | 1273.6461 | 18194.9442 | 26110.2623 |  |  | 6 | 26110.2623
Everson Budgetary Estimate | [6 empty] | Contingency
Total Material Cost All Trim Coils | [5 empty] | 26110.2623
Cost from Everson Budgetary Estimate out of Plane |  | 8450 | 7575 | 7575 | 7575
Adjusted Cost for Planar Coils |  | 8450 | 7575 | 6438.75 | 6438.75
Total Cost for Fixtures |  | 40000 | 30000 | 30000 | 30000 | 130000
Recurring Costs for N Coils no materials |  | 50700 | 90900 | 38632.5 | 154530 | 334762.5
Total Cost For N Coils with Materials |  | 92610.9865 | 125630.6855 | 69906.1461 | 202724.9442
Total Cost All Coils | [5 empty] | 490872.7623
Everson Budgetary Estimate (adjusted for uncertainty)
Total Material Cost All Trim Coils | [5 empty] | 39165.3934 | 50% | Vendor quote adjusted for experieince with this vendor
Manufacturing Cost from Everson Budgetary Estimate |  | 8450 | 7575 | 6438.75 | 6438.75 |  |  |  | `
Total Cost for Fixtures |  | 40000 | 30000 | 30000 | 30000 | 195000 | 50% | Vendor quote adjusted for experieince with this vendor
Recurring Costs for N Coils no materials |  | 50700 | 90900 | 38632.5 | 154530 | 502143.75 | 50% | Vendor quote adjusted for experieince with this vendor
Total Cost For N Coils with Materials |  | 92610.9865 | 125630.6855 | 69906.1461 | 202724.9442
Total Cost All Coils | [5 empty] | 736309.1434 |  |  | 6 | 736309.1434
Support Brackets
$ per lb for plate (316 SS $8/lb AL $5/lb, $40/lb inconel) | 40 | [6 empty] | Vendor quotes for similar material
Weight LB per meter | 16.56
$$ per coil for brackets material per coil |  | 3058.632 | 2038.536 | 2038.536 | 2038.536
Cost of Material for Brackets Total |  | 18351.792 | 24462.432 | 12231.216 | 48924.864
Fabrication Cost per meter | 340 | [6 empty] | Engineering judgement
Cost Bracket Fabrication per coil |  | 1569.95 | 1046.35 | 1046.35 | 1046.35
Cost Bracket Fabrication Total |  | 9419.7 | 12556.2 | 6278.1 | 25112.4
Cost Bracket Fabrication with Materials Total |  | 27771.492 | 37018.632 | 18509.316 | 74037.264 | 157336.704 | 50% |  | 6 | 236005.056
Cost for Clamps per Coil |  | 1157.1455 | 771.2215 | 771.2215 | 771.2215
Hardware Cost per 3/8 Bolt (Inconnel) |  | 18 | 18 | 18 | 18
Cost for Bolts and Studs per coil |  | 498.69 | 332.37 | 332.37 | 332.37 |  |  | Vendor quotes for similar material
Cost for all Bolts and Studs & Brackets Total |  | 9935.013 | 13243.098 | 6621.549 | 26486.196 | 56285.856 | 50% |  | 6 | 84428.784
Cost for Mockups of Each Coil |  | 5700 | 3800 | 3800 | 3800 | 17100 | 50% | Engineering judgement | 2 | 25650
Cost For Installation Fixtures |  | 3000 | 3000 | 3000 | 3000 | 12000 | 50% | Engineering judgement | 2 | 18000
Cost for Hardware | [5 empty] | 242722.56
Cost for Support Brackets adjusted for uncertainty | [5 empty] | 364083.84 |  |  |  | 364083.84
Installation Man Hour Estimate (Budgeted in job 1815 station 5 assembly)
| 1849 | 144 |  | 1993 |  | 161433 |  |  | 81
632 | 1934 | 192 | 940 | 3698 |  | 628660 |  |  | 170
#REF!
Weeks for two technicians per Field Period |  | #REF! |  |  | Cost Total M&S | #REF!
Weeks for four technicians per Field Period |  | #REF!
[5 empty] | Total Hours | #REF!
[5 empty] | Technicican Rate | 85
[5 empty] | Eng Rate | 160
[5 empty] | Cost Man-hours | #REF!
[5 empty] | Total Cost | #REF!
[9 empty] | Category | Amount ($) | % of ETC ($)
CATEGORIZATION CODES:
[6 empty] | 1 - National Standards |  |  | 1 | 0 | 0%
[6 empty] | 2 - Engineering Judgement/Experience |  |  | 2 | 43650 | 3.967%
[6 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.) |  |  | 3 | 0 | 0%
[6 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.) |  |  | 4 | 0 | 0%
[6 empty] | 5 - Prototype Data/Test Results |  |  | 5 | 0 | 0%
[6 empty] | 6 - Catelogue Price/Vendor Quote |  |  | 6 | 1056742.9834 | 96.03%
[6 empty] | 7 - Placed Contracts |  |  | 7 | 0 | 0%
[6 empty] | 8 - Actual experience for NCSX Work |  |  | 8 | 0 | 0%
[6 empty] | 9 - Other |  |  | 9 | 0 | 0%
[8 empty] | Totals |  | 1100392.9834 | 100%

## Table III - FabAssy & Instl
WBS Number: 133
WBS Title: External Trim Coils
Job Number: 1354
Job Title: Trim Coil Design and Procurement
Job Manager: Mike Kalish
In-house Fabrication and Assembly and Installation
Description: Incl in M&S Table II

## Table IV - Conting & Risk
WBS Number: 133
WBS Title: External Trim Coils
Job Number: 1354
Job Title: Trim Coil Design and Procurement
Job Manager: Mike Kalish
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  | X |  |  | Early stages of determining trim coil requirements - but costs small (probably under $100K)
-10%/+15%
| Design Complexity |  |  | X |  | Present requirement is for a round two turn coil. Simple coil design.
Other comments: Although price of Cu variable (see Job 1352 discussion), so little Cu needed for these coils, no considered a significant uncertainty
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
[8 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan | Basis of estimate | Low | High | Low | High
1354 | Trim coils still in very conceptual stage of design. Likely will be required to "baseline" cost and schedule prior to even reaching a preliminary design stage. |  |  |  | VL | Expediting design effort, but unlikely to have significantly more information prior to "baseline" => apply appropriate contingency to reflect this. | Based on simple coil design for LTX | 1000 | 3000 | 0 | 1 | RR#40
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is reponsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)