## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 161
WBS Title: LN2 Distribution System
Job Number: 1601-161
Job Title: LN2 Distribution System
Job Manager: Paul Goranson
Description:
This effort covers all Title I, II, and III engineering for the LN2 distribution system inside the cryostat, which includes all the necessary manifolding and connections to interface with the ex-cryostat LN2 supply system. This system will be fabricated in-house by PPPL. All Title III engr associated with installation is included in WBS 7.
Schedule:
See Attached
Approvals:
________________________________________________________
Job Manager
________________________________________________________
Responsible Line Manager
________________________________________________________
Project Manager
________________________________________________________
Engineering Department Head

## Table I - Dsn Labor
WBS Number: 161
WBS Title: LN2 Distribution System
Job Number: 1601-161
Job Title: LN2 Distribution System
Job Manager: Paul Goranson
Description:
This effort covers all R&D, Title I, II, and III engineering for the LN2 distribution system inside the cryostat, which includes all the necessary manifolding and connections to interface with the ex-cryostat LN2 supply system. This system will be fabricated in-house by PPPL. All Title III engr associated with installation is included in WBS 7.
HOURS
Task ID | Multiplier | Unit | Number of Units | Hours | ORNL EM | ORNL DSN | ORNL RM | EMEM | EMSM | EMSB | EMTB | EAEM | EASB | Basis of Estimate | Category | Amount (Hrs)
Title I an II Design
Pro-E models (avg) | 4 | hrs/model | 40 | 160 | 160 | [8 empty] | See Worksheet below - based on recent NCSX experience | 8 | 160
assy dwgs | 8 | hrs/dwg | 11 | 88 | 88 | [8 empty] | See Worksheet below - based on recent NCSX experience | 8 | 88
Detail drawings | 4 | hrs/dwg | 6 | 24 | 24 | [8 empty] | See Worksheet below - based on recent NCSX experience | 8 | 24
installation dwg | 8 | hrs/dwg | 11 | 88 | 88 | [8 empty] | See Worksheet below - based on recent NCSX experience | 8 | 88
cooling schematic | 20 | hrs/dwg | 1 | 20 | 20 | [8 empty] | See Worksheet below - based on recent NCSX experience | 8 | 20
electrical schematic | 0 | hrs/dwg | 1 | 0 | 0 | [8 empty] | See Worksheet below - based on recent NCSX experience | 8 | 0
I&C schematic | 20 | hrs/dwg | 1 | 20 | 20 | [8 empty] | See Worksheet below - based on recent NCSX experience | 8 | 20
stress analysis | 40 | hrs/calc | 1 | 40 | 40 | [8 empty] | See Worksheet below - based on recent NCSX experience | 8 | 40
thermal analysis | 40 | hrs/calc | 1 | 40 | 40 | [8 empty] | See Worksheet below - based on recent NCSX experience | 8 | 40
special analysis (electromagnetics) | 160 | hrs/calc | 0 | 0 | 0 | [8 empty] | See Worksheet below - based on recent NCSX experience | 8 | 0
fab specifications | 160 | hrs/spec | 2 | 320 | 320 | [8 empty] | See Worksheet below - based on recent NCSX experience | 8 | 320
preliminary and final design reviews | 80 | hrs/rev | 2 | 160 | 160 | [8 empty] | See Worksheet below - based on recent NCSX experience | 8 | 160
Resolve PDR Comments | 40 | hrs/PDR | 1 | 40 | 40 | [8 empty] | Based on recent NCSX experience | 8 | 40
meetings/reporting/presentations | 10% | % of tot hrs |  | 100 | 100 | [8 empty] | See Worksheet below - based on recent NCSX experience | 8 | 100
Subtotal Title I & II Design |  |  |  | 1100 | 1100 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
R&D Activities
R&D design time to build mounts(clamp, spider), lead terminations. |  |  |  | 40 | 40 | [8 empty] | Based on recent NCSX experience at MDL | 8 | 40
Title III
Disposition of deviation requests and non-conformances | 1 | hrs per | 38 | 38 |  |  |  | 38 | 0 | 0 | 0 | 0 | 0 | Based on recent experience on NCSX | 8 | 38
As-built drawings | 2 | # dwgs | 29 | 58 |  | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Based on recent experience on NCSX | 8 | 58
Procurement coordination |  |  |  | 80 |  | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | Based on recent experience on NCSX | 8 | 80
Subtotal Title III Design |  |  |  | 176 | 0 | 58 | 0 | 78 | 40 | 0 | 0 | 0 | 0
Total |  |  |  | 1316 | [11 empty] | 1316
Notes and worksheets
LN2 distribution system
|  |  | total | Vessel Torus, | Port Extensions | NBI duct |  |  | Manifolds | Headers
Pro-E models |  |  | 33 | 10 | 13 | 2 |  |  | 6 | 2 |  |  |  | models for each type of tube, manifold, and header
assy dwgs |  |  | 5 | 1 | 1 | 1 |  |  | 1 | 1
Detail drawings |  |  | 6 | 0 | 0 | 0 |  |  | 4 | 2 |  |  |  | drawings of each manifold and header
installation dwg |  |  | 4 | 1 | 1 | 1 |  |  | 1 |  |  |  |  | on drawing per type of part
cooling schematic |  |  | 0
electrical schematic |  |  | 0
I&C schematic |  |  | 0
stress analysis |  |  | 1
thermal analysis |  |  | 1 | 1 | [9 empty] | one analysis for all cooling lines
special analysis |  |  | 0
procurement specifications |  |  | 1 | [10 empty] | one procurement spec for the tubing, piping and fittings
preliminary and final design reviews |  |  | 1 | [10 empty] | one review for all the plumbing
meetings/reporting/presentations |  |  | 15%
Flow Control System |  |  | total
Pro-E models |  |  | 6 | [10 empty] | elements added to piping system
assy dwgs |  |  | 6
Detail drawings |  |  | 0
installation dwg |  |  | 6
cooling schematic |  |  | 1 | [10 empty] | block flow diagram
electrical schematic |  |  | 1 | [10 empty] | actuator electrical schematic, if applicable
I&C schematic |  |  | 0
stress analysis |  |  | 0
thermal analysis |  |  | 0
special analysis |  |  | 0
procurement specifications |  |  | 1 | [10 empty] | one procurement specification for all flow control elements
preliminary and final design reviews |  |  | 0 | [10 empty] | reviews covered under WBS 191
meetings/reporting/presentations |  |  | 10%
Local I&C
Pro-E models |  |  | 1
assy dwgs |  |  | 0
Detail drawings |  |  | 0
installation dwg |  |  | 1
cooling schematic |  |  | 0
electrical schematic |  |  | 0
I&C schematic |  |  | 1
stress analysis |  |  | 0
thermal analysis |  |  | 0
special analysis |  |  | 0
procurement specifications |  |  | 0
preliminary and final design reviews |  |  | 1
meetings/reporting/presentations |  |  | 10%
Notes:
1. LN2 distribution system instrumentation consists of a single thermocouple placed on each return header inside cryostat
2. There will be a single supply and return header for each field period which supplies the TF coils and the upper and lower PF coils
3. Reviews and procurement specs for T/C are covered as part of WBS 171
[15 empty] | Category | Amount (Hrs) | % of ETC
CATEGORIZATION CODES:
[12 empty] | 1 - National Standards |  |  | 1 | 0 | 0% | 0 | #DIV/0!
[12 empty] | 2 - Engineering Judgement/Experience |  |  | 2 | 0 | 0% | 0 | #DIV/0!
[12 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.) |  |  | 3 | 0 | 0% | 0 | #DIV/0!
[12 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.) |  |  | 4 | 0 | 0% | 0 | #DIV/0!
[12 empty] | 5 - Prototype Data/Test Results |  |  | 5 | 0 | 0% | 0 | #DIV/0!
[12 empty] | 6 - Catelogue Price/Vendor Quote |  |  | 6 | 0 | 0% | 0 | #DIV/0!
[12 empty] | 7 - Placed Contracts |  |  | 7 | 0 | 0% | 0 | #DIV/0!
[12 empty] | 8 - Actual experience for NCSX Work |  |  | 8 | 1316 | 100% | 0 | #DIV/0!
[12 empty] | 9 - Other |  |  | 9 | 0 | 0% | 0 | #DIV/0!
[14 empty] | Totals |  | 1316 | 100% | 0 | #DIV/0!

## Table II - M&S
WBS Number: 161
WBS Title: LN2 Distribution System
Job Number: 1601-161
Job Title: LN2 Distribution System
Job Manager: Paul Goranson
Materials and Supplies
Description: | [10 empty] | Basis of Estimate | Category | Amount ($)
This effort covers procurement of materials for the LN2 distribution system by fixed price subcontract.
Assumptions:
outside engr rate = | 120 | $ per hour | [8 empty] | Based on recent experiences on NCSX and UT work being done at MDL
outside fab rate = | 60 | $ per hour | [8 empty] | Based on recent experiences on NCSX and UT work being done at MDL
outside inspection/technician rate = | 80 | $ per hour | [8 empty] | Based on recent experiences on NCSX and UT work being done at MDL
MDL labor | 80 | $per hour
Purchased parts:
coolant line pigtails from coils to manifolds | 19800 | see notes below | [8 empty] | See Worksheet Below | 8 | 19800
Insulating Jumper hoses | 4320 | [9 empty] | See Worksheet Below | 8 | 4320
Manifolds for cooling lines | 6912.3718 | [9 empty] | See Worksheet Below | 8 | 6912.3718
valves | 9000 | see notes below | [8 empty] | See Worksheet Below | 8 | 9000
orifices & other hardware | 17200 | [9 empty] | See Worksheet Below | 8 | 17200
Thermocouples | 0 | included in job 1408 for the modular coil fabrication | [9 empty] | 8 | 0
R&D material and labor from below | 18000 | [10 empty] | 8 | 18000
subtotal, purchased parts | 75232.3718 | [11 empty] | 75232.3718
Worksheet:
coolant line pigtails from coils to manifolds
Average length of pigtail | 3 | ft
| Total | TF | Modular | PF1 | PF2 | PF3 | PF4 | PF5 | PF6 | Trim
No. of coils | 60 | 18 | 18 | 2 | 2 | 2 | 2 | 2 | 2 | 12
circuits per coil at header |  | 1 | 8 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1
total circuits | 180 | 18 | 144 | 1 | 1 | 1 | 1 | 1 | 1 | 12
Total number of pigtails | 360 | supply and return per circuit
Cost per pigtail, with fittings | 55
Total cost of pigtails | 19800 |  | 3660 | [7 empty] | Based on recent purchases for NCSX and UT at MDL
Number of MC coil insulating break jumper hoses and end fittings | 144
cost per jumper | 30 | [9 empty] | Based on recent purchases for NCSX and UT at MDL
total cost of jumpers | 4320
total cost of all lines
Manifolds for cooling lines
Assume 1 pair of 1.5 inch manifolds for each field period, one above and one below the midplane inside the PF5 coil
Each manifold will have 1/3 of the required cooling connections plus 25% spare
The manifolds will connect via vertical pipes to the supply system below the cryostat
avg toroidal perimeter of field period | 15.8041 | ft
avg vertical height of connection lines | 9 | ft
no of header pairs | 3
cost of tubing | 15 | per foot, 316 SSt | [8 empty] | Based on recent purchases for NCSX and UT at MDL
cost per field period | 2232.3718
total number of coolant connections, all headers | 900
cost per connection | 5
cost of nipples for all manifolds | 4500
welding consumables | 200 | total
no. connections for supply piping | 6 | 2 connections per manifold
cost per connection | 30
cost for supply piping connections | 180
total matl cost for manifolds | 6912.3718
Flow control hardware
no. of circuits | 36
Valves | 250 | ea | [8 empty] | Based on recent purchases for NCSX and UT at MDL
no.of valves | 36 | one for each pf, trim, and tf coil circuit at manifold
Total cost for valves | 9000
flow control orifice at manifold | 50 | ea | [8 empty] | Based on recent purchases for NCSX and UT at MDL
no of orifice units | 144 | one for each MC coil circuit
Total cost for orifice | 7200
Other misc items | 10000 | [9 empty] | Based on recent purchases for NCSX and UT at MDL
Thermocouples
Number | 0 | ea | [8 empty] | Included in Job 1431
Thermocouple cost each, with connector | 68 | $ each | [8 empty] | Based on recent purchases for NCSX and UT at MDL
total for thermocouples | 0
R&D Activities
Technicians labor to build mounts(clamp, spider). Build lead terminations. | 200 | hrs | [8 empty] | Based on experiences for NCSX and UT at MDL
Material to built prototypes of clamps, terminations, and spiders, including 20 feet of cable. | 2000 | [9 empty] | Based on recent purchases for NCSX and UT at MDL
18000
[12 empty] | Category | Amount ($) | % of ETC
CATEGORIZATION CODES:
[8 empty] | 1 - National Standards |  |  |  | 1 | 0 | 0%
[8 empty] | 2 - Engineering Judgement/Experience |  |  |  | 2 | 0 | 0%
[8 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.) |  |  |  | 3 | 0 | 0%
[8 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.) |  |  |  | 4 | 0 | 0%
[8 empty] | 5 - Prototype Data/Test Results |  |  |  | 5 | 0 | 0%
[8 empty] | 6 - Catelogue Price/Vendor Quote |  |  |  | 6 | 0 | 0%
[8 empty] | 7 - Placed Contracts |  |  |  | 7 | 0 | 0%
[8 empty] | 8 - Actual experience for NCSX Work |  |  |  | 8 | 75232.3718 | 100%
[8 empty] | 9 - Other |  |  |  | 9 | 0 | 0%
[11 empty] | Totals |  | 75232.3718 | 100%

## Table III Fab & Assy
WBS Number: 161
WBS Title: LN2 Distribution System
Job Number: 1601-161
Job Title: LN2 Distribution System
Job Manager: Paul Goranson
Fabrication and Assembly
Description:
This effort covers all the fabrication of the LN2 system inside the cryostat including headers. | [5 empty] | Labor category
[6 empty] | total fraction | EAEM |  | EASM, EMSM |  | EMTB |  | EADM |  | Basis of Estimate | Category | Amount (Hrs)
| multiplier | unit | no. | hours |  |  | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
Fab operations summary
| 652.5 | hrs/lot | 1 | 652.5 |  | 1 | 0 | 0 | 0.2 | 130.5 | 0.8 | 522 | 0 | 0
| 0 | hrs/line | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | hrs / coil | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
subtotal | 652.5 |  |  | 652.5 |  |  |  | 0 |  | 130.5 |  | 522 |  | 0 | See Worksheet Below | 8 | 652.5
[6 empty] | total fraction | EAEM |  | EASM, EMSM |  | EMTB |  | EADM
Assembly operations summary | [6 empty] | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs | None - Part of Machine Assembly Jobs
| 0 | hr/lot | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | hr/lot | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | hr/coil | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | hours | 1 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
subtotal | 0 |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0
Worksheets
coolant line pigtails from coils to manifolds
Average length of pigtail | 3 | ft
| Total | TF | Modular | PF1 | PF2 | PF3 | PF4 | PF5 | PF6 | Trim
No. of coils | 60 | 18 | 18 | 2 | 2 | 2 | 2 | 2 | 2 | 12
circuits per coil at header |  | 1 | 8 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1
total circuits | 180 | 18 | 144 | 1 | 1 | 1 | 1 | 1 | 1 | 12
Total number of pigtails | 360 | supply and return per circuit
Manifolds for cooling lines
Assume 1 pair of 1.5 inch manifolds for each field period, one above and one below the midplane inside the PF5 coil
Each manifold will have 1/3 of the required cooling connections plus 25% spare
The manifolds will connect via vertical pipes to the supply system below the cryostat
avg toroidal perimeter of field period | 15.8041 | ft
avg vertical height of connection lines | 9 | ft
no of header pairs | 3
cost of tubing | 15 | per foot, 316 SSt | [12 empty] | Based on recent purchases for NCSX and UT at MDL | 8
cost per field period | 2232.3718
total number of coolant connections, all headers | 900
hours to weld each connection | 0.5 | hr per connection | [12 empty] | Based on recent experience at MDL | 8
shifts to form manifold tube | 0.5 | per manifold pair | [12 empty] | Based on recent experience at MDL | 8
crew size for forming | 2 | [13 empty] | Based on recent experience at MDL | 8
hours to cut vertical pipes | 2 | hrs per pipe | [12 empty] | Based on recent experience at MDL | 8
hours to weld vertical pipes to header | 2 | hrs per pipe | [12 empty] | Based on recent experience at MDL | 8
total shifts for manifolds | 65.25 | [13 empty] | Based on recent experience at MDL | 8
tech hours for manifolds | 522 | hours | [12 empty] | Based on recent experience at MDL | 8
technical oversight, inspection | 130.5 | hrs | [12 empty] | Based on recent experience at MDL | 8
total hours for manifolds | 652.5 | hrs | [13 empty] | Category | Amount (Hrs) | % of ETC
CATEGORIZATION CODES:
[12 empty] | 1 - National Standards |  |  |  | 1 | 0 | 0%
[12 empty] | 2 - Engineering Judgement/Experience |  |  |  | 2 | 0 | 0%
[12 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.) |  |  |  | 3 | 0 | 0%
[12 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.) |  |  |  | 4 | 0 | 0%
[12 empty] | 5 - Prototype Data/Test Results |  |  |  | 5 | 0 | 0%
[12 empty] | 6 - Catelogue Price/Vendor Quote |  |  |  | 6 | 0 | 0%
[12 empty] | 7 - Placed Contracts |  |  |  | 7 | 0 | 0%
[12 empty] | 8 - Actual experience for NCSX Work |  |  |  | 8 | 652.5 | 100%
[12 empty] | 9 - Other |  |  |  | 9 | 0 | 0%
[15 empty] | Totals |  | 652.5 | 100%

## Table IV - Conting & Risk
WBS Number: 161
WBS Title: LN2 Distribution System
Job Number: 1601-161
Job Title: LN2 Distribution System
Job Manager: Paul Goranson
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  | X |  |  | Design well established based on previous devices
-10%/+15%
| Design Complexity |  |  | X |  | Standard Components
Other Comments:
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
[8 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan | Basis of estimate | Low | High | Low | High
NONE
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is reponsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)