## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 162
WBS Title: Coil Electrical Leads
Job Number: 1601-162
Job Title: Coil Electrical Leads
Job Manager: Paul Goranson
Description:
This WBS element consists of the design and fabrication of the coil electrical leads inside the cryostat which then connect the coils to the power supply bus or cables outside the cryostat.
Schedule:
See Attached
Approvals:
_________________________________________________________
Job Manager
_________________________________________________________
Responsible Line Manager
_________________________________________________________
Project Manager
_________________________________________________________
Engineering Department Head

## Table I - Dsn Labor
WBS Number: 162
WBS Title: Coil Electrical Leads
Job Number: 1601-162
Job Title: Coil Electrical Leads
Job Manager: Paul Goranson
Description:
This effort covers all R&D, Title I, II, and III engineering design of the coil electrical leads inside the cryostat connecting the coils to the power supply bus or cables outside the cryostat.
HOURS
Task ID |  | Multiplier | Unit | Number of Units | Hours | ORNL EM | ORNL DSN | ORNOL RM | EMEM | EMSM | EMSB | EMTB | EAEM | EASM | EEEM | EESM |  | EESB | EETB | ECEM | ECSB | ECTB | Basis of Estimate | Category | Amount (Hrs)
Title I an II Design
Pro-E models (avg) |  | 8 | hrs/model | 50 | 400 | 400 | [16 empty] | See Worksheet below - based on recent NCSX experience | 8 | 400
assy dwgs |  | 16 | hrs/dwg | 15 | 240 | 240 | [16 empty] | See Worksheet below - based on recent NCSX experience | 8 | 240
Detail drawings |  | 8 | hrs/dwg | 40 | 320 | 320 | [16 empty] | See Worksheet below - based on recent NCSX experience | 8 | 320
installation dwg |  | 16 | hrs/dwg | 29 | 464 | 464 | [16 empty] | See Worksheet below - based on recent NCSX experience | 8 | 464
cooling schematic |  | 0 | hrs/dwg | 1 | 0 | 0 | [16 empty] | See Worksheet below - based on recent NCSX experience | 8 | 0
electrical schematic |  | 8 | hrs/dwg | 14 | 112 | 112 | [16 empty] | See Worksheet below - based on recent NCSX experience | 8 | 112
I&C schematic |  | 8 | hrs/dwg | 0 | 0 | 0 | [16 empty] | See Worksheet below - based on recent NCSX experience | 8 | 0
stress analysis |  | 0 | hrs/calc | 0 | 0 | 0 | [16 empty] | See Worksheet below - based on recent NCSX experience | 8 | 0
thermal analysis |  | 24 | hrs/calc | 1 | 24 | 24 | [16 empty] | See Worksheet below - based on recent NCSX experience | 8 | 24
special analysis (electromagnetics) |  | 40 | hrs/calc | 1 | 40 | 40 | [16 empty] | See Worksheet below - based on recent NCSX experience | 8 | 40
Procuremnt Specifications |  | 40 | hrs/spec | 1 | 40 | 40 | [16 empty] | See Worksheet below - based on recent NCSX experience | 8 | 40
preliminary and final design reviews |  | 40 | hrs/rev | 1 | 40 | 40 | [16 empty] | See Worksheet below - based on recent NCSX experience | 8 | 40
Resolve PDR comments |  | 40 | hrs/pdr | 1 | 40 | 40 | [16 empty] | Based on ecent NCSX experience | 8 | 40
meetings/reporting/presentations |  | 10% | % of tot hrs |  | 172 | 172 | [16 empty] | See Worksheet below - based on recent NCSX experience | 8 | 172
Subtotal Title I & II Design | [5 empty] | 1892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
R&D Activities
R&D Pressure drop simulation w pessurized LN2 and valve. Design of test unit. |  |  |  |  | 40 | 40 | [16 empty] | Based on ecent NCSX experience | 8 | 40
Title III
vendor inspection & oversight |  | 8 | hrs per | 1 | 8 | 8 | [16 empty] | Based on recent experience on NCSX | 8 | 8
Disposition of deviation requests and non-conformances |  | 0.5 | hrs/wk | 20 | 10 | 10 | [16 empty] | Based on recent experience on NCSX | 8 | 10
In-House fab/assy oversight & inspection |  | 2 | hrs/wk | 4 | 8 | 8 | [7 empty] | 8 | [8 empty] | Based on recent experience on NCSX | 8 | 16
As-built drawings |  | 1 | hrs/dwg | 84 | 84 | 84 | [16 empty] | Based on recent experience on NCSX | 8 | 84
Subtotal Title III Design | [5 empty] | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Total | [5 empty] | 2042 | [7 empty] | 8 | [10 empty] | 2050
Notes and worksheets
PF Coil leads
|  | coils at 10, 70, 130, 190, 250, 310 degrees | coils at 30, 90, 150, 210, 270, 330 degrees | coils at 50, 110, 170, 230, 290, 350 degrees | PF1-2 | PF3 | PF4 | PF5 | PF6 | coils at 0, 120, 240, degrees, top and bottom | coils at 60, 180, 300 degrees Top and bottom | Outer perimeter coils | coil 1 at 10, 70, 130, 190, 250, 310 degrees | coil 2 at 30, 90, 150, 210, 270, 330 degrees | coil 3 at 50, 110, 170, 230, 290, 350 degrees | thermal transition box | total
Pro-E models |  | 6 | 6 | 6 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 2 | 6 | 6 | 6 | 1 | 50 | [5 empty] | leads modeled to create drawings, reserve space in assembly
assy dwgs |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 15 | [5 empty] | one assembly for each circuit
Detail drawings |  | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 40 | [5 empty] | drawings for lead length, mounting details
installation dwg |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 29 | [5 empty] | one installation dwg for each cable
cooling schematic | [16 empty] | 1 | [5 empty] | one cooling schematic for all leads
electrical schematic |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 14 | [5 empty] | one schematic for each circuit
I&C schematic | [22 empty] | part of WBS 163
stress analysis
thermal analysis | [16 empty] | 1 | [5 empty] | one analysis to check temp rise, cooling
special analysis | [16 empty] | 1 | [5 empty] | one analysis for field error determination
procurement specifications | [16 empty] | 1 | [5 empty] | one specification for leads, all carry the same current, will have the same terminations, only the lengths are different
preliminary and final design reviews | [16 empty] | 1 | [5 empty] | one review for all coil leads
meetings/reporting/presentations | [16 empty] | 10%
Note:
Labor estimates based on recent NCSX experience
[24 empty] | Category | Amount (Hrs) | % of ETC
CATEGORIZATION CODES:
[21 empty] | 1 - National Standards |  |  | 1 | 0 | 0%
[21 empty] | 2 - Engineering Judgement/Experience |  |  | 2 | 0 | 0%
[21 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.) |  |  | 3 | 0 | 0%
[21 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.) |  |  | 4 | 0 | 0%
[21 empty] | 5 - Prototype Data/Test Results |  |  | 5 | 0 | 0%
[21 empty] | 6 - Catelogue Price/Vendor Quote |  |  | 6 | 0 | 0%
[21 empty] | 7 - Placed Contracts |  |  | 7 | 0 | 0%
[21 empty] | 8 - Actual experience for NCSX Work |  |  | 8 | 2050 | 100%
[21 empty] | 9 - Other |  |  | 9 | 0 | 0%
[23 empty] | Totals |  | 2050 | 100%

## Table II - M&S
WBS Number: 162
WBS Title: Coil Electrical Leads
Job Number: 1601-162
Job Title: Coil Electrical Leads
Job Manager: Paul Goranson
Description:
This effort covers all coil leads that connect the coil terminals to the buswork at the boundary of the cryostat. The lead cables are all the same except for length, and will be procured from a qualified vendor. All installation will be performed as part of WBS 7. The leads exit the cryostat boundary through a thermal transition box that brings leads up to room temperature (or, at a minimum, above the dew point) before exiting to prevent frost build up. | [6 empty] | Basis of Estimate | Category | Amount ($)
Assumptions:
outside engr rate = | 120 | $ per hour
outside fab rate = | 60 | $ per hour
outside inspection/technician rate = | 80 | $ per hour
Purchased parts:
set of cables | 32552.3893 | [5 empty] | Based on recent experiences on NCSX and UT work being done at MDL
misc attachment hardware | 16162.2216 | @10$/ft |  |  |  |  | Based on recent experiences on NCSX and UT work being done at MDL
thermal transition box material | 0 | [5 empty] | Based on recent experiences on NCSX and UT work being done at MDL
subtotal, purchased parts | 48714.611
[8 empty] | 8 | 48714.611
Lead bundles consist of six, 250 MCM cable with teflon sleeve. |  | Lead ends are cooled by bleed liquid nitrogen supplied by the coil coolant header (WBS 161)
Leads connect from coil terminals to buswork at bottom of machine.
Each coil is connected separately except PF1 and PF2, which are connected in series within the central solenoid assembly
Purchased materials for in-house fabrication and sub-assembly
None required | 0
subtotal purchased materials | 0
Worksheet, TF Coils:
Lead cost, TF Coils
Terminations,assembly | 400 | ea |  |  |  |  | Based on recent experiences on NCSX and UT work being done at MDL
Cable with teflon insulation, reinforced teflon outer jacket | 50 | per foot |  |  |  |  | Based on recent experiences on NCSX and UT work being done at MDL
Total number of cables | 18
Total length of cables | 176.25
Total cable cost | 16012.5
[8 empty] | 8 | 16012.5
Geometry
radius of vertical runs | 12 | ft
height of upper terminals | 11 | ft
height of lower terminals | 7 | ft
Lengths | terminal radius | height from floor | cable length
| (m) | (ft) | (ft)
coils at 10, 130, 250 degrees | 3 | 11 | 11
coils at 70, 190, 310 degrees | 3 | 7 | 7
coils at 30, 150, 270 degrees | 3 | 11 | 11
coils at 90, 210, 330 degrees | 3 | 7 | 7
coils at 50, 170, 290 degrees | 3 | 11 | 11
coils at 110, 230, 350 degrees | 3 | 7 | 7
Subtotals |  |  | 47
Total length | 141 | ft
25% extra for bends, offsets | 35.25
Total procured length | 176.25 | ft
Avg length per cable | 9.7917 | ft
Worksheet, PF Coils:
Lead cost, PF Coils
Terminations,assembly | 400 | ea |  |  |  |  | Based on recent experiences on NCSX and UT work being done at MDL
Cable with teflon insulation, reinforced teflon outer jacket | 50 | per foot |  |  |  |  | Based on recent experiences on NCSX and UT work being done at MDL
Total number of cables | 10
Total length of cables | 192.5828
Total cable cost | 13629.141 | [6 empty] | 8 | 13629.141
Geometry
radius of vertical runs | 10 | ft
height of upper runs | 12 | ft
height of connection to buswork | 0 | ft
Lengths | terminal radius | height from midplane | top length | bottom length
| (m) | (m) | (ft) | (ft)
TF Coils
PF1, PF2, connected in series as assy | 0 | 1.3 | 29.7349 | 10
PF3 | 0 | 1.3 | 29.7349 | 10
PF4 | 0.69 | 1.6 | 26.4869 | 7.7362
PF5 | 2.23 | 1.5 | 21.7625 | 2.6837
PF6 | 2.8 | 1 | 21.5328 | 0.81367
External Trim Coils
Mod Coils
Subtotals |  |  | 129.2521 | 31.2336
Total length | 160.4857 | ft
20% extra for bends, toroidal offsets | 32.0971
Total procured length | 192.5828 | ft
Avg length per cable | 19.2583 | ft
Worksheet, Mod coils:
Lead cost for modular coils
Terminations,assembly | 400 | ea |  |  |  |  | Based on recent experiences on NCSX and UT work being done at MDL
Cable with teflon insulation, reinforced teflon outer jacket | 50 | per foot |  |  |  |  | Based on recent experiences on NCSX and UT work being done at MDL
Total number of cables | 36
Total length of cables | 345
Total cable cost | 31650 | [6 empty] | 8 | 31650
Geometry
radius of vertical runs | 12 | ft
height of upper terminals | 10 | ft
height of lower terminals | 8 | ft
Lengths | terminal radius | height from floor | cable length
| (m) | (ft) | (ft)
coils at 10, 130, 250 degrees | 3 | 10 | 10
coils at 70, 190, 310 degrees | 3 | 8 | 8
coils at 30, 150, 270 degrees | 3 | 10 | 10
coils at 90, 210, 330 degrees | 3 | 8 | 8
coils at 50, 170, 290 degrees | 3 | 10 | 10
coils at 110, 230, 350 degrees | 3 | 8 | 8
Subtotals |  |  | 46
Total length | 138 | ft
25% extra for bends, offsets | 34.5
Total procured length | 345 | ft
Avg length per cable | 9.5833 | ft
Worksheet, lead thermal transition box
66 leads, 11 to a box | size
| (in) | number reqd | cost ea | total
sheet material, foil backed insul. foam | 1 x 48 x 96 | 5 | 25 | 125 |  |  | Based on recent experiences on NCSX and UT work being done at MDL
end seals | 1" tube x 6" | 22 | 20 | 440 |  |  | Based on recent experiences on NCSX and UT work being done at MDL
cryo epoxy |  | .5 lb | 28.3333 | 14.1667 |  |  | Based on recent experiences on NCSX and UT work being done at MDL
misc mount hardware, ss base frame |  |  |  | 500 |  |  | Based on recent experiences on NCSX and UT work being done at MDL
foam caulk | 16 oz | 4 | 4 | 16 |  |  | Based on recent experiences on NCSX and UT work being done at MDL
acryic sheet window | 3/8" x 12 x 24 | 1 | 62 | 62 |  |  | Based on recent experiences on NCSX and UT work being done at MDL
assembly | 40 hr each= | 40 | 82 | 3280 |  |  | Based on recent experiences on NCSX and UT work being done at MDL
|  |  |  | 4437.1667 | each
number required for test floor |  |  |  | 6
|  |  | Total | 26623 |  |  |  | 8 | 26623
Worksheet, trim coils
Lead bundles consist of six, #2 cable with teflon sleeve.
Leads connect from coil terminals to buswork at bottom of machine.
Purchased materials for in-house fabrication and sub-assembly
None required | 0
subtotal purchased materials | 0
Worksheet, Error field correction (Trim) coil leads:
Full machine utilizes 12 coils.
Lead cost, Error field coils
Terminations,assembly | 150 | ea |  |  |  |  | Based on recent experiences on NCSX and UT work being done at MDL
Cable with teflon insulation, reinforced teflon outer jacket | 10 | per foot including brackets and sleeving. |  |  |  |  | Based on recent experiences on NCSX and UT work being done at MDL
Total number of cables | 24
Total length of cables | 902.3893 | ft
Subtoal cable cost | 9023.8934
Total cable cost | 30623.8934 | [6 empty] | 8 | 30623.8934
Geometry
horizontal radial runs | 6 | ft
height of upper terminals | 12 | ft
height of lower terminals | 6 | ft
Lengths | radial length from terminals | av height from floor | av cable length
| ft | (ft) | (ft)
coils top and bottom | 6 | 9 | 15
Subtotals
length | 15 | ft
Routing along cryostat floor | 18.8496
25% extra for bends, offsets | 3.75 | ft
total length to floor | 37.5996 | ft
SubTotal | 37.5996 | ft
R&D Activities
R&D Pressure drop simulation w pessurized LN2 and valve. Fabricate and operate test unit. |  | 200 | hrs | two technicians part time |  |  | Based on recent experiences on NCSX and UT work being done at MDL
Purchase hose, pump, piping, and valve.
Liquid nitrogen supply. |  | 7000 |  |  |  |  | Based on recent experiences on NCSX and UT work being done at MDL
| subtotal | 7600 | [5 empty] | 8 | 7600
174853.1454
[8 empty] | Category | Amount ($) | % of ETC
CATEGORIZATION CODES:
[6 empty] | 1 - National Standards |  | 1 | 0 | 0%
[6 empty] | 2 - Engineering Judgement/Experience |  | 2 | 0 | 0%
[6 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.) |  | 3 | 0 | 0%
[6 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.) |  | 4 | 0 | 0%
[6 empty] | 5 - Prototype Data/Test Results |  | 5 | 0 | 0%
[6 empty] | 6 - Catelogue Price/Vendor Quote |  | 6 | 0 | 0%
[6 empty] | 7 - Placed Contracts |  | 7 | 0 | 0%
[6 empty] | 8 - Actual experience for NCSX Work |  | 8 | 174853.1454 | 100%
[6 empty] | 9 - Other |  | 9 | 0 | 0%
[7 empty] | Totals |  | 174853.1454 | 100%

## Table III Fab & Assy
WBS Number: 162
WBS Title: Coil Electrical Leads
Job Number: 1601-162
Job Title: Coil Electrical Leads
Job Manager: Paul Goranson
Fabrication and Assembly
No local fab or assembly is anticipated for the Coil leads. Installation is part of WBS 7.

## Table IV - Conting & Risk
WBS Number: 162
WBS Title: Coil Electrical Leads
Job Number: 1601-162
Job Title: Coil Electrical Leads
Job Manager: Paul Goranson
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) |  | Comments/Other Considerations
| Design Maturity |  | X |  |  | Design well established based on previous devices
-5%/+10%
| Design Complexity |  |  | X |  | Standard Components
Other Comments:
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
[9 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  | Basis of estimate | Low | High | Low | High
162 | Design of cables not firmly established, satisfying field error requirements could require more costly solutions and longer lead time. |  |  |  | L | Moving preliminary design into FY08 to give more lead time. |  | Increased time for Engineering study of alternate configurations. | 200 hrs ORNL EM but reduce M&S by 10% | 400 hrs ORNL EM but reduce M&S by 10% | 0 | 4 months
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is reponsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)