## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 61
WBS Title: Water Cooling Systems
Job Number: 6101
Job Title: Water Cooling Systems
Job Manager: Larry Dudek
Description:
This WBS element includes all the effort required to add cooling loops to the existing C-site (CS) and HVAC Water Systems as required for NCSX subsystems.
Schedule:
See Attached
Approvals:
_________________________________________________________
Job Manager
_________________________________________________________
Responsible Line Manager
________________________________________________________
Project Manager
_______________________________________________________
Engineering Department Head

## Table I - Dsn Labor
WBS Number: 61
WBS Title: Water Cooling Systems
Job Number: 6101
Job Title: Water Cooling Systems
Job Manager: Larry Dudek
|  | $ |  |  |  |  | HOURS
TASK DESCRIPTION |  | 41MS | 48MS | 37STK | 35TRVL | 31OT | ORNLEM | ORNLDSN | EMEM | EMSM | EMSB | EMTB | EAEM | EASB | EEEM | EESM | EESB | EETB | Basis of Estimae | Category | Amount ($) | Amount (Hrs)
Design - Field Run
| Requiements Definition | [7 empty] | 20 |  |  |  |  | 20 |  |  |  |  | Based on engineering judgement from experience on NSTX | 4 | 0 | 40
| Conceptual Definition | [7 empty] | 20 | [9 empty] | Based on engineering judgement from experience on NSTX | 4 | 0 | 20
| Layout Drawings | [7 empty] | 10 |  |  |  |  | 20 |  |  |  |  | Based on engineering judgement from experience on NSTX | 4 | 0 | 30
| Final Design & Detail Drawings | [7 empty] | 40 |  |  |  |  | 160 |  |  |  |  | Based on engineering judgement from experience on NSTX | 4 | 0 | 200
Procrurement & Fabrication/Installation
| Procurements | 22970 | [16 empty] | See Basis of Estimate Details Below - Based on Means Plumbing 2002 => escalated to 2007 | 6 | 22970 | 0
| Installation | [10 empty] | 265 | [6 empty] | Based on engineering judgement from experience on NSTX | 4 | 0 | 265
| Supervision | [7 empty] | 50 |  | 30 | [7 empty] | Based on engineering judgement from experience on NSTX | 4 | 0 | 80
PTP Testing
| Test | [7 empty] | 8 |  |  | 40 | [6 empty] | Based on engineering judgement from experience on NSTX | 4 | 0 | 48
| TOTALS | 22970 | 0 | 0 | 0 | 0 | 0 | 0 | 148 | 0 | 30 | 305 | 0 | 200 | 0 | 0 | 0 | 0 |  |  | 22970 | 683
[20 empty] | Category | Amount ($) | Amount (Hrs) | % of ETC ($) | % of ETC (Hrs)
CATEGORIZATION CODES:
[16 empty] | 1 - National Standards |  |  |  | 1 | 0 | 0 | 0% | 0%
[16 empty] | 2 - Engineering Judgement/Experience |  |  |  | 2 | 0 | 0 | 0% | 0%
[16 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.) |  |  |  | 3 | 0 | 0 | 0% | 0%
[16 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.) |  |  |  | 4 | 0 | 683 | 0% | 100%
[16 empty] | 5 - Prototype Data/Test Results |  |  |  | 5 | 0 | 0 | 0% | 0%
[16 empty] | 6 - Catelogue Price/Vendor Quote |  |  |  | 6 | 22970 | 0 | 100% | 0%
[16 empty] | 7 - Placed Contracts |  |  |  | 7 | 0 | 0 | 0% | 0%
[16 empty] | 8 - Actual experience for NCSX Work |  |  |  | 8 | 0 | 0 | 0% | 0%
[16 empty] | 9 - Other |  |  |  | 9 | 0 | 0 | 0% | 0%
Basis of Estimate Details
[19 empty] | Totals |  | 22970 | 683 | 100% | 100%
Missing backup details on "adders" - please provide

## Table II - M&S
WBS Number: 61
WBS Title: Water Cooling Systems
Job Number: 6101
Job Title: Water Cooling Systems
Job Manager: Larry Dudek
Materials and Subcontracts (M&S) | Basis of Estimate
M&S in Table I

## Table III - FabAssy & Instl
WBS Number: 61
WBS Title: Water Cooling Systems
Job Number: 6101
Job Title: Water Cooling Systems
Job Manager: Larry Dudek
In-house Fabrication and Assembly and Installation
Fabrication & Installation in Table I

## Table IV - Conting & Risk
WBS Number: 61
WBS Title: Water Cooling Systems
Job Number: 6101
Job Title: Water Cooling Systems
Job Manager: Larry Dudek
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  | X |  |  | Design not complicated, but still in a conceptual stage.
-10%/15%
| Design Complexity |  |  | X |  | Standard piping -- off-the-shelf components
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
[8 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan | Basis of estimate | Low | High | Low | High
NONE
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is reponsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)