## Sheet1
| Contingency Analysis | Base (BCWS) | Base To Date (11/30/06) | Base To Go | Budgeted Contingency |  | Total |  | Contingency Analysis | Base (BCWS) | Base To Date (11/30/06) | Base To Go | Budgeted Contingency |  | Total
WBS Level II | Job Level | $k | $k | $k | $k | % | $k |  |  | $k | $k | $k | $k | % | $k
dcma | dcma | 75 | 75 | 0 | 0 |  | 75 | WBS
12 | Job: 1201 - Vacuum Vessel Prelim Dsn-**CLOSED** | 424.42 | 424 | 0 | 0 |  | 424 | 12 | Vacuum Vessel | 9921.76 | 9623.5 | 360.7373 | 52.7211 | 14.61% | 10036.9584
12 | Job: 1202 - Vacuum Vessel R&D | 1769.81 | 1771 | 0 | 0 |  | 1771 | 13 | Conventional Coils | 5380.92 | 2957 | 2375.7078 | 240.926 | 10.14% | 5573.6337
12 | Job: 1203 - Vacuum Vessel Final Dsn-**CLOSED** | 1217.81 | 1220 | 0 | 0 |  | 1220 | 14 | Modular Coils | 34639.15 | 30133 | 6981.9133 | 667.3342 | 9.558% | 37782.2475
12 | Job: 1204-VV Sys Procurements (non VVSA)-DUDEK | 685.08 | 378 | 360.7373 | 52.7211 | 14.61% | 791.4584 | 15 | Coil Structures | 1350.19 | 143 | 1234.6223 | 291.0779 | 23.58% | 1668.7002
12 | Job: 1206 - VV Field Weld Joint R&D-**CLOSED** | 15.64 | 16 | 0 | 0 |  | 16 | 16 | Coil Services | 1148.33 | 3 | 1143.74 | 167.1556 | 14.61% | 1313.8956
12 | Job: 1250 - Vacuum Vessel Fabrication--**CLOSED** | 5809 | 5814.5 | 0 | 0 |  | 5814.5 | 17 | Cryostat & Base | 1214.09 | 417 | 787.9663 | 141.523 | 17.96% | 1346.4893
13 | Job: 1301 - TF Design-KALISH**CLOSED** | 970.57 | 970 | 0 | 0 |  | 970 | 18 | Field Period Assembly | 6579.99 | 2699 | 3999.8988 | 1475.8024 | 36.9% | 8174.7012
13 | Job: 1302 - PF Design -KALISH | 131.97 | 19 | 139.744 | 20.4233 | 14.61% | 179.1674 | 19 | Stellarator Core Mgt. / Integration | 2621 | 2007.5 | 576.7641 | 33.7172 | 5.846% | 2617.9814
13 | Job: 1303 -Central Solenoid Support Dsn-DAHLGREN | 106.35 | 138 | 0 | 0 |  | 138 | 1 | Stellarator Core Systems | 62855.43 | 47983 | 17461.3499 | 3070.2575 | 17.58% | 68514.6073
13 | Job: 1350 TF Coil Fab Prep-CHRZANOWSKI**CLOSED** | 547.01 | 536 | 0 | 0 |  | 536 | 2 | Fueling & Vacuum | 486.33 | 348 | 138.2 | 12.1186 | 8.769% | 498.3186
13 | Job: 1351 - TF Coil Fabr Supplies-KALISH | 470 | 453 | 6.5447 | 0.3826 | 5.846% | 459.9273 | 3 | Diagnsotics | 936.07 | 808 | 196.799 | 18.9755 | 9.642% | 1023.7745
13 | Job: 1352 - PF Coil Procurement-KALISH | 787.95 | 0 | 787.25 | 138.0663 | 17.54% | 925.3163 | 4 | Power Systems | 3183.01 | 714.3 | 1830 | 142.7138 | 7.799% | 2687.0138
13 | Job: 1353 - CS Structure Procurement-DAHLGREN | 122.61 | 0 | 122.51 | 17.9046 | 14.61% | 140.4146 | 5 | Central I&C / Data Aq. | 803.4 | 33 | 753.1 | 66.0386 | 8.769% | 852.1386
13 | Job: 1354 - Trim Coil Design &Procurement-KALISH | 106.07 | 0 | 106 | 23.2376 | 21.92% | 129.2376 | 6 | Facility Systems | 601.23 | 24 | 576 | 141.1088 | 24.5% | 741.1088
13 | Job: 1355 - WBS 13 I&C Proc & | 93.42 | 0 | 93 | 8.1551 | 8.769% | 101.1551 | 7 | Test Cell Prep / Machine Assembly | 3831.18 | 953 | 2875.0559 | 513.8833 | 17.87% | 4341.9392
13 | Job: 1361 - TF Fabrication-KALISH | 2044.97 | 841 | 1120.659 | 32.7565 | 2.923% | 1994.4155 | 8 | Project Mgt. & Integration | 13002.51 | 9405.5 | 3237.8103 | 1024.2887 | 31.64% | 13667.599
14 | Job: 1401 - Mod Coil Prel.Dsn**CLOSED** | 304.05 | 304 | 0 | 0 |  | 304 |  | DCMA | 75 | 75 |  |  |  | 75
14 | Job: 1402 - Mod.Coil Analyses**CLOSED** | 239.12 | 239 | 0 | 0 |  | 239 |  |  | 85774.16 | 60343.8 | 27068.3151 | 4989.3847 | 18.43% | 92401.4998
14 | Job: 1403 - Modular Coil Final Design-WILLIAMSON | 3310.02 | 3309.5 | 0 | 0 |  | 3309.5
14 | Job: 1404-MCWF R&D & 1st Prod Casting**CLOSED** | 2544 | 2553.5 | 0 | 0 |  | 2553.5
14 | Job: 1405-Mod Coil Winding R&D Prep-**CLOSED** | 168.07 | 168 | 0 | 0 |  | 168
14 | Job: 1406 - Mod. Coil Winding | 2262.96 | 2263 | 0 | 0 |  | 2263
14 | Job: 1407 -Mod Coil Winding Facility-**CLOSED** | 2570.78 | 2569.5 | 0 | 0 |  | 2569.5
14 | Job: 1408-Mod Coil Winding Supplies-CHRZANOWSKI | 1952.63 | 1957 | 227.51 | 16.6251 | 7.307% | 2201.1351
14 | Job: 1409 - Coil Test Stand-GETTELFINGER*CLOSED* | 825.96 | 833 | 0 | 0 |  | 833
14 | Job: 1410 MC Twisted Racetrack Fabr-**CLOSED** | 1049.9 | 1050 | 0 | 0 |  | 1050
14 | Job: 1411-MCWF Fabrication S005242-HEITZENROEDER | 9844.47 | 8719.5 | 1175.0464 | 34.3462 | 2.923% | 9928.8926
14 | Job: 1412 - Complete Winding Facilities-*CLOSED* | 541.02 | 541 | 0 | 0 |  | 541
14 | Job: 1413 -MCWF Fracture Analysis-**CLOSED** | 27.84 | 28 | 0 | 0 |  | 28
14 | Job: 1414 Coil Testing-Gettelfinger**CLOSED** | 674.68 | 639 | 0 | 0 |  | 639
14 | Job: 1415 Dim Cntrl Testing-RAFTOPOLOUS*CLOSED** | 23.83 | 24 | 0 | 0 |  | 24
14 | Job: 1416-Mod Coil Type A&B Final Dsn-WILLIAMSON | 685.89 | 642 | 227.3872 | 16.6161 | 7.307% | 886.0034
14 | Job: 1419-Winding Fac. Mods-CHRZANOWSKI*CLOSED* | 55.21 | 46 | 0 | 0 |  | 46
14 | Job: 1421-Mod Coil Interface Design-WILLIAMSON | 379.91 | 120 | 487.7344 | 71.2815 | 14.61% | 679.0159
14 | Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 698.9 |  | 698.9 | 204.286 | 29.23% | 903.186
14 | Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 5994 | 4045 | 3810.9626 | 222.7862 | 5.846% | 8078.7488
| Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI | 422.86 | 45 | 344.3878 | 100.6634 | 29.23% | 490.0512
14 | Job: 1460 3rd Winding Fixture-CHRZANOWSKI | 63.05 | 37 | 9.9849 | 0.72964 | 7.307% | 47.7146
15 | Job: 1501 - Coil Structures Design- DAHLGREN | 217.92 | 143 | 93.1523 | 40.8421 | 43.84% | 276.9944
15 | Job: 1550 - Coil Structures Procurement -DAHLGREN | 1132.27 |  | 1141.47 | 250.2358 | 21.92% | 1391.7058
16 | Job: 1601 - Coil Services Design-WILLIAMSON | 1148.33 | 3 | 1143.74 | 167.1556 | 14.61% | 1313.8956
17 | Job: 1701-Cryost&Base Sprt Strct Dsn-GETTLEFINGER | 605.72 | 417 | 180.3863 | 52.7263 | 29.23% | 650.1126
17 | Job: 1751 - Cryostat Procurement | 377.29 |  | 377 | 55.0979 | 14.61% | 432.0979
17 | Job: 1752 - Base Support Structure Procurement | 231.08 |  | 230.58 | 33.6989 | 14.61% | 264.2789
18 | Job: 1801-Field Period Assly -CHRZANOWSKI (ORNL) | 64.72 | 64 | 0 | 0 |  | 64
18 | Job: 1802 - FP Assy Oversight&Support-VIOLA | 1614.34 | 754 | 826.2931 | 96.609 | 11.69% | 1676.9022
18 | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1170.14 | 1007 | 298.6245 | 43.6434 | 14.61% | 1349.2679
18 | Job: 1804-Metrology Hardware-RAFTOPOULOS | 587.41 | 559 | 12.6741 | 0 | 0% | 571.6741
18 | Job: 1805 -FP Assy H/W&Fixture | 315.2 | 7 | 313.0511 | 68.6278 | 21.92% | 388.6789
18 | Job: 1806 - FP Assembly specs & dwgs | 210.18 | 4 | 177.7288 | 20.7798 | 11.69% | 202.5086
18 | Job: 1810 - Field Period Assembly-VIOLA | 2618 | 304 | 2371.5272 | 1246.1423 | 52.55% | 3921.6695
19 | Job: 1901 - Stellarator Core Mngtt&Integr-NELSON | 2621 | 2007.5 | 576.7641 | 33.7172 | 5.846% | 2617.9814
2 | Job: 2001-VPS Gas& Cond Sys Oversight-BLANCHARD | 62.89 | 63 | 0 | 0 |  | 63
2 | Job: 2101 - Fueling Systems | 61.21 |  | 61.2 | 5.3666 | 8.769% | 66.5666
2 | Job: 2201 - Vacuum Pumping Systems | 77.22 |  | 77 | 6.752 | 8.769% | 83.752
2 | Job: 2501 - Neutral Beam Refurbishment-STEVENSON | 285.01 | 285 | 0 | 0 |  | 285
3 | Job: 3101 Magnetic Diagnostics | 521.71 | 481 | 133.9229 | 9.7863 | 7.307% | 624.7092
3 | Job: 3601 - Edge and Divertor | 9.47 |  | 9 | 1.3153 | 14.61% | 10.3153
3 | Job: 3801 - Electron Beam Mapping | 29.63 |  | 29 | 4.2383 | 14.61% | 33.2383
3 | Job: 3901 - Diagnostics sys Integration-JOHNSON | 375.26 | 327 | 24.8761 | 3.6356 | 14.61% | 355.5117
4 | Job: 4101 - AC Power-RAMAKRISHNAN | 363.99 | 107 | -123 | 0 | 0% | -16
4 | Job: 4301 - DC Systems-RAMAKRISHNAN | 729.11 | 370 | 347 | 25.3567 | 7.307% | 742.3567
4 | Job: 4401 - Control & Protection-RAMAKRISHNAN | 1012.6 | 81 | 855 | 62.4784 | 7.307% | 998.4784
4 | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 1076.03 | 155 | 751 | 54.8787 | 7.307% | 960.8787
4 | Job: 4601 - FCPC Bldg Mods-RAMAKRISHNAN | 1.28 | 1.3 | 0 | 0 |  | 1.3
5 | Job: 5101 - TCP/IP Infrastructure Systems | 150.84 |  | 150 | 13.1533 | 8.769% | 163.1533
5 | Job: 5201 - I&C Systems | 138.77 |  | 137 | 12.0134 | 8.769% | 149.0134
5 | Job: 5301 - Data Acquisition | 150.09 |  | 150.1 | 13.1621 | 8.769% | 163.2621
5 | Job: 5401 - Facility Timing & | 82.15 |  | 82 | 7.1905 | 8.769% | 89.1905
5 | Job: 5501 - Real Time Control System | 94 |  | 93 | 8.1551 | 8.769% | 101.1551
5 | Job: 5601 - Central Safety Interlock Systems | 129.35 |  | 129 | 11.3119 | 8.769% | 140.3119
5 | Job: 5801 -Central I&C Integr | 58.2 | 33 | 12 | 1.0523 | 8.769% | 46.0523
6 | Job: 6101 - Water Systems | 13.81 |  | 13 | 1.5199 | 11.69% | 14.5199
6 | Job: 6163 - Facility Systems Support FY04 | 15 | 15 | 0 | 0 |  | 15
6 | Job: 6201 - Cryogenic Systems | 456.14 |  | 456 | 66.6436 | 14.61% | 522.6436
6 | Job: 6301 - Utility Systems | 106.9 |  | 107 | 72.9453 | 68.17% | 179.9453
6 | Job: 6501 - Facility Systems Integration-DUDEK | 9.38 | 9 | 0 | 0 |  | 9
7 | Job: 7101 - Shield Wall Modif | 32.64 | 33 | 0 | 0 |  | 33
7 | Job: 7301 - Platform Design & | 113.89 | 76 | 39.3 | 5.7436 | 14.61% | 121.0436
7 | Job: 7401 - TC Prep & Mach Assy Planning-PERRY | 1552 | 844 | 717.5559 | 52.4348 | 7.307% | 1613.9907
7 | Job: 7501 - Construction Support Crew | 589 |  | 588.2 | 42.9822 | 7.307% | 631.1822
7 | Job: 7503 - Machine Assembly | 1306 |  | 1294 | 378.2317 | 29.23% | 1672.2317
7 | Job: 7601 - Tooling Design & Fabrication | 237.65 |  | 236 | 34.491 | 14.61% | 270.491
8 | Job: 8101 - Project Management & Control-NEILSON | 3836 | 2638.5 | 999.0368 | 29.2015 | 2.923% | 3666.7383
8 | Job: 8102 - NCSX MIE Management ORNL-LYON | 532.35 | 466 | 88.6288 | 2.5906 | 2.923% | 557.2194
8 | Job: 8202 - Engr Mgmt & Sys Eng Support-REIERSEN | 3091 | 2382 | 872.592 | 51.0111 | 5.846% | 3305.6031
8 | Job: 8203 - Design Integration-BROWN | 1037 | 889 | 152.6298 | 788.5191 | 516.6% | 1830.1489
8 | Job: 8204 - Systems Analysis-BROOKS | 1216.11 | 1061 | 204.0514 | 23.8574 | 11.69% | 1288.9089
8 | Job: 8205 - Dimensional Control Coordination | 301 | 242 | 56.584 | 6.6157 | 11.69% | 305.1998
8 | Job: 8401 - Project Physcis-ZARNSTORFF | 324.61 | 324 | 0 | 0 |  | 324
8 | Job: 8402 - Project Physics MIE ORNL-LYON | 146.44 | 146 | 0 | 0 |  | 146
8 | Job: 8501 - Integrated Systems Testing | 814 |  | 812 | 118.6724 | 14.61% | 930.6724
8 | Job: 8998 - Allocations | 1704 | 1257 | 52.2874 | 3.8209 | 7.307% | 1313.1083
|  | 85774.16 | 60343.8 | 27068.3151 | 4989.3847 | 18.43% | 92401.4998
| TEC= | 92401.4998