## Sheet2
current forecast | OCT FY06 | NOV FY06 | DEC FY06 | JAN FY06 | ytd cost variance | Oct-Jan Actual | FEB FY06 | MAR FY06 | APR FY06 | MAY FY06 | JUN FY06 | JUL FY06 | AUG FY06 | SEP FY06 | EAC (bcwr and actual cost) | add'l unbudgeted work etc |  | accelerated scope |  | schedule slip |  | PMB |  | Unknown
1203 | 21.4 | 24.7 | 19.8 | 45.4 | 17.899 | 105.101 | 63.9 | [7 empty] | 169.001 | [6 empty] | 155.3 | 13.701
1204 |  |  | 11.2 | 13.8 | 28.306 | 52.865 | 0.8 | 35.1 | 96.4 | 4.4 | 4.1 | 0.8 | 0.9 | 0.8 | 196.165 | [6 empty] | 192.9 | 3.265
1250 | 198.7 | 120.6 | 175.5 | 299.7 | 52.763 | 1215.919 | 281.7 | 236.1 | 156 | 217.2 | 588.2 | 0.3 |  |  | 2695.419 | 146 | sxr modification |  |  |  |  | 2611 | 84.419
1301 | 2.3 | 2.2 | 1.9 | 2.3 | 19.043 | 22.509 | 1.3 | 0.1 | [6 empty] | 23.909 | [6 empty] | 2.8 | 21.109
1302 | 0.1 | 0.1 | 0.1 | 0.1 | -3.115 |  | 10.4 | 7.6 | 7.8 | 10.6 | 15 | 13.6 | 15.7 | 2 | 82.7 |  |  | 70 | PF design |  |  | 12.5 | 70.2
1303 |  |  |  | 10.9 | 0 | 7.781 | 34.9 | 33.5 | 27.5 | 30.3 | 20.6 |  |  |  | 154.581 |  |  | 154 | CS supt design |  |  |  | 154.581
1350 | 67.8 | 21.9 | 15.8 | 16.1 | 36.738 | 143.386 | 9.2 |  | 56.1 | 61.7 | 5.6 |  | 62.3 | 77.3 | 415.586 | [6 empty] | 352.2 | 63.386
TF fab 1351/1361 | 5.9 | 7.4 | 6.3 | 96.9 | 34.096 | 151.463 | 22.4 | 15.7 | 101 | 55.2 | 65.3 | 73.2 | 81.2 | 118.2 | 683.663 |  |  | -200 | TF fab delayed |  |  | 885.1 | -201.437 | ?
1353 |  |  |  |  | 0 | [6 empty] | 3.2 | 4.6 | 15.4 | 23.2 | [7 empty] | 23.2
1354 |  |  |  |  | 0 | [8 empty] | 8.1 | 8.1 | [7 empty] | 8.1
1403/1421 | 29.7 | 25.3 | 15.6 | 19.3 | 193.839 | 180.467 | 51.1 | 27.9 | 10.7 | 11.8 | 11.8 | 4.9 | 18.8 | 11.5 | 328.967 | [6 empty] | 201.7 | 127.267
1408 | 60.5 | 27.5 | 65.5 | 214.2 | -17.884 | 335.192 | 284.3 | 127.3 | 17.1 | 144.4 | 158.7 | 35.9 | 1.9 | 1.7 | 1106.492 | [6 empty] | 1065.6 | 40.892
1411 | 277.4 | 277.7 | 259 | 473.9 | -48.4705 | 1102.4215 | 345.3 | 412.1 | 401.3 | 418.4 | 317.6 | 205.5 | 243.7 | 195.7 | 3642.0215 | 178 | tech change (50% of 356) | 165 | incentives if PPPL dates met | -411 | MCWF deliveries | 4053.4 | -411.3785 | 195 | add'l if EIO meets their comittment date
1414 | 31.6 |  | 10.7 | 23.8 | 8.142 | 72.171 | 23.5 | 1.2 | 30.3 | [5 empty] | 127.171 | 63 | kickless cable testing |  |  |  |  | 141.8 | -14.629
1416 | 23.8 | 30 | 77.9 | 97.1 | -121.81 | 126.813 | 165.1 | 198.6 | 87.2 | 46.1 | 14.2 |  |  |  | 638.013 | [6 empty] | 691.2 | -53.187
1451 | 145.8 | 83.1 | 80.3 | 152.5 | 211.6735 | 672.0825 | 138.6 | 197 | 212.5 | 222.8 | 254 | 219.6 | 247.2 | 228 | 2391.7825 | 1719.7 | if winding continues at .8 cpi |  |  |  |  | 2413.4 | -21.6175
1459 |  |  |  |  | 42.617 | 49 | [8 empty] | 49 | 2292.9333 | 1658 | [5 empty] | 49 | 175 | Add'l if winding continues at .7 cpi instead of .8
1501 |  |  |  |  | 0 | 7.761 | 11.2 | 34.8 | 22.2 | 41.7 | 19.9 | 3.1 |  |  | 140.661 | 573.2333 | [5 empty] | 130.6 | 10.061
1601 |  |  |  |  | 0 | [6 empty] | 17.3 | 19.9 | 17.3 | 54.5 | 0.25004 |  | 55 | coil serv LN2 supply design |  |  |  | 54.5
1701 | 2.1 | 2 | 1.7 | 2.1 | 28.326 | 24.554 | 1.3 | 1.5 | 1.3 | 1.4 | 31.6 | 28.7 | 25.3 | 21 | 136.654 |  |  | 131 | Base supt structue |  |  | 5.5 | 131.154
1802 | 12.4 | 11.8 | 26.7 | 32.9 | -5.601 | 77.805 | 31.3 | 36 | 31.3 | 34.5 | 34.5 | 31.3 | 36 | 31.3 | 344.005 | [6 empty] | 350.2 | -6.195
1803 | 39.4 | 33.8 | 29.7 | 35.2 | -9.854 | 120.508 | 27.2 | 54 | 60.1 | 43.8 | 33.8 | 37 | 53.6 | 45.5 | 475.508 | [6 empty] | 464.6 | 10.908
1804 |  |  |  |  | 20.598 | 20.305 | 6.7 | 1.5 | 1.3 | 0.1 |  |  |  | 11 | 40.905 | [6 empty] | 14.6 | 26.305
1810 |  |  |  |  | 0 | 0.575 | 15.7 | 25.9 | 43.4 | 59 | 69.5 | 50.6 | 77.3 | 62.8 | 404.775 | 312 | updated estimate |  |  |  |  | 362.1 | 42.675
1901 | 51.9 | 49.4 | 42 | 51.9 | -12.43 | 150.661 | 41 | 47.2 | 41 | 45.1 | 45.1 | 41 | 47.2 | 41 | 499.261 | [6 empty] | 517.7 | -18.439
3101 | 24.5 | 15 | 15.9 | 20.2 | 98.8 | 159.521 | 38.7 | 12.4 | 65 | 10.8 | 29.7 | 18.3 | 25.5 | 19.6 | 379.521 | [6 empty] | 294.8 | 84.721
3901 | 5.9 | 5.7 | 4.8 | 5.9 | -3.401 | 19.351 | 5.7 | 6.5 | 5.7 | 6.2 | 6.2 | 5.7 | 6.5 | 5.7 | 67.551 | [6 empty] | 70.5 | -2.949
4101 | 1 | 0.8 | 0.7 | 0.9 | 0 | [8 empty] | 0.1 | 0.1 | [6 empty] | 0.1 | 0
4301 | 16 | 15.2 | 13 | 7.8 | 74.752 | 119.398 | 3.5 | 4.1 | 1.6 | 1.8 | 1.8 | 1.6 | 8.3 | 8.1 | 150.198 | [6 empty] | 88 | 62.198
4401 | 0.4 | 0.3 | 0.3 | 0.4 | 15.078 | 19.28 | [8 empty] | 19.28 | [7 empty] | 19.28
4501 | 0.1 | 0.4 | 0.3 | 0.4 | 0 |  | 36 | 49.1 | 6.5 | 7.2 | 7.2 | 6.5 | 7.5 | 6.5 | 126.5 | [6 empty] | 127.6 | -1.1
7301 | 0.7 |  |  |  | 0 | 3.044 | [8 empty] | 3.044 | [7 empty] | 3.044
7401 | 0.3 |  |  |  | 23.652 | 29.634 |  |  |  |  | 3 | 2.7 | 3.1 | 2.7 | 41.134 | [6 empty] | 17.6 | 23.534
8101 | 53.3 | 50.8 | 43.2 | 53.3 | 17.78 | 218.356 | 50.8 | 58.4 | 50.8 | 55.8 | 55.8 | 50.8 | 58.4 | 53.3 | 652.456 | [6 empty] | 634.6 | 17.856
8102 | 14.6 | 13.9 | 11.8 | 14.6 | 38.919 | 57.8 | 13.9 | 16 | 13.9 | 15.3 | 15.3 | 13.9 | 16 | 14.6 | 176.7 | [6 empty] | 173.6 | 3.1
8202 | 52.6 | 50.1 | 42.5 | 52.6 | 0 | 236.839 | 50.1 | 57.6 | 50.1 | 55.1 | 55.1 | 50.1 | 57.6 | 52.6 | 665.139 | [6 empty] | 625.6 | 39.539
8203 | 11.8 | 11.2 | 9.5 | 11.8 | -16.227 | 27.923 | 11.2 | 12.9 | 11.2 | 12.3 | 12.3 | 11.2 | 12.9 | 11.8 | 123.723 | [6 empty] | 140.2 | -16.477
8204 | 18.9 | 18 | 15.3 | 18.9 | 70.08 | 140.861 | 18 | 20.7 | 18 | 19.8 | 19.8 | 18 | 20.7 | 18.9 | 294.761 | [6 empty] | 225.4 | 69.361
8205 | 15.9 | 15.1 | 12.9 | 15.9 | -9.471 | 50.141 | 15.1 | 17.4 | 15.1 | 16.7 | 16.7 | 15.1 | 17.4 | 15.9 | 179.541 | [6 empty] | 189.3 | -9.759
8998 | 27.7 | 26.4 | 22.4 | 27.7 | 36.096 | 139.914 | 26.4 | 30.3 | 26.4 | 29 | 29 | 26.4 | 30.3 | 27.7 | 365.414 | [6 empty] | 329.8 | 35.614
[5 empty] | 820.934 | 5861.402 | [8 empty] | 18077.102 | 5285.1167 |  | 375 |  | -411 |  | 17541.3 | 535.802
738.1825
1719.7
[5 empty] | 137.177 | [9 empty] | 429.925

## Sheet1
FY 2006 Budget Status 3/15/06
Funding | [12 empty] | FY06 YTD | Cum
|  |  | BA |  |  |  | 15900 |  |  |  |  | BCWS | 7761 | 46323
|  |  | BA Increment |  |  |  | 1291 |  |  |  |  | BCWP | 6429 | 44743
|  |  | 1% holdback |  |  |  | -171.91 |  |  |  |  | ACWP | 7858 | 46172
|  |  | net BA |  |  |  | 17019.09 |  |  |  |  | SV | -1332 | -1580
|  |  | FY2005 carryover |  |  |  | 2930.113 |  |  |  |  | SPI | 0.82837 | 0.96589
|  |  | FY2006 Budget |  |  |  | 19949.203 |  |  |  |  | CV | -1429 | -1429
Plan | [11 empty] | CPI | 0.81815 | 0.96905
|  |  | ECP-39 BCWS |  |  |  | 17534 |  |  |  |  | BCWR | 11105
|  |  | Management Reserve |  |  |  | 2415.203 | [5 empty] | #REF! |  | ETC = (BCWR + ETC+accel scope+MCWF slip+scope increase+
[7 empty] | 19949.203 | [5 empty] | 1.25% | -0.326% | Spending rate in excess of plan (ACWP-BCWS)/BCWS)
EAC bottoms-up | [12 empty] | 138.7946 | #REF! | Cost Variance in excess of schedule slip =
| Baseline scope | [5 empty] | 17534 | [6 empty] | Say future cost variance to be offset by schedule slippages
| Cost Variances to date | [10 empty] | 1 | Cost Variances to date | 1409 | 58.34%
|  |  | Winding operations |  |  |  | 381 |  |  |  |  | 2 | ETC Update | 845.784 | 35.02%
|  |  | Project engr |  |  |  | 143 |  |  |  |  | 3 | Accelerated Scope | 452 | 18.71%
|  |  | Vac Vessel Design & hardware |  |  |  | 134 |  |  |  |  | 5 | Schedule slip into FY07 | -411 | -17.02%
|  |  | Electr Power sys |  |  |  | 132 |  |  |  |  | 6 | Management Reserve Balance= | 119.419 | 4.944%
|  |  | TF Fabr prep |  |  |  | 118 | [6 empty] | 2415.203 | 100%
|  |  | Coil Testing facility |  |  |  | 102
|  |  | Project management |  |  |  | 74
|  |  | MC Design |  |  |  | 63
|  |  | Magnetic diagnostics |  |  |  | 50
|  |  | misc other |  |  |  | 212
1409
ETC Update
|  |  | VV H/W (heater tape, Vert suprts) |  |  |  | 71
|  |  | Stage 1 FP Assy |  |  |  | 56
|  |  | MCWF Contract mod #11 for technical changes |  |  |  | 122.784 | (balance of $356 contract mod to be paid in FY07)
|  |  | Winding operations |  |  |  | 387 | (assumes balance of year at .8 cpi)
|  |  | MCWF Contract mod #12 delivery incentives |  |  |  | 209 | PPPL Dates met
845.784
Accelerated Scope
|  |  | PF Design |  |  |  | 70
|  |  | CS Suprt Design |  |  |  | 154
|  |  | Coil Services Design |  |  |  | 55
|  |  | Base Suprt Structure Design |  |  |  | 131
|  |  | Stage 1 FP Assy |  |  |  | 42
452
Schedule slip into FY07
|  |  | MCWF Schedule slip |  |  |  | -411 | (relative to Baseline)
|  |  | FY06 EAC = |  |  |  | 19829.784
| Management Reserve Balance= | [5 empty] | 119.419
EAC straightline costs | [6 empty] | 19851.7895
| Management Reserve Balance= | [5 empty] | 97.4135
ECP Plans
ECP-43 (march)
|  |  | MCWF Contract mod #11 for technical changes | [6 empty] | 356
|  |  | MCWF Contract mod #12 delivery incentives | [6 empty] | 535.8767
[10 empty] | 891.8767 |  | 1601.8767
Risks
| MCWFadditional if EIO meets their comittment dates | [8 empty] | 710 | FY06= $161
Opportunities
| SXR Diagnostic Modification to VVSA (classify as capital upgrade (non-MIE) | [8 empty] | 146
| Startup manpower (reclassify as non-MIE operating consistent with DOE regs) | [8 empty] | 711
| TF Fabrication Facility (Reclassify as non-MIE future upgrade or other use) | [8 empty] | 545
| Reduced MCWF Contract oversight (titleIII) | [8 empty] | 50
| First Plasma Acceleration (2 months) | [8 empty] | 400
| Central Solenoid Support Fabrication | [8 empty] | ?
| Health Physics in support of D-site fabrication | [8 empty] | ?
[10 empty] | 1852 | [5 empty] | 0.65753 | 0.82192 | 0 | -13.8082 | -25
[16 empty] | 0.65753 | 0.82192 | 0 | -10.5205 | -25
[16 empty] | 0.65753 | 0.82192 | 0 | -15.1233 | -25
[16 empty] | 0.65753 | 0.82192 | 0 | -19.726 | -25
|  | Contracy |  |  |  |  | EIO Incentive Payment plan (Contract vs Project schedule) | [8 empty] | 0.65753 | 0.82192 | 0 | -20 | -4.589
|  | Incentives | [13 empty] | 0.65753 | 0.82192 | 0 | -20 | -10.3425
| Winding form | On Contract Date | 1 mo. Late | 2 mo. Late | 3 mo. Late | Contract Date | Project ECP-43 Baseline Date | difference | Project Incentives Planned (ECP-43) | [6 empty] | 0.65753 | 0.82192 | 0 | -20 | -15.274
| C3 | 45 | 25 |  |  | 2006-02-28 | 2006-03-03 | 3 | 43.0274 | [6 empty] | 2.137 | 2.4658 | 4.9315 | -65 | -65.5479 | -150
| C4 | 45 | 25 |  |  | 2006-03-10 | 2006-03-31 | 21 | 31.1918 | [6 empty] | 0.65753 | 0.82192 | 0 | -20 | -25
| C5 | 45 | 25 |  |  | 2006-04-18 | 2006-05-04 | 16 | 34.4795 | [6 empty] | 0.82192 | 1.6438 | 1.6438 | -25 | -50
| A1 | 45 | 25 |  |  | 2006-05-16 | 2006-06-08 | 23 | 29.8767 | [6 empty] | 0.65753 | 0.82192 | 0 | -20 | -25
| A2 | 45 | 25 |  |  | 2006-06-13 | 2006-07-13 | 30 | 25.274 | [6 empty] | 0.65753 | 0.82192 | 0 | -20 | -25
| A3 | 45 | 25 |  |  | 2006-07-11 | 2006-08-16 | 36 | 20.411 | [6 empty] | 0.65753 | 0.82192 | 0 | -20 | -25
| B1 | 45 | 25 |  |  | 2006-08-08 | 2006-09-20 | 43 | 14.6575 | [6 empty] | 0.65753 | 0.82192 | 0 | -20 | -25
| A4 | 45 | 25 |  |  | 2006-09-05 | 2006-10-24 | 49 | 9.726 | [6 empty] | 1.6438 | 1.6438 | 0 | -50 | -50
| B2 | 290 | 225 | 150 |  | 2006-10-03 | 2006-11-29 | 57 | 159.4521
| B3 | 45 | 25 |  |  | 2006-10-31 | 2007-01-11 | 72 | 1e-06
| B4 | 125 | 100 | 50 |  | 2006-11-28 | 2007-02-14 | 78 | 21.7808
| B5 | 45 | 25 |  |  | 2006-12-29 | 2007-03-20 | 81 | 1e-06
| B6 | 45 | 25 |  |  | 2007-01-23 | 2007-04-23 | 90 | 1e-06
| A5 | 45 | 25 |  |  | 2007-02-20 | 2007-05-25 | 94 | 1e-06
| A6 | 45 | 25 |  |  | 2007-03-20 | 2007-06-29 | 101 | 1e-06
| C6 | 100 | 50 |  |  | 2007-04-17 | 2007-08-03 | 108 | 1e-06
1100
| eio= | 146 | [6 empty] | 146
|  | 1246 | Maximun cost | [5 empty] | 535.8767 | [13 empty] | 710.1233
[8 empty] | Potential Risk Outstanding to DOE = | 410.1233
[8 empty] | Risk borne by Princeton University= | 300
91.25
|  |  | days in average month = | 30.4167
Note on I32: rstrykowsky: 129 for EIO, 13x8