## Sheet2
[5 empty] | - | Unrecoverable Cost Variances |  | ETC Updates
ETC Updates |  |  |  |  | 12 - Vacuum Vessel Systems Total |  |  | 372
WBS 12 | Vac Vsl hardware design and hardware | 106 | Completion of thermal insulation, heater tape and assembly drawings. Port Insulation increase. | WBS 12 |  | 154 | Vac Vsl hardware design - Design of heater tape, cooling tubes and associated hardware | 161 | Vac Vsl hardware design and hardwareCompletion of thermal insulation, heater tape and assembly drawings. Port Insulation increase. -
WBS 13 | TF coil- fabrication | 348 | Increase in fabrication cost ($1,473 contract award) | WBS 12 |  | 57 | VVSA Contract oversight - Support of MTM leak testing of the VVSA, and NCR reconciliation
WBS 13 | TF coil -PPPL oversight/title III | 165 | Increase to oversee outsourcing of fabrication (average of 1 trip/week). Risk mitigation due to vendor history. |  | 13 - Conventional Coils Total |  |  | 565
WBS 13 | PF coil procurement & design | -95.266 | Estimate reduced in recognition of TF cost. | WBS 13 |  | 64 | TF Fab Facility - TF Coil Hardware fabrication | 443 | TF coil- fabricationIncrease in fabrication cost ($1,473 contract award) - |  | 793
WBS 13,15 | Base ,& coil support struct | -63 | combine base ,& coil support struct into one procurement | WBS 13 |  | 101 | TF coil -PPPL oversight/title III - TF outsourcing efforts (documentation, travel, evaluation) | 185 | TF coil -PPPL oversight/title IIIIncrease to oversee outsourcing of fabrication (average of 1 trip/week). Risk mitigation due to vendor history. -
WBS 13 | Central solenoid support structure fabrication | -144 | Simpler design to be fabricated by PPPL |  |  |  |  | -90 | PF coil procurement & design-Estimate reduced in recognition of TF cost. - |  | -228
WBS 14 | Cryogenic test facility (job 1414) | 66 | Completion of test facility and testing of modular coil |  |  |  |  | -138 | Central solenoid support structure design&fabrication-Simpler design to be fabricated by PPPL
WBS 14 | MC winding (job 1451 & 1459) | 448.83 | Estimate growth (including overtime and second shift differential) into mid-FY07. |  | 14 - Modular Coils Total |  |  | 1436
WBS 14 | Completion of Type A & B modular coil design | -97 | Elimination of redundant assembly and hardware drawings. | WBS 14 |  | 130 | Cryogenic test facility (job 1414) - Facility design , testing and modifications in support of the upcoming mod. coil cold test | 27 | Cryogenic test facility (job 1414)Completion of test facility and testing of modular coil - | 157 | 644
WBS 14 | Mod Coil interface design | 125 | Additional analysis of joint and resultant design modifications | WBS 14 |  | 492 | MC winding (job 1451 & 1459) - Unanticipated work, facility mods, initial learning curve/efficiencies. | 688 | MC winding (materials and labor job 1408, 1451 & 1459) Estimate growth (including overtime and second shift differential) into mid-FY07. -
WBS 14 | Mod Coil interface hardware | 70 | Shims, bolts, washers and bladder hardware. | WBS 14 |  | 22 | Modular Coil Design - | -90 | Type C, A & B modular coil design. Elimination of redundant assembly and hardware drawings. - | 108 | 86
WBS 18 | FP assy stage 1 | 163 | Additional assembly steps and includes hands-on senior field supervisor. |  |  |  |  | 106 | Mod Coil interface design Additional analysis of joint and resultant design modifications -
WBS 18 | FP assy tooling & fixtures | 112 | Fixtures re-estimate plus add'l stage 5 fixture. |  |  |  |  | 70 | Mod Coil interface hardwareShims, bolts, washers and bladder hardware. -
WBS 18 | FP assy tooling & fixtures -engr& design increase | 140 | Additional engr and designer support to design field period assy fixtures. |  |  |  |  | -9 | Misc
WBS 18 | Metrology H/W maint and support (job 1804) | 74 | Metrology hardware & software maintenance, replacement parts, calibration |  | 15 - Structures Total |  |  | 3 | Misc. rescheduling
WBS 18 | Metrology engr supervision (raftopolous) stage 1 FP assy | 168 | Increase to full time metrology engr to support completion of mod coil fabr plus field period assembly tasks thru FY07. |  | 16 - Coil Services |  |  | 3 | Misc. rescheduling
WBS 82 | Proj Engr (Reierson,Dudek, Simmons) | 77.911 | Increased RLM oversight and Project engineering |  | 17 - Cryostat and Base Support Structure Total |  |  | -34
WBS 82 | Design Integration (brown, Designer) | 58.672 | Increase designer and engineer time for global design interface. | WBS 17 |  | 47 | WBS 17 cryostat and base support - Alternate configurations studied. | -81 | Base ,& coil support struct combine base ,& coil support struct into one procurement -
WBS 82 | Systems Analysis (Brooks) | 72.87 | Global machine modeling and analysis |  | 18 - Field Period Assembly Total |  |  | 641
WBS 82 | Dimensional Control (Stratton, Raftopolous) | 66.166 | Dimensional control supervision. | WBS 18 |  | 79 | WBS 18 Field period assy fuxtures & prep - Purchase of a third Romer arm and computer | 190 | FP assy stage 1-Additional assembly steps and includes hands-on senior field supervisor. - | 225
|  | 1862.183 | [5 empty] | 35 | Metrology engr supervision (raftopolous) stage 1 FP assyIncrease to full time metrology engr to support completion of mod coil fabr plus field period assembly tasks thru FY07. -
[8 empty] | 185 | FP assy tooling & fixtures-Fixtures re-estimate plus add'l stage 5 fixture. - | 325
[8 empty] | 140 | FP assy tooling & fixtures -engr& design increase-Additional engr and designer support to design field period assy fixtures. -
ETC Updates (continued) | [7 empty] | 12 | Metrology H/W maint and support (job 1804)Metrology hardware & software maintenance, replacement parts, calibration -
WBS 2 | Fueling and Vacuum Pumping | -306 | Simplified systems design using existing pumping system (tested on VVSA).
WBS 3 | Magnetic Diagnostic design and fabrication | -7.379 | Anticipated FY06 rate variance |  | 19 - Stellarator Core Management and Integr |  |  | 4 | Misc. rescheduling
WBS 3 | E-beam mapping diagnostic hardware | -176 | Use of collaration for e-beam mapping |  | 2 - Heating,Fueling & Vac Systems |  |  | -306
WBS 3 | Edge & diverter diagnostics | -36 | Share camera from NSTX | WBS 2 |  |  |  | -306 | Fueling and Vacuum Pumping - Simplified systems design using existing pumping system (tested on VVSA).
WBS 4 | Controls and protection | -339.734 | eliminate DC shunts and simplify overload protection |  | 3 - Diagnostics |  |  | -146
WBS 4 | AC power | -67.977 | Minimal ex-test cell AC power and grounding | WBS 3 |  | 70 | Magnetic Diagmnostics - Engineering and fabrication of vacuum vessel saddle loops. | -3 | Magnetic Diagnostic design and fabrication -
WBS 4 | DC power | 70 | Power loop design and C-site rectifier maintenance\ |  |  |  |  | -177 | E-beam mapping diagnostic hardware - Use of collaration for e-beam mapping
WBS 51 | TCP/IP network | -106.486 | Local TCP/IP network infrastructure |  |  |  |  | -36 | Edge & diverter diagnostics - Share camera from NSTX
WBS 52 | Central Facilities I&C | -383.452 | Local Control |  | 4 - Electrical Power Systems |  |  | -212
WBS 53 | Diagnostic Data Acquisition & computing | -176.857 | The NSTX infrastructure will be used where possible. | WBS 4 |  | 141 | Electrical Power Systems - Revisions to the C-site power systems and cabling design | -358 | Controls and protection - eliminate DC shunts and simplify overload protection
WBS 54 | Facility timing & synchronization | -102.971 | Use timing device designs in use on NSTX |  |  |  |  | -67 | AC power - Minimal ex-test cell AC power and grounding
WBS 55 | Real time plasma control | -85.716 | PC based "LabVIEW" will produce open-loop power supply commands. |  |  |  |  | 72 | DC power - Power loop design and C-site rectifier maintenance\
WBS 56 | Central Safety & Interlokcs | -200.08 | Use of locks and physical barriers |  | 5 - Central I&C Systems |  |  | -1072.8
WBS 58 | Central I&C Integr and oversight | 24.2 | Oversight | WBS 5 |  |  |  | -130 | TCP/IP network - Local TCP/IP network infrastructure
WBS 61 | Water systems | -78.4 | Once through potable water system for vacuum pumps only |  |  |  |  | -392 | Central Facilities I&C - Local Control |  | Expected FY06 Rate Variance | - $406k
WBS 75 | Machine assy preparations | -19.578 | Eliminate TC floor resurface and completion of control rm floors. |  |  |  |  | -179 | Diagnostic Data Acquisition & computing - The NSTX infrastructure will be used where possible.
WBS 75 | Machine assembly | -135 | 2 shift ops on select tasks (reduced support crews |  |  |  |  | -114 | Facility timing & synchronization - Use timing device designs in use on NSTX
WBS 81 | Project management office | -88.8 | Anticipated FY06 rate variance and allocations |  |  |  |  | -86 | Real time plasma control - PC based "LabVIEW" will produce open-loop power supply commands.
WBS 85 | wbs 85 PTP & ISTP startup | -396.6 | Reduced operational and startup procdures plus allocation of startup staff |  |  |  |  | -196 | Central Safety & Interlokcs - Use of locks and physical barriers
|  | -2612.83 | [5 empty] | 24.2 | Central I&C Integr and oversight - Oversight
* includes anticipated rates variances |  | -750.647 |  |  | 6 - Facility Systems |  |  | -79
|  |  |  | WBS 6 |  |  |  | -79 | Water systems - Once through potable water system for vacuum pumps only
[5 empty] | 7 - Test Cell Prep & Machine Assembly |  |  | -194
|  | #REF! |  | WBS 7 |  | 37 | Test Cell Preparations - NCSX test cell electrical power upgrades | -231 | Machine assy preparations - Eliminate TC floor resurface and completion of control rm floors. 2 shift ops on select tasks (reduced support crews
|  | -750.647 | -2612.83 |  | 8 - ProjectOversight & Support |  |  | 224
|  |  |  | WBS 81 |  | 83 | Project management office - Project management team (PPPL & ORNL) and overhead allocations | -53 | Project management office
|  |  |  | WBS 82 |  | 40 | Proj Engr (Reierson,Dudek, Simmons) - RLM oversight | 132 | Proj Engr (Reierson,Dudek, Simmons) - Increased RLM oversight and Project engineering | 402
|  |  |  | WBS 82 |  | 143 | Systems Analysis (Brooks) - Integrated stellarator modeling and analysis (ie mod coil coil-to-coil and machine support) | 61 | Design Integration (brown, Designer) - Increase designer and engineer time for global design interface. | 172
[8 empty] | 151 | Systems Analysis (Brooks) - Global machine modeling and analysis | 294
[8 empty] | 58 | Dimensional Control (Stratton, Raftopolous) - Dimensional control supervision.
|  |  |  | WBS 85 |  |  |  | -391 | wbs 85 PTP & ISTP startup - Reduced operational and startup procdures plus allocation of startup staff
[5 empty] | Rate Variance |  |  | -406 | Anticpated Rate Reductions at PPPL due to the overliqidation of indirect costs.
798.2
494

## Sheet1
ECP45 vs ECP43 comparison
Sum of Budget
WBS II | Job | ecp45 | ecp49 | Change |  | WBS II |  |  |  | Change
11 - In-Vessel Components | Job: 1101 - Limiter Adv Conc/Prel Dsn-**CLOSED* | 0.1 | 0.1 | 0
12 - Vacuum Vessel Systems | Job: 1201 - Vacuum Vessel Prelim Dsn-**CLOSED** | 424.4 | 424.4 | 0
| Job: 1202 - Vacuum Vessel R&D | 1770.2 | 1770.2 | 0 |  | 12 - Vacuum Vessel Systems Total | + $372k |  |  | 372 | + $ | k | + $372k
| Job: 1203 - Vacuum Vessel Final Dsn-GORANSON | 1270.3 | 1270.3 | 0
| Job: 1206 - VV Field Weld Joint R&D-**CLOSED** | 15.6 | 15.6 | 0 |  | 13 - Conventional Coils Total | + $565k |  |  | 565.1 | + $ | k | + $565.1k
| Job: 1250 - Vacuum Vessel Fabrication-VIOLA | 5682.63 | 5682.63 | 0
| Job:1204-VV Sys Procurements (non VVSA)-DUDEK | 603.5 | 603.5 | 0 |  | 14 - Modular Coils Total | + $1,436k |  |  | 1435.8 | + $ | k | + $1435.8k
12 - Vacuum Vessel Systems Total |  | 9766.63 | 9766.63 | 0 |  | 15 - Structures Total | + $3k |  |  | 2.7 | + $ | k | + $2.7k
13 - Conventional Coils | Job: 1301 - TF Design-KALISH | 965.8 | 965.8 | 0
| Job: 1302 - PF Design -KALISH | 132 | 132 | 0 |  | 16 - Coil Services | + $3k |  |  | 2.8 | + $ | k | + $2.8k
| Job: 1303 -Centrol Solenoid Support Dsn-DAHLGREN | 116.9 | 116.9 | 0 |  | 17 - Cryostat and Base Support Structure Total | - $34k |  |  | -33.6 | - $ | k | - $-33.6k
| Job: 1350 TF Coil Fab Preparation-CHRZANOWSKI | 560.3 | 560.3 | 0
| Job: 1351 - TF Coil Fabr Supplies-KALISH | 469.6 | 469.6 | 0 |  | 18 - Field Period Assembly Total | + $641k |  |  | 640.7 | + $ | k | + $640.7k
| Job: 1352 - PF Coil Procurement-KALISH | 794.6 | 794.6 | 0
| Job: 1353 - CS Structure Procurement-DAHLGREN | 120.9 | 120.9 | 0 |  | 19 - Stellarator Core Management and Integration | + $4k |  |  | 4.3 | + $ | k | + $4.3k
| Job: 1354 - Trim Coil Design &Procurement-KALISH | 103.4 | 103.4 | 0 |  | 2 - Heating,Fueling & Vac Systems | - $307k |  |  | -307.3 | - $ | k | - $-307.3k
| Job: 1355 - WBS 13 I&C Proc & | 91.2 | 91.2 | 0 |  | 3 - Diagnostics | - $146k |  |  | -145.7 | - $ | k | - $-145.7k
| Job: 1361 - TF Fabrication-KALISH | 2016.6 | 2016.6 | 0 |  | 4 - Electrical Power Systems | - $213k |  |  | -212.6 | - $ | k | - $-212.6k
13 - Conventional Coils Total |  | 5371.3 | 5371.3 | 0
14 - Modular Coils | Job: 1401 - Mod Coil Prel.Dsn**CLOSED** | 304 | 304 | 0 |  | 5 - Central I&C Systems | - $1072k |  |  | -1071.9 | - $ | k | - $-1071.9k
| Job: 1402 - Mod.Coil Analyses**CLOSED** | 239.1 | 239.1 | 0
| Job: 1403 - Modular Coil Final Design-WILLIAMSON | 3496.6 | 3496.6 | 0 |  | 6 - Facility Systems | - $79k |  |  | -78.5 | - $ | k | - $-78.5k
| Job: 1405-Mod Coil Winding R&D Prep-**CLOSED** | 168.1 | 168.1 | 0
| Job: 1406 - Mod. Coil Winding | 2263.6 | 2263.6 | 0 |  | 7 - Test Cell Prep & Machine Assembly | - $194k |  |  | -193.5 | - $ | k | - $-193.5k
| Job: 1407 -Mod Coil Winding Facility-**CLOSED** | 2571.4 | 2571.4 | 0
| Job: 1410 MC Twisted Racetrack Fabr-**CLOSED** | 1050 | 1050 | 0 |  | 8 - ProjectOversight & Support | + $224k
| Job: 1411-MCWF Fabrication S005242-HEITZENROEDER | 9589.04 | 9589.04 | 0 |  | Expected FY06 Rate Variance | - $406k |  |  | -406 | - $ | k | - $-406k
| Job: 1412 - Complete Winding Facilities-*CLOSED* | 541 | 541 | 0
| Job: 1413 -MCWF Fracture Analysis-**CLOSED** | 27.8 | 27.8 | 0
| Job: 1409 - Coil Test Stand-GETTELFINGER*CLOSED* | 915.92 | 825.92 | -90
| Job: 1414 Coil Testing-Gettelfinger **CLOSED** | 470.861 | 674.861 | 204 | 114
| Job: 1415 Dim Cntrl Testing-RAFTOPOLOUS*CLOSED** | 23.9 | 23.9 | 0
| Job: 1416-Mod Coil Type A&B Final Dsn-WILLIAMSON | 446.2 | 446.2 | 0
| Job: 1419-Winding Fac. Mods-CHRZANOWSKI*CLOSED* | 55.2 | 55.2 | 0
| Job: 1421-Mod Coil Interface Hardware-WILLIAMSON | 916.9 | 916.9 | 0 |  | 21 - Fueling Systems Total |  | 88.1 | 123 | 34.9
| Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 6089.475 | 6089.475 | 0 |  | 22 - Torus Vacuum Pumping Systems |  | 418.9 | 76.1 | -342.8
| Job:1404-MCWF R&D & 1st Prod Casting**CLOSED** | 2543.5 | 2543.5 | 0 |  | 25 - Neutral Beam Injection System | Job: 2501 - Neutral Beam Refurbishment-STEVENSON | 284.4 | 285 | 0.6
| Job:1408-Mod Coil Winding Supplies-CHRZANOWSKI | 1864.8 | 1864.8 | 0 |  | 31 - Magnetic Diagnostics | Job: 3101 Magnetic Diagnostics | 521.4 | 595 | 73.6
14 - Modular Coils Total |  | 33577.396 | 33691.396 | 114 |  | 36 - Edge and Divertor Diagnostics | Job: 3601 - Edge and Divertor | 45.6 | 9.4 | -36.2
15 - Structures | Job: 1501 - Structures Design- DAHLGREN | 217.1 | 217.1 | 0 |  | 38 - Electron Beam (EB) Mapping | Job: 3801 - Electron Beam Mapping | 206.2 | 29.6 | -176.6
| Job:1550 - Structures Procurement -DAHLGREN | 1171.7 | 1171.7 | 0 |  | 41 - AC Power | Job: 4101 - AC Power-RAMAKRISHNAN | 424 | 357 | -67
15 - Structures Total |  | 1388.8 | 1388.8 | 0 |  | 44 - Control and protection Systems | Job: 4401 - Control & Protection-RAMAKRISHNAN | 1346 | 987.9 | -358.1
16 - Coil Services | Job: 1601 - Coil Services Design-WILLIAMSON | 1137.8 | 1137.8 | 0 |  | 45 - Power System Design and Integration | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 1055.1 | 1062.9 | 7.8
17 - Cryostat and Base Support Structure | Job: 1751 - Cryostat Procurement | 540.5 | 540.5 | 0 |  | 46 - FCPC Building Modifications | Job: 4601 - FCPC Bldg Mods-RAMAKRISHNAN | 1.3 | 1.3 | 0
| Job: 1752 - Base Support Structure Procurement | 230.9 | 230.9 | 0 |  | 51 - TCP/IP Infrastructure Systems | Job: 5101 - TCP/IP Infrastructure Systems | 280.4 | 150.8 | -129.6
| Job:1701-Cryost&Base Sprt Strct Dsn-GETTLEFINGER | 681.41 | 730.41 | 49 | 49 | 52 - Central Instrumentation & Control | 5201 - I&C Systems | 530.1 | 138.1 | -392
17 - Cryostat and Base Support Structure Total |  | 1452.81 | 1501.81 | 49 |  | 53 - Data Acquisition & Facility Computing | 5301 - Data Acquisition | 329.1 | 149.8 | -179.3
18 - Field Period Assembly | Job: 1801-Field Period Assly -CHRZANOWSKI (ORNL) | 64.7 | 64.7 | 0 |  | 54 - Facility Timing & Synchronization | Job: 5401 - Facility Timing & | 195.8 | 82.2 | -113.6
| Job: 1802 - FP Assy Oversight&Support-VIOLA | 1507.5 | 1507.5 | 0 |  | 55 - Real Time Plasma & Power Supply Control Sys | 5501 - Real Time Control System | 179.3 | 93.6 | -85.7
| Job: 1803- FP Assy Toolg/Constructability-BROWN | 1372.4 | 1372.4 | 0 |  | 56 - Central Safety Interlock Systems | Job: 5601 - Central Safety Interlock Systems | 325.5 | 129.4 | -196.1
| Job: 1804-FP Assy Measurement | 585.9 | 585.9 | 0 |  | 58 - Central I&C management and Integration | Job: 5801 -Central I&C Integr | 33.4 | 57.8 | 24.4
| Job:1810 - Field Period Assembly-VIOLA | 2392.2 | 2392.2 | 0 |  | 61 - Water Systems | Job:6101 - Water Systems | 92.3 | 13.8 | -78.5
18 - Field Period Assembly Total |  | 5922.7 | 5922.7 | 0 |  | 62 - Cryogenic Systems | Job: 6201 - Cryogenic Systems | 455 | 455 | 0
19 - Stellarator Core Management and Integration | Job: 1901 - Stellarator Core Mngtt&Integr-NELSON | 2771.3 | 2771.3 | 0 |  | 63 - Utility Systems | Job: 6301 - Utility Systems | 106.9 | 106.9 | 0
WBS 1 Subtotal |  | 61388.836 | 61551.836 | 163
21 - Fueling Systems | Job: 2001-VPS Gas& Cond Sys Oversight-BLANCHARD | 62.9 | 62.9 | 0 |  | 65 - Facility Systems Integration | Job: 6163 - Facility Systems Support FY04 | 15 | 15 | 0
| Job: 2101 - Fueling Systems | 60.1 | 60.1 | 0 |  |  | Job: 6501 - Facility Systems Integration-DUDEK | 9.4 | 9.4 | 0
21 - Fueling Systems Total |  | 123 | 123 | 0 |  | 65 - Facility Systems Integration Total |  | 24.4 | 24.4 | 0
22 - Torus Vacuum Pumping Systems | Job: 2001-VPS Gas& Cond Sys Oversight-BLANCHARD |  |  | 0 |  | 71 - Shield Wall Seismic Modifications | Job: 7101 - Shield Wall Modif | 32.2 | 32.6 | 0.4
| Job: 2201 - Vacuum Pumping Systems | 76.1 | 76.1 | 0 |  | 72 - Control Room Refurbishment | Job: 7201 - Control Room Walls&Floors-PERRY | 9.1 |  | -9.1
22 - Torus Vacuum Pumping Systems |  | 76.1 | 76.1 | 0 |  | 73 - Platform Design & Fabrication | Job: 7301 - Platform Design & | 109.1 | 112.9 | 3.8
25 - Neutral Beam Injection System | Job: 2501 - Neutral Beam Refurbishment-STEVENSON | 285 | 285 | 0 |  | 74 - Machine Assembly Planning and Oversight | Job: 7401 - TC Prep & Mach Assy Planning-PERRY | 1753.1 | 1773 | 19.9
WBS 2 Subtotal |  | 484.1 | 484.1 | 0
31 - Magnetic Diagnostics | Job: 3101 Magnetic Diagnostics | 518.59 | 518.59 | 0 |  | 75 - Test Cell and Basement Assembly Operations | 7501 - Construction Support Crew | 1063.4 | 935.4 | -128
36 - Edge and Divertor Diagnostics | Job: 3601 - Edge and Divertor | 9.4 | 9.4 | 0 |  |  | 7502 - Test Cell Facility Preparations | 74.6 |  | -74.6
38 - Electron Beam (EB) Mapping | Job: 3801 - Electron Beam Mapping | 29.6 | 29.6 | 0 |  |  | 7503 - Machine Assembly | 1275.3 | 1269.6 | -5.7
39 - Diagnostics Integration | Job: 3901 - Diagnostics sys Integration-JOHNSON | 345.3 | 345.3 | 0 |  | 75 - Test Cell and Basement Assembly Operations Total |  | 2413.3 | 2205 | -208.3
WBS 3 Subtotal |  | 902.89 | 902.89 | 0
41 - AC Power | Job: 4101 - AC Power-RAMAKRISHNAN | 357.4 | 357.4 | 0 |  | 76 - Tooling Design & Fabrication | Job: 7601 - Tooling Design & Fabrication | 237.8 | 237.6 | -0.2
43 - DC Systems | Job: 4301 - DC Systems-RAMAKRISHNAN | 620.07 | 725.57 | 105.5 |  | 81 - Project Management and Control | Job: 8101 - Project Management & Control-NEILSON | 3937.1 | 3897.3 | -39.8
44 - Control and protection Systems | Job: 4401 - Control & Protection-RAMAKRISHNAN | 965.01 | 988.51 | 23.5 |  |  | Job: 8102 - NCSX MIE Management ORNL-LYON | 515.8 | 537.5 | 21.7
45 - Power System Design and Integration | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 1057.5 | 1062.5 | 5 | 134 |  | Job: 8998 - Allocations | 1608.4 | 1656.4 | 48
46 - FCPC Building Modifications | Job: 4601 - FCPC Bldg Mods-RAMAKRISHNAN | 1.3 | 1.3 | 0 |  | 81 - Project Management and Control Total |  | 6061.3 | 6091.2 | 29.9
WBS 4 Subtotal |  | 3001.28 | 3135.28 | 134
51 - TCP/IP Infrastructure Systems | Job: 5101 - TCP/IP Infrastructure Systems | 150.8 | 150.8 | 0 |  | 82 - Project Engineering | Job: 8202 - Engr Mgmt & Sys Eng Support-REIERSEN | 2789.4 | 2963.9 | 174.5
52 - Central Instrumentation & Control | 5201 - I&C Systems | 138.1 | 138.1 | 0 |  |  | Job: 8203 - Design Integration-BROWN | 959.5 | 1017 | 57.5
53 - Data Acquisition & Facility Computing | 5301 - Data Acquisition | 149.8 | 149.8 | 0 |  |  | Job: 8204 - Systems Analysis-BROOKS | 724.5 | 1018.1 | 293.6
54 - Facility Timing & Synchronization | Job: 5401 - Facility Timing & | 82.2 | 82.2 | 0 |  |  | Job: 8205 - Dimensional Control Coordination | 428.7 | 487.1 | 58.4
55 - Real Time Plasma & Power Supply Control Sys | 5501 - Real Time Control System | 93.6 | 93.6 | 0 |  | 82 - Project Engineering Total |  | 4902.1 | 5486.1 | 584
56 - Central Safety Interlock Systems | Job: 5601 - Central Safety Interlock Systems | 129.4 | 129.4 | 0 |  | 84 - Project Physics | Job: 8401 - Project Physcis-ZARNSTORFF | 324.1 | 324.6 | 0.5
58 - Central I&C management and Integration | Job: 5801 -Central I&C Integr | 57.8 | 57.8 | 0 |  |  | Job: 8402 - Project Physics MIE ORNL-LYON | 145.9 | 146.5 | 0.6
WBS 5 Subtotal |  | 801.7 | 801.7 | 0
61 - Water Systems | Job:6101 - Water Systems | 13.8 | 13.8 | 0 |  | 84 - Project Physics Total |  | 470 | 471.1 | 1.1
62 - Cryogenic Systems | Job: 6201 - Cryogenic Systems | 455 | 455 | 0 |  | 85 - Integrated Systems Testing | Job: 8501 - Integrated Systems Testing | 1197.6 | 806.9 | -390.7
63 - Utility Systems | Job: 6301 - Utility Systems | 106.9 | 106.9 | 0 |  | Contingency | Contingency | 8720 | 7921.4 | -798.6
65 - Facility Systems Integration | Job: 6163 - Facility Systems Support FY04 | 15 | 15 | 0 |  | DCMA | DCMA | 75 | 75 | 0
| Job: 6501 - Facility Systems Integration-DUDEK | 9.4 | 9.4 | 0 |  | Misc Adjustments | Rate Adjustments FY06 |  | -406 | -406
65 - Facility Systems Integration Total |  | 24.4 | 24.4 | 0 |  | Grand Total |  | 92401.4 | 92401.4 | 0
WBS 6 Subtotal |  | 600.1 | 600.1 | 0
71 - Shield Wall Seismic Modifications | Job: 7101 - Shield Wall Modif | 32.6 | 32.6 | 0
72 - Control Room Refurbishment | Job: 7201 - Control Room Walls&Floors-PERRY |  |  | 0
73 - Platform Design & Fabrication | Job: 7301 - Platform Design & | 112.9 | 112.9 | 0
74 - Machine Assembly Planning and Oversight | Job: 7401 - TC Prep & Mach Assy Planning-PERRY | 1773 | 1773 | 0
75 - Test Cell and Basement Assembly Operations | 7501 - Construction Support Crew | 935.4 | 935.4 | 0
| 7502 - Test Cell Facility Preparations |  |  | 0
| 7503 - Machine Assembly | 1269.6 | 1269.6 | 0
75 - Test Cell and Basement Assembly Operations Total |  | 2205 | 2205 | 0
76 - Tooling Design & Fabrication | Job: 7601 - Tooling Design & Fabrication | 237.6 | 237.6 | 0
WBS 7 Subtotal |  | 4361.1 | 4361.1 | 0
81 - Project Management and Control | Job: 8101 - Project Management & Control-NEILSON | 3868.05 | 3868.05 | 0
| Job: 8102 - NCSX MIE Management ORNL-LYON | 531.4 | 531.4 | 0
| Job: 8998 - Allocations | 1608.41 | 1608.41 | 0
81 - Project Management and Control Total |  | 6007.86 | 6007.86 | 0
82 - Project Engineering | Job: 8202 - Engr Mgmt & Sys Eng Support-REIERSEN | 2919.46 | 2919.46 | 0
| Job: 8203 - Design Integration-BROWN | 1020.78 | 1020.78 | 0
| Job: 8204 - Systems Analysis-BROOKS | 902.254 | 902.254 | 0
| Job: 8205 - Dimensional Control Coordination | 487.1 | 487.1 | 0
82 - Project Engineering Total |  | 5329.594 | 5329.594 | 0
84 - Project Physics | Job: 8401 - Project Physcis-ZARNSTORFF | 324.6 | 324.6 | 0
| Job: 8402 - Project Physics MIE ORNL-LYON | 146.5 | 146.5 | 0
84 - Project Physics Total |  | 471.1 | 471.1 | 0
85 - Integrated Systems Testing | Job: 8501 - Integrated Systems Testing | 806.9 | 806.9 | 0
WBS 8 Subtotal |  | 12615.454 | 12615.454 | 0
Misc Adjustments | Rate Adjustments FY06 | 0 | 0 | 0
DCMA | DCMA | 75 | 75 | 0
| Subtotal | 84230.46 | 84527.46 | 297
| Contingency | 8171 | 7874 | -297
Grand Total |  | 92401.46 | 92401.46 | 0
297

## P3
WBS II | Job | Budget | ecp44
11 - In-Vessel Components | Job: 1101 - Limiter Adv Conc/Prel Dsn-**CLOSED* | 0.1 | ecp44
12 - Vacuum Vessel Systems | Job: 1201 - Vacuum Vessel Prelim Dsn-**CLOSED** | 424.4 | ecp44
12 - Vacuum Vessel Systems | Job: 1202 - Vacuum Vessel R&D | 1770.2 | ecp44
12 - Vacuum Vessel Systems | Job: 1206 - VV Field Weld Joint R&D-**CLOSED** | 15.6 | ecp44
12 - Vacuum Vessel Systems | Job: 1203 - Vacuum Vessel Final Dsn-GORANSON | 1270.3 | ecp44
12 - Vacuum Vessel Systems | Job:1204-VV Sys Procurements (non VVSA)-DUDEK | 603.5 | ecp44
12 - Vacuum Vessel Systems | Job: 1250 - Vacuum Vessel Fabrication-VIOLA | 5727.5 | ecp44
13 - Conventional Coils | Job: 1301 - TF Design-KALISH | 965.8 | ecp44
13 - Conventional Coils | Job: 1350 TF Coil Fab Preparation-CHRZANOWSKI | 560.3 | ecp44
13 - Conventional Coils | Job: 1351 - TF Coil Fabr Supplies-KALISH | 469.6 | ecp44
13 - Conventional Coils | Job: 1361 - TF Fabrication-KALISH | 2016.6 | ecp44
13 - Conventional Coils | Job: 1302 - PF Design -KALISH | 132 | ecp44
13 - Conventional Coils | Job: 1352 - PF Coil Procurement-KALISH | 794.6 | ecp44
13 - Conventional Coils | Job: 1354 - Trim Coil Design &Procurement-KALISH | 103.4 | ecp44
13 - Conventional Coils | Job: 1303 -Centrol Solenoid Support Dsn-DAHLGREN | 116.9 | ecp44
13 - Conventional Coils | Job: 1353 - CS Structure Procurement-DAHLGREN | 120.9 | ecp44
13 - Conventional Coils | Job: 1355 - WBS 13 I&C Proc & | 91.2 | ecp44
14 - Modular Coils | Job: 1401 - Mod Coil Prel.Dsn**CLOSED** | 304 | ecp44
14 - Modular Coils | Job: 1402 - Mod.Coil Analyses**CLOSED** | 239.1 | ecp44
14 - Modular Coils | Job:1404-MCWF R&D & 1st Prod Casting**CLOSED** | 2543.5 | ecp44
14 - Modular Coils | Job: 1413 -MCWF Fracture Analysis-**CLOSED** | 27.8 | ecp44
14 - Modular Coils | Job: 1405-Mod Coil Winding R&D Prep-**CLOSED** | 168.1 | ecp44
14 - Modular Coils | Job: 1407 -Mod Coil Winding Facility-**CLOSED** | 2571.4 | ecp44
14 - Modular Coils | Job: 1412 - Complete Winding Facilities-*CLOSED* | 541 | ecp44
14 - Modular Coils | Job: 1406 - Mod. Coil Winding | 2263.6 | ecp44
14 - Modular Coils | Job: 1410 MC Twisted Racetrack Fabr-**CLOSED** | 1050 | ecp44
14 - Modular Coils | Job: 1409 - Coil Test Stand-GETTELFINGER*CLOSED* | 861.7 | ecp44
14 - Modular Coils | Job: 1415 Dim Cntrl Testing-RAFTOPOLOUS*CLOSED** | 23.9 | ecp44
14 - Modular Coils | Job: 1419-Winding Fac. Mods-CHRZANOWSKI*CLOSED* | 55.2 | ecp44
14 - Modular Coils | Job: 1403 - Modular Coil Final Design-WILLIAMSON | 3496.6 | ecp44
14 - Modular Coils | Job: 1416-Mod Coil Type A&B Final Dsn-WILLIAMSON | 446.2 | ecp44
14 - Modular Coils | Job:1408-Mod Coil Winding Supplies-CHRZANOWSKI | 1885.8 | ecp44
14 - Modular Coils | Job: 1411-MCWF Fabrication S005242-HEITZENROEDER | 9581.3 | ecp44
14 - Modular Coils | Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 6262.4 | ecp44
14 - Modular Coils | Job: 1414 Coil Testing-Gettelfinger | 452.3 | ecp44
14 - Modular Coils | Job: 1421-Mod Coil Interface Hardware-WILLIAMSON | 916.9 | ecp44
15 - Structures | Job: 1501 - Structures Design- DAHLGREN | 217.1 | ecp44
15 - Structures | Job:1550 - Structures Procurement -DAHLGREN | 1171.7 | ecp44
16 - Coil Services | Job: 1601 - Coil Services Design-WILLIAMSON | 1137.8 | ecp44
17 - Cryostat and Base Support Structure | Job:1701-Cryost&Base Sprt Strct Dsn-GETTLEFINGER | 727.9 | ecp44
17 - Cryostat and Base Support Structure | Job: 1751 - Cryostat Procurement | 540.5 | ecp44
17 - Cryostat and Base Support Structure | Job: 1752 - Base Support Structure Procurement | 230.9 | ecp44
18 - Field Period Assembly | Job: 1801-Field Period Assly -CHRZANOWSKI (ORNL) | 64.7 | ecp44
18 - Field Period Assembly | Job: 1802 - FP Assy Oversight&Support-VIOLA | 1507.5 | ecp44
18 - Field Period Assembly | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1372.4 | ecp44
18 - Field Period Assembly | Job: 1804-FP Assy Measurement | 585.9 | ecp44
18 - Field Period Assembly | Job:1810 - Field Period Assembly-VIOLA | 2392.2 | ecp44
19 - Stellarator Core Management and Integration | Job: 1901 - Stellarator Core Mngtt&Integr-NELSON | 2771.3 | ecp44
21 - Fueling Systems | Job: 2001-VPS Gas& Cond Sys Oversight-BLANCHARD | 62.9 | ecp44
21 - Fueling Systems | Job: 2101 - Fueling Systems | 60.1 | ecp44
22 - Torus Vacuum Pumping Systems | Job: 2201 - Vacuum Pumping Systems | 76.1 | ecp44
25 - Neutral Beam Injection System | Job: 2501 - Neutral Beam Refurbishment-STEVENSON | 285 | ecp44
31 - Magnetic Diagnostics | Job: 3101 Magnetic Diagnostics | 595 | ecp44
36 - Edge and Divertor Diagnostics | Job: 3601 - Edge and Divertor | 9.4 | ecp44
38 - Electron Beam (EB) Mapping | Job: 3801 - Electron Beam Mapping | 29.6 | ecp44
39 - Diagnostics Integration | Job: 3901 - Diagnostics sys Integration-JOHNSON | 338.8 | ecp44
41 - AC Power | Job: 4101 - AC Power-RAMAKRISHNAN | 357 | ecp44
43 - DC Systems | Job: 4301 - DC Systems-RAMAKRISHNAN | 733.2 | ecp44
44 - Control and protection Systems | Job: 4401 - Control & Protection-RAMAKRISHNAN | 987.9 | ecp44
45 - Power System Design and Integration | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 1062.9 | ecp44
46 - FCPC Building Modifications | Job: 4601 - FCPC Bldg Mods-RAMAKRISHNAN | 1.3 | ecp44
51 - TCP/IP Infrastructure Systems | Job: 5101 - TCP/IP Infrastructure Systems | 150.8 | ecp44
52 - Central Instrumentation & Control | 5201 - I&C Systems | 138.1 | ecp44
53 - Data Acquisition & Facility Computing | 5301 - Data Acquisition | 149.8 | ecp44
54 - Facility Timing & Synchronization | Job: 5401 - Facility Timing & | 82.2 | ecp44
55 - Real Time Plasma & Power Supply Control Sys | 5501 - Real Time Control System | 93.6 | ecp44
56 - Central Safety Interlock Systems | Job: 5601 - Central Safety Interlock Systems | 129.4 | ecp44
58 - Central I&C management and Integration | Job: 5801 -Central I&C Integr | 57.8 | ecp44
61 - Water Systems | Job:6101 - Water Systems | 13.8 | ecp44
62 - Cryogenic Systems | Job: 6201 - Cryogenic Systems | 455 | ecp44
63 - Utility Systems | Job: 6301 - Utility Systems | 106.9 | ecp44
65 - Facility Systems Integration | Job: 6163 - Facility Systems Support FY04 | 15 | ecp44
65 - Facility Systems Integration | Job: 6501 - Facility Systems Integration-DUDEK | 9.4 | ecp44
71 - Shield Wall Seismic Modifications | Job: 7101 - Shield Wall Modif | 32.6 | ecp44
73 - Platform Design & Fabrication | Job: 7301 - Platform Design & | 112.9 | ecp44
74 - Machine Assembly Planning and Oversight | Job: 7401 - TC Prep & Mach Assy Planning-PERRY | 1773 | ecp44
75 - Test Cell and Basement Assembly Operations | 7501 - Construction Support Crew | 935.4 | ecp44
75 - Test Cell and Basement Assembly Operations | 7503 - Machine Assembly | 1269.6 | ecp44
76 - Tooling Design & Fabrication | Job: 7601 - Tooling Design & Fabrication | 237.6 | ecp44
81 - Project Management and Control | Job: 8101 - Project Management & Control-NEILSON | 3897.3 | ecp44
81 - Project Management and Control | Job: 8102 - NCSX MIE Management ORNL-LYON | 537.5 | ecp44
82 - Project Engineering | Job: 8202 - Engr Mgmt & Sys Eng Support-REIERSEN | 2963.9 | ecp44
82 - Project Engineering | Job: 8203 - Design Integration-BROWN | 1017 | ecp44
82 - Project Engineering | Job: 8204 - Systems Analysis-BROOKS | 1018.1 | ecp44
82 - Project Engineering | Job: 8205 - Dimensional Control Coordination | 487.1 | ecp44
84 - Project Physics | Job: 8401 - Project Physcis-ZARNSTORFF | 324.6 | ecp44
84 - Project Physics | Job: 8402 - Project Physics MIE ORNL-LYON | 146.5 | ecp44
85 - Integrated Systems Testing | Job: 8501 - Integrated Systems Testing | 806.9 | ecp44
81 - Project Management and Control | Job: 8998 - Allocations | 1656.4 | ecp44
Contingency | Contingency | 7921.4 | ecp44
DCMA | DCMA | 75 | ecp44
Misc Adjustments | Rate Adjustments FY06 | -406 | ecp44 | 92401.4
11 - In-Vessel Components | Job: 1101 - Limiter Adv Conc/Prel Dsn-**CLOSED* | 0.1 | ecp43
12 - Vacuum Vessel Systems | Job: 1201 - Vacuum Vessel Prelim Dsn-**CLOSED** | 424.4 | ecp43
12 - Vacuum Vessel Systems | Job: 1202 - Vacuum Vessel R&D | 1770.2 | ecp43
12 - Vacuum Vessel Systems | Job: 1206 - VV Field Weld Joint R&D-**CLOSED** | 15.6 | ecp43
12 - Vacuum Vessel Systems | Job: 1203 - Vacuum Vessel Final Dsn-GORANSON | 1100.8 | ecp43
12 - Vacuum Vessel Systems | Job:1204-VV Sys Procurements (non VVSA)-GORANSON | 458.7 | ecp43
12 - Vacuum Vessel Systems | Job: 1250 - Vacuum Vessel Fabrication-VIOLA | 5669.8 | ecp43
13 - Conventional Coils | Job: 1301 - TF Design-KALISH | 946.3 | ecp43
13 - Conventional Coils | Job: 1350 TF Coil Fab Preparation-CHRZANOWSKI | 743.2 | ecp43
13 - Conventional Coils | Job: 1351 - TF Coil Fabr Supplies-KALISH | 870.4 | ecp43
13 - Conventional Coils | Job: 1361 - TF Fabrication-CHRZANOWSKI | 659.9 | ecp43
13 - Conventional Coils | Job: 1302 - PF and CS Design -KALISH | 230.1 | ecp43
13 - Conventional Coils | Job: 1352 - PF Coil Procurement-KALISH | 895.9 | ecp43
13 - Conventional Coils | Job: 1353 - CS Structure Procurement-KALISH | 265.8 | ecp43
13 - Conventional Coils | Job: 1354 - Trim Coil Procurement-KALISH | 103.4 | ecp43
13 - Conventional Coils | Job: 1355 - WBS 13 I&C Proc & | 91.2 | ecp43
14 - Modular Coils | Job: 1401 - Mod Coil Prel.Dsn**CLOSED** | 304 | ecp43
14 - Modular Coils | Job: 1402 - Mod.Coil Analyses**CLOSED** | 239.1 | ecp43
14 - Modular Coils | Job:1404-MCWF R&D & 1st Prod Casting**CLOSED** | 2543.5 | ecp43
14 - Modular Coils | Job: 1413 -MCWF Fracture Analysis-**CLOSED** | 28.2 | ecp43
14 - Modular Coils | Job: 1405-Mod Coil Winding R&D Prep-**CLOSED** | 168.1 | ecp43
14 - Modular Coils | Job: 1407 -Mod Coil Winding Facility-**CLOSED** | 2546 | ecp43
14 - Modular Coils | Job: 1412 - Complete Winding Facilities-*CLOSED* | 537.4 | ecp43
14 - Modular Coils | Job: 1406 - Mod. Coil Winding | 2246.6 | ecp43
14 - Modular Coils | Job: 1410 MC Twisted Racetrack Fabr-**CLOSED** | 1050.2 | ecp43
14 - Modular Coils | Job: 1409 - Coil Test Stand-GETTELFINGER*CLOSED* | 915.9 | ecp43
14 - Modular Coils | Job: 1415 Dim Cntrl Testing-RAFTOPOLOUS*CLOSED** | 23.9 | ecp43
14 - Modular Coils | Job: 1419-Winding Fac. Mods-CHRZANOWSKI*CLOSED* | 48 | ecp43
14 - Modular Coils | Job: 1403 - Modular Coil Final Design-WILLIAMSON | 3156.2 | ecp43
14 - Modular Coils | Job: 1416-Mod Coil Type A&B Final Dsn-WILLIAMSON | 756.3 | ecp43
14 - Modular Coils | Job:1408-Mod Coil Winding Supplies-CHRZANOWSKI | 1811.9 | ecp43
14 - Modular Coils | Job: 1411-MCWF Fabrication S005242-HEITZENROEDER | 9597.8 | ecp43
14 - Modular Coils | Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 5155.8 | ecp43
14 - Modular Coils | Job: 1414 Coil Testing-Gettelfinger | 295.2 | ecp43
14 - Modular Coils | Job: 1421-Mod Coil Interface Hardware-WILLIAMSON | 830.1 | ecp43
15 - Structures | Job: 1501 - Structures Design- Kalish | 208.4 | ecp43
15 - Structures | Job:1550 - Structures Procurement -KALISH | 1177.7 | ecp43
16 - Coil Services | Job: 1601 - Coil Services Design-WILLIAMSON | 1135 | ecp43
17 - Cryostat and Base Support Structure | Job:1701-Cryost&Base Sprt Strct Dsn-GETTLEFINGER | 681 | ecp43
17 - Cryostat and Base Support Structure | Job: 1751 - Cryostat Procurement | 540.5 | ecp43
17 - Cryostat and Base Support Structure | Job: 1752 - Base Support Structure Procurement | 311.4 | ecp43
18 - Field Period Assembly | Job: 1801-Field Period Assly -CHRZANOWSKI (ORNL) | 60.8 | ecp43
18 - Field Period Assembly | Job: 1802 - FP Assy Oversight&Support-VIOLA | 1485 | ecp43
18 - Field Period Assembly | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1050.6 | ecp43
18 - Field Period Assembly | Job: 1804-FP Assy Measurement | 486.4 | ecp43
18 - Field Period Assembly | Job:1810 - Field Period Assembly-VIOLA | 2199.2 | ecp43
19 - Stellarator Core Management and Integration | Job: 1901 - Stellarator Core Mngtt&Integr-NELSON | 2767 | ecp43
21 - Fueling Systems | Job: 2101 - Fueling Systems | 88.1 | ecp43
22 - Torus Vacuum Pumping Systems | Job: 2001-VPS Gas& Cond Sys Oversight-BLANCHARD | 63.7 | ecp43
22 - Torus Vacuum Pumping Systems | Job: 2201 - Vacuum Pumping Systems | 355.2 | ecp43
25 - Neutral Beam Injection System | Job: 2501 - Neutral Beam Refurbishment-STEVENSON | 284.4 | ecp43
31 - Magnetic Diagnostics | Job: 3101 Magnetic Diagnostics | 521.4 | ecp43
36 - Edge and Divertor Diagnostics | Job: 3601 - Edge and Divertor | 45.6 | ecp43
38 - Electron Beam (EB) Mapping | Job: 3801 - Electron Beam Mapping | 206.2 | ecp43
39 - Diagnostics Integration | Job: 3901 - Diagnostics sys Integration-JOHNSON | 345.3 | ecp43
41 - AC Power | Job: 4101 - AC Power-RAMAKRISHNAN | 424 | ecp43
43 - DC Systems | Job: 4301 - DC Systems-RAMAKRISHNAN | 528.5 | ecp43
44 - Control and protection Systems | Job: 4401 - Control & Protection-RAMAKRISHNAN | 1346 | ecp43
45 - Power System Design and Integration | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 1055.1 | ecp43
46 - FCPC Building Modifications | Job: 4601 - FCPC Bldg Mods-RAMAKRISHNAN | 1.3 | ecp43
51 - TCP/IP Infrastructure Systems | Job: 5101 - TCP/IP Infrastructure Systems | 280.4 | ecp43
52 - Central Instrumentation & Control | 5201 - I&C Systems | 530.1 | ecp43
53 - Data Acquisition & Facility Computing | 5301 - Data Acquisition | 329.1 | ecp43
54 - Facility Timing & Synchronization | Job: 5401 - Facility Timing & | 195.8 | ecp43
55 - Real Time Plasma & Power Supply Control Sys | 5501 - Real Time Control System | 179.3 | ecp43
56 - Central Safety Interlock Systems | Job: 5601 - Central Safety Interlock Systems | 325.5 | ecp43
58 - Central I&C management and Integration | Job: 5801 -Central I&C Integr | 33.4 | ecp43
61 - Water Systems | Job:6101 - Water Systems | 92.3 | ecp43
62 - Cryogenic Systems | Job: 6201 - Cryogenic Systems | 455 | ecp43
63 - Utility Systems | Job: 6301 - Utility Systems | 106.9 | ecp43
65 - Facility Systems Integration | Job: 6163 - Facility Systems Support FY04 | 15 | ecp43
65 - Facility Systems Integration | Job: 6501 - Facility Systems Integration-DUDEK | 9.4 | ecp43
71 - Shield Wall Seismic Modifications | Job: 7101 - Shield Wall Modif | 32.2 | ecp43
72 - Control Room Refurbishment | Job: 7201 - Control Room Walls&Floors-PERRY | 9.1 | ecp43
73 - Platform Design & Fabrication | Job: 7301 - Platform Design & | 109.1 | ecp43
74 - Machine Assembly Planning and Oversight | Job: 7401 - TC Prep & Mach Assy Planning-PERRY | 1753.1 | ecp43
75 - Test Cell and Basement Assembly Operations | 7501 - Construction Support Crew | 1063.4 | ecp43
75 - Test Cell and Basement Assembly Operations | 7502 - Test Cell Facility Preparations | 74.6 | ecp43
75 - Test Cell and Basement Assembly Operations | 7503 - Machine Assembly | 1275.3 | ecp43
76 - Tooling Design & Fabrication | Job: 7601 - Tooling Design & Fabrication | 237.8 | ecp43
81 - Project Management and Control | Job: 8101 - Project Management & Control-NEILSON | 3937.1 | ecp43
81 - Project Management and Control | Job: 8102 - NCSX MIE Management ORNL-LYON | 515.8 | ecp43
82 - Project Engineering | Job: 8202 - Engr Mgmt & Sys Eng Support-REIERSEN | 2789.4 | ecp43
82 - Project Engineering | Job: 8203 - Design Integration-BROWN | 959.5 | ecp43
82 - Project Engineering | Job: 8204 - Systems Analysis-BROOKS | 724.5 | ecp43
82 - Project Engineering | Job: 8205 - Dimensional Control Coordination | 428.7 | ecp43
84 - Project Physics | Job: 8401 - Project Physcis-ZARNSTORFF | 324.1 | ecp43
84 - Project Physics | Job: 8402 - Project Physics MIE ORNL-LYON | 145.9 | ecp43
85 - Integrated Systems Testing | Job: 8501 - Integrated Systems Testing | 1197.6 | ecp43
81 - Project Management and Control | Job: 8998 - Allocations | 1608.4 | ecp43
Contingency | Contingency | 8720 | ecp43
DCMA | DCMA | 75 | ecp43