## Fab Project
WBS 121 Vacuum Vessel Assembly | [10 empty] | 17 |  | Duration of activity per fiscal year (weeks)
Labor
| Activity Title |  | Manhours | FY2003 $$ | Labor Type | Start Date Month/Yr | End Date Month/Yr | Comments |  |  |  | duration (weeks) | 2002-10-01 | 2003-10-01 | 2004-10-01 | 2005-10-01 | 2006-10-01 | 2007-10-01 | 2008-10-01
Preliminary Design (Title I)
|  | ( 57% of design schedule) | 68.4179 |  | EAEM | 2003-04-01 | 2003-10-09 | PPPL Engineer |  |  |  | 27.2857 | 26.1429 | 1.1429 | 0 | 0 | 0 | 0 |  | 57.0149 | 57.01% | of design is preliminary design
|  |  | 0 |  | EADM | 2003-04-01 | 2003-10-09 | PPPL Designer |  |  |  | 27.2857 | 26.1429 | 1.1429 | 0 | 0 | 0 | 0
|  |  | 2394.1707 |  | ORNL Eng | 2003-04-01 | 2003-10-09 | Composite of ORNL Engineer / Designer |  |  |  | 27.2857 | 26.1429 | 1.1429 | 0 | 0 | 0 | 0
|  |  | 91.2239 |  | ORNL Phys. | 2003-04-01 | 2003-10-09 | Composite of ORNL Physics / scientific |  |  |  | 27.2857 | 26.1429 | 1.1429 | 0 | 0 | 0 | 0
|  |  | 0 |  | PPPL Phys. | 2003-04-01 | 2003-10-09 | PPPL Physics/scientific |  |  |  | 27.2857 | 26.1429 | 1.1429 | 0 | 0 | 0 | 0
Final Design (Title II)
|  | ( 43% of design schedule) | 51.5821 |  | EAEM | 2003-10-09 | 2004-03-01 | PPPL Engineer |  |  |  | 20.5714 | 0 | 20.5714 | 0 | 0 | 0 | 0 |  | 42.9851 | 42.99% | of design schedule is final design
|  |  | 0 |  | EADM | 2003-10-09 | 2004-03-01 | PPPL Designer |  |  |  | 20.5714 | 0 | 20.5714 | 0 | 0 | 0 | 0
|  |  | 1805.0293 |  | ORNL Eng | 2003-10-09 | 2004-03-01 | Composite of ORNL Engineer / Designer |  |  |  | 20.5714 | 0 | 20.5714 | 0 | 0 | 0 | 0
|  |  | 68.7761 |  | ORNL Phys. | 2003-10-09 | 2004-03-01 | Composite of ORNL Physicist |  |  |  | 20.5714 | 0 | 20.5714 | 0 | 0 | 0 | 0
|  |  | 0 |  | PPPL Phys. | 2003-10-09 | 2004-03-01 | PPPL Physics/scientific |  |  |  | 20.5714 | 0 | 20.5714 | 0 | 0 | 0 | 0
Lab R&D labor
|  |  | 488 |  | EAEM | 2003-04-01 | 2003-10-09 | PPPL Engineer |  |  |  | 27.2857 | 26.1429 | 1.1429 | 0 | 0 | 0 | 0
|  |  | 0 |  | EADM | 2003-04-01 | 2003-10-09 | PPPL Designer |  |  |  | 27.2857 | 26.1429 | 1.1429 | 0 | 0 | 0 | 0
|  |  | 1271.2 |  | ORNL Eng | 2003-04-01 | 2003-10-09 | Composite of ORNL Engineer / Designer |  |  |  | 27.2857 | 26.1429 | 1.1429 | 0 | 0 | 0 | 0
|  |  | 408 |  | EASM | 2003-04-01 | 2003-10-09 | PPPL monthly support |  |  |  | 27.2857 | 26.1429 | 1.1429 | 0 | 0 | 0 | 0
|  |  | 0 |  | EMTB | 2003-04-01 | 2003-10-09 | PPPL Technician |  |  |  | 27.2857 | 26.1429 | 1.1429 | 0 | 0 | 0 | 0
Lab Fab/Assembly/Installation (Title III)
|  |  | 348.3429 |  | EAEM | 2004-05-01 | 2006-10-01 | PPPL Engineer |  |  |  | 126.1429 | 0 | 21.8571 | 52.1429 | 52.1429 | 0 | 0
|  |  | 0 |  | EADM | 2004-05-01 | 2006-10-01 | PPPL Designer |  |  |  | 126.1429 | 0 | 21.8571 | 52.1429 | 52.1429 | 0 | 0
|  |  | 938.5143 |  | ORNL Eng | 2004-05-01 | 2006-10-01 | Composite of ORNL Engineer / Designer |  |  |  | 126.1429 | 0 | 21.8571 | 52.1429 | 52.1429 | 0 | 0
|  |  | 0 |  | EASM | 2004-05-01 | 2006-10-01 | PPPL monthly support |  |  |  | 126.1429 | 0 | 21.8571 | 52.1429 | 52.1429 | 0 | 0
|  |  | 0 |  | EMTB | 2004-05-01 | 2006-10-01 | PPPL Technician |  |  |  | 126.1429 | 0 | 21.8571 | 52.1429 | 52.1429 | 0 | 0
Labor | [11 empty] | R&D labor cost = |  | 280720
[12 empty] | total R&D costs |  | 1036170
Manhours per fiscal year by labor category
Level of Effort |  |  |  | FY2003 | FY2004 | FY2005 | FY2006 | FY2007 | FY2008 | TOTAL
| PPPL Engineer |  | EAEM | 533.1124 | 135.2459 | 143.9922 | 143.9922 | 0 | 0 | 956.3429 |  | 146320.4571 | 153 | per hour
| PPPL Designer |  | EADM | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 100 | per hour
| Composite of ORNL Engineer / Designer |  | ORNL Eng | 3511.8474 | 2121.1718 | 387.9476 | 387.9476 | 0 | 0 | 6408.9143 |  | 833158.8571 | 130 | per hour
| PPPL monthly support |  | EASM | 390.911 | 17.089 | 0 | 0 | 0 | 0 | 408 |  | 40800 | 100 | per hour
| PPPL Technician |  | EMTB | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 73 | per hour
| Composite of ORNL Physics / scientific |  | ORNL Phy | 87.403 | 72.597 | 0 | 0 | 0 | 0 | 160 |  | 25600 | 160 | per hour
| PPPL Physics/scientific |  | PPPL Phy | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 141 | per hour
[12 empty] | 1364.3429 | 187120.4571 | PPPL
[12 empty] | 6568.9143 | 858758.8571 | ORNL
M&S Costs
| Activity Title |  |  | FY2003 $$ |  | Comment
Manufacturing Development (R&D)
|  | Purchased Design Services |  | 0
|  | Procured Hardware/Material |  | 755450
|  | Profit |  | 0 |  | included in hardware estimate
|  | total, manf/dev (R&D) |  | 755450 |  | w/o G&A
Procured Hardware/Material
|  | vacuum vessel assembly |  | 2729354.5
|  | NBI port duct assemblies |  | 144360
|  | Profit |  | 0 |  | included in hardware estimate
|  | total, procured hdwe/matl. |  | 2873714.5 |  | w/o G&A
| Purchased Design Services |  |  | 0 |  | no purchased services anticipated
| Procured Installation/Assembly Costs |  |  | 0 |  | All installation and assembly costs are included in WBS 7
Other Costs
| Activity Title |  |  | FY2003 $$ |  | Comment
| Travel |  |  | 24000 |  | at least one trip per month is expected for two years
Summary Costs
| Activity Title |  | Manhours | FY2003 $$ |  | Comment
Labor
| PPPL Effort |  | 1364.3429 | 187120.4571 |  | Assumed rates: |  | EASM | 100 $/hr
| ORNL effort |  | 6568.9143 | 858758.8571 |  | EAEM | 153 $/hr | EMTB | 73 $/hr
|  | subtotal, labor | 7933.2571 | 1045879.3143 |  | EADM | 100 $/hr | PPPL Phys | 141 $/hr
[6 empty] | ORNL Eng | 130 $/hr | ORNL Phys | 160 $/hr
M&S, Other
| Manufacturing Development (R&D) |  |  | 755450
| Procured Hardware/Material |  |  | 2873714.5
| Purchased Design Services |  |  | 0
| Procured Installation/Assembly Costs |  |  | 0
| Travel |  |  | 24000
|  | subtotal, M&S |  | 3653164.5
| G&A |  |  | 355952.5 |  | 25% | on all purchased materials, subcontracts, travel
[6 empty] | 557338.625 | G&A adjustment on large procurement
| Subtotal without contingency |  |  | 5054996.3143
| Contingency |  |  | 2021998.5257 |  | 40% | Overall on this WBS
| Total cost |  |  | 7076994.84

## Other Costs
|  | 1808-NCSX-1701 | [5 empty] | XX represents the 2 digit WBS code
| Activity Title |  | Manhours | FY2002 $$ | Labor Type | Start Date Month/Year | End Date Month/Year | Comments
Level of Effort | [7 empty] | Research Prep Activities
FY2003
[5 empty] | RMRM3 |  |  | SAMPLE - Put in specific labor type
[5 empty] | FCEM |  |  | SAMPLE - Put in specific labor type
FY2004
FY2005
FY2006
FY2007
Research Planning/Preparations
FY2003
[5 empty] | RMRM3 |  |  | SAMPLE - Put in specific labor type
[5 empty] | FCEM |  |  | SAMPLE - Put in specific labor type
FY2004
FY2005
FY2006
FY2007
Operational Spares
M&S Costs
Manufacturing Development
Purchased Design Services
|  | Procured Hardware/Material | [5 empty] | Include any M&S carried over from FY2002
| Procured Hardware/Material | [6 empty] | Identify each procurement over $100K individually
Purchased Design Services
Procured Installation/Assembly Costs
Other Costs
Travel
FY2003
[5 empty] | RMRM3 |  |  | SAMPLE - Put in specific labor type
[5 empty] | FCEM |  |  | SAMPLE - Put in specific labor type
FY2004
FY2005
FY2006
FY2007
Allocations (WBS 81 only)
Instructions for Completing Form
(1) One form for each 3 digit WBS element (e.g., 111, 121, 452, etc.) => if no 3 digit WBS, use 2 digit WBS (e.g., 81, 82, 84)
(2) For Lab labor, provide estimate in manhours => provide estimate by specific labor type.
(3) For M&S, provide estimate in FY2002 direct dollars if procured by PPPL, or in fully loaded dollars if procured by ORNL
(4) Start and end date provided in month/year format => March/2003

## Engr
WBS 121 Vacuum Vessel Assembly
Engineering, Title I, II and III
Description:
This effort covers all Title I, II, and III engineering for the vacuum vessel assembly, which includes the vessel shell, port extensions, spacer flange and seals. Two R&D subcontracts will be awarded for fabrication demonstration and development, followed by procurement of the final vessel by fixed price subcontract. All Title III engr associated with installation is included in WBS 7. |  |  |  |  | Labor category
[5 empty] | total fraction | EAEM |  | EADM |  | ORNL Eng |  | ORNL Physics |  | PPPL Physics
| multiplier | unit | no. | hours |  | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
Title I, II design
Pro-E models (avg) | 24 | hrs/model | 48 | 1152 | 1 | 0 | 0 | 0 | 0 | 1 | 1152 | 0 | 0 | 0 | 0
assy dwgs | 40 | hrs/dwg | 20 | 800 | 1 | 0 | 0 | 0 | 0 | 1 | 800 | 0 | 0 | 0 | 0
Detail drawings | 20 | hrs/dwg | 54 | 1080 | 1 | 0 | 0 | 0 | 0 | 1 | 1080 | 0 | 0 | 0 | 0
installation dwg | 8 | hrs/dwg | 30 | 240 | 1 | 0 | 0 | 0 | 0 | 1 | 240 | 0 | 0 | 0 | 0
cooling schematic | 20 | hrs/dwg | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
electrical schematic | 0 | hrs/dwg | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
I&C schematic | 20 | hrs/dwg | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
stress analysis | 50 | hrs/calc | 4 | 200 | 1 | 0 | 0 | 0 | 0 | 1 | 200 | 0 | 0 | 0 | 0
thermal analysis | 60 | hrs/calc | 2 | 120 | 1 | 0 | 0 | 0 | 0 | 1 | 120 | 0 | 0 | 0 | 0
special analysis (electromagnetics) | 160 | hrs/calc | 1 | 160 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 160 | 0 | 0
procurement/fab specifications | 160 | hrs/spec | 1 | 160 | 1 | 0.75 | 120 | 0 | 0 | 0.25 | 40 | 0 | 0 | 0 | 0
preliminary and final design reviews | 80 | hrs/rev | 2 | 160 | 1 | 0 | 0 | 0 | 0 | 1 | 160 | 0 | 0 | 0 | 0
meetings/reporting/presentations | 10% | % of tot | 4072 | 407.2 | 1 | 0 | 0 | 0 | 0 | 1 | 407.2 | 0 | 0 | 0 | 0
subtotal |  |  |  | 4479.2 |  |  | 120 |  | 0 |  | 4199.2 |  | 160 |  | 0
[5 empty] | total fraction | EAEM |  | EASM |  | EADM |  | ORNL Eng
Title III | [5 empty] | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
vendor oversight, inspection | 8 | hrs/wk | 72.5714 | 580.5714 | 1 | 0.5 | 290.2857 | 0 | 0 | 0 | 0 | 0.5 | 290.2857
Disposition of deviation requests and non-conformances | 4 | hrs/wk | 72.5714 | 290.2857 | 1 | 0.2 | 58.0571 | 0 | 0 | 0 | 0 | 0.8 | 232.2286
As-built drawings | 4 | hrs/dwg | 104 | 416 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 416
subtotal |  |  |  | 1286.8571 |  |  | 348.3429 |  | 0 |  | 0 |  | 938.5143
Schedule assumptions | start | duration (weeks) | end
Title I Design | 2003-04-01 | 27.2857 | 2003-10-09
Title II Design | 2003-10-09 | 20.5714 | 2004-03-01 |  |  | FDR | 2004-01-01
Procurement | 2004-05-01 | 72.5714 | 2005-09-21
In-house fab / sub-assy | 2005-10-01 | 21.5714 | 2006-03-01
Installation / final assembly | 2006-03-01 | 30.5714 | 2006-10-01
Notes and worksheets
vacuum vessel design
| total | vessel torus, flanges, and port reinforcements | port extensions | joint spacer flange | bolts, seals, and other hardware
Pro-E models | 48 | 5 | 37 | 3 | 3
assy dwgs | 20 | 3 | 13 | 2 | 2 | 13 port extension/flange assemblies
Detail drawings | 54 | 6 | 36 | 6 | 6 | half period vessel shell, flanges, ports x 13 types, seals, spacer, etc.
installation dwg | 30 | 15 | 13 | 1 | 1
cooling schematic | 0 | 0 | 0 |  |  | Included in WBS 123
electrical schematic | 0 | 0
I&C schematic | 0 | 0 | 0 |  |  | included in WBS 125
stress analysis | 4 | 1 | 1 | 1 | 1 | Analyses include stress and buckling from normal and disruption loads
thermal analysis | 2 | 1 | 1
special analysis | 1 | 1 |  |  |  | em disruption analysis
procurement specifications | 1 |  |  |  |  | one procurement specification for vessel assembly
preliminary and final design reviews | 2 |  |  |  |  | two standard reviews
meetings/reporting/presentations | 15%
Formulas:
multiplier = [no., row above]

## R&D
WBS 121 Vacuum Vessel Assembly
R&D
Description:
This effort covers all R&D necessary for developing and demonstrating the fabrication process for the vacuum vessel. This R&D will be performed by two vendors, preferrably proposing different fabrication approaches, after which a fixed price subcontract will be let for the production vessel assembly. In addition, PPPL will perform in-house R&D to verify the field joint welding joint design and process.
Summary
Purchased Design Services
None expected | EAEM
subtotal | 0 |  | w/o G&A
Procured Hardware/Material
vacuum vessel R&D contracts | 751245 |  | allocations for 2 forms from different vendors
weld test materials | 4200 | 4200
subtotal | 755450 |  | w/o G&A
Subcontractor labor rates:
design rate: | 120 | per hour
fab rate | 60 | per hour
inspection/technician rate | 80 | per hour
Labor category
R&D design | [5 empty] | total fraction | EAEM |  | EADM |  | ORNL Eng |  | EASM |  | Vendor
|  | unit | no. | hours |  |  | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
Task
Pro-E models | 24 | hrs/model | 11 | 264 |  | 1 | 0 | 0 | 0 | 0 | 1 | 264 | 0 | 0 | 0 | 0
assy dwgs | 20 | hrs/dwg | 5 | 100 |  | 1 | 0 | 0 | 0 | 0 | 1 | 100 | 0 | 0 | 0 | 0
Detail drawings | 16 | hrs/dwg | 12 | 192 |  | 1 | 0 | 0 | 0 | 0 | 1 | 192 | 0 | 0 | 0 | 0
installation dwg | 0 | hrs/dwg | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
cooling schematic | 0 | hrs/dwg | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
electrical schematic | 0 | hrs/dwg | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
I&C schematic | 0 | hrs/dwg | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
special analysis | 0 | hrs/calc | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
procurement specifications | 80 | hrs/spec | 1 | 80 |  | 1 | 0 | 0 | 0 | 0 | 1 | 80 | 0 | 0 | 0 | 0
vendor shop drawings | 0 | hrs/dwg | 0 | 0 |  | 1 | [8 empty] | 1 | 0
vendor part programming | 0 | hrs/model | 0 | 0 |  | 1 | [8 empty] | 1 | 0
vendor misc engineering | 0% | % of tot | 0 | 0 |  | 1 | [8 empty] | 1 | 0
preliminary and final design reviews | 80 | hrs/rev | 1 | 80 |  | 1 | 0 | 0 | 0 | 0 | 1 | 80 | 0 | 0 | 0 | 0
meetings/reporting/presentations | 20% | % of tot | 716 | 143.2 |  | 1 | 0 | 0 | 0 | 0 | 1 | 143.2 | 0 | 0 | 0 | 0
subtotal |  |  |  | 859.2 |  |  |  | 0 |  | 0 |  | 859.2 |  | 0 |  | 0
[5 empty] | total fraction |  | EAEM |  | EADM |  | ORNL Eng |  | EASM, EMSM |  | EMTB
[7 empty] | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
R&D Tasks and Title III (see notes)
Procurement assistance | 8 | hrs/wk | 12 | 96 |  | 1 | 0.5 | 48 | 0 | 0 | 0.5 | 48 | 0 | 0 | 0 | 0
Vendor surveillance, oversight | 8 | hrs/wk | 52 | 416 |  | 1 | 0.5 | 208 | 0 | 0 | 0.5 | 208 | 0 | 0 | 0 | 0
Disposition of deviation requests and non-conformances | 4 | hrs/wk | 52 | 208 |  | 1 | 0.25 | 52 | 0 | 0 | 0.75 | 156 | 0 | 0 | 0 | 0
subtotal |  |  |  | 720 |  |  |  | 308 |  | 0 |  | 412 |  | 0 |  | 0
Schedule assumptions | start | duration (weeks) | end
Bid and award | 2003-07-10 | 12 | 2003-10-02
Vessel R&D | 2003-10-02 | 52 | 2004-09-30
Notes and worksheets
Vessel R&D Engineering Design
|  | vessel torus, flanges, and port reinforcements | typical port extension | VV joint prototype
Pro-E models | 11 | 5 | 2 | 4
assy dwgs | 5 | 3 | 1 | 1
Detail drawings | 12 | 6 | 2 | 4
installation dwg | 0 | 0 | 0
cooling schematic | 0 | 0 | 0
electrical schematic | 0 | 0
I&C schematic | 0 | 0 | 0
special analysis | 0 | 0 | 0
procurement specifications | 1 | 1
vendor shop drawings | 0 |  |  |  |  | included in R&D estimate
vendor part programming | 0 |  |  |  |  | included in R&D estimate
vendor misc engineering | 0 |  |  |  |  | included in R&D estimate
preliminary and final design reviews | 0
meetings/reporting/presentations | 20%
Vacuum vessel fabrication R&D
Cost derived from subcontracts with two vendors
| Composite Cost Estimate |  |  | vendor 1 |  |  | vendor 2
| (FY-03$) | ($) |  | (FY-03$) |  |  | (FY-03$) | ($)
R&D studies by vendors
PVVS
R&D budget allotted, 2 vendors | 751245
0
R&D Schedule | 12 months | 12 months |  | 10 months |  |  | 12 months
123635
178378
|  |  |  | 70399 |  |  | 137055
|  |  |  | 27931 |  |  | 128545
|  | PVVS |  | 400343 |  |  | 265600
|  | PVVS, total |  | 665943
|  | total contract |  | 400343 |  |  | 350902
751245
Notes:
Desired results include demonstration of forming the torus shell, port stub reinforcements, and port extension to torus welding.
Vessel weld joint R&D
Modify two prototype vessel segments to include weld joint
materials | qty | unit | unit cost | cost
flange material | 100 | lb | 5 | 500
welding consumables | 1 | lot | 1000 | 1000
seals, misc. | 1 | ea | 2500 | 2500
thermocouples | 4 | ea | 50 | 200
subtotal, materials |  |  |  | 4200
labor
[6 empty] | total fraction | EAEM |  | EASM, EMSM |  | EMTB |  | EADM
[7 empty] | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
machining segments | 40 | hr | 2 | 80 |  | 1 | 0 | 0 | 1 | 80 | 0 | 0 | 0 | 0
machining flanges | 40 | hr | 2 | 80 |  | 1 | 0 | 0 | 1 | 80 | 0 | 0 | 0 | 0
welding flanges | 40 | hr | 2 | 80 |  | 1 | 0 | 0 | 1 | 80 | 0 | 0 | 0 | 0
perform test welds | 80 | hr | 1 | 80 |  | 1 | 0 | 0 | 1 | 80 | 0 | 0 | 0 | 0
install thermocouples | 2 | hr | 4 | 8 |  | 1 | 0 | 0 | 1 | 8 | 0 | 0 | 0 | 0
measure distortion, temperature on backside of weld, etc. | 160 | hr/coil | 1 | 160 |  | 1 | 0.5 | 80 | 0.5 | 80 | 0 | 0 | 0 | 0
supervision /QA | 80 | hr/coil | 1 | 80 |  | 1 | 1 | 80 | 0 | 0 | 0 | 0 | 0 | 0
reports | 20 | hours | 1 | 20 |  | 1 | 1 | 20 | 0 | 0 | 0 | 0 | 0 | 0
subtotal |  |  |  | 588 |  |  |  | 180 |  | 408 |  | 0 |  | 0
Formulas:
start = [no.]-[unit]*7
no. = [start, row below]

## M&S
WBS 121 Vacuum Vessel Assembly
Materials and Subcontracts (M&S)
Description:
This effort covers procurement of the vacuum vessel assembly by fixed price subcontract. The vessel assembly includes the torus, port extensions, spacers, and miscellaneous hardware. The R&D is costed separately.
[5 empty] | outside engr rate = | 120 | $ per hour
Purchased parts: |  |  |  |  | outside fab rate = | 60 | $ per hour
Vacuum vessel assembly | 2729354.5 | see notes below |  |  | outside inspection/technician rate = | 80 | $ per hour
NBI port duct extensions | 144360
subtotal, purchased parts | 2873714.5
Worksheet:
Vacuum Vessel Assembly
Cost derived from budgetary estimates by two vendors as part of R&D subcontracts
| Composite Cost Estimate |  | vendor 1 | vendor 2
| (FY-02$) | ($) | (FY-02$) | (FY-02$)
#REF!
Vessel assembly, 3 field periods
Vendor design, tooling, fixtures |  |  | 875000 | 1203483
Forming or casting vessel, extensions |  |  | 1673000 | 1677673
Welding |  |  | incl above | incl above
Machining / polishing |  |  | incl above | incl above
Assy,Inspection, leak check, seals |  |  | incl above | incl above
shipping |  |  |  | 29553
Production Total | 2729354.5 |  | 2548000 | 2910709
Production Schedule |  | 24 months | 12 months
|  | 36 months | 2004-04-01
2005-03-25
NBI port duct extension
This element consists of the port duct, seals, and all cover flanges
weight of shell assembly, with ports | 1400 | lbs
$/lb for fabrication | 25 | $/lb
subtotal, fab cost shell | 35000
no. of ports | 12 | ea
8" o.d. flange, 6" tube | 225 | $/ea
8" o.d. rotatable cover flange | 125 | $/ea
no. of 8" ports | 7 | ea
cost for 8" ports | 2450
14.5" x 16.5" flange with tube | 1500 | $/ea
blank 14.5" x 16.5" flanges | 1000 | $/ea
no. of 14.5" x 16.5" ports | 2 | ea
cost for 14.5" x 16.5" ports | 5000
16.5" o.d. flange, 14" tube | 1000 | $/ea
16.5" o.d. rotatable cover flange | 710 | $/ea
no. of 16.5" ports | 2 | ea
cost for 16.5" ports | 3420
large square flange cover | 2000
seals for diamond flange and square flange | 250
subtotal, ports | 13120
total, each nbi port duct extension | 48120
no. of nbi duct extensions | 3
total, 3 extensions | 144360
Note on C25: Bob Simmons: Assumed 2 vendors

## Fab_assy
WBS 121 Vacuum Vessel Assembly
In-house Fabrication and Assembly
Description:
No fabrication and assembly is associated with this WBS |  |  |  |  | Labor category
[5 empty] | total fraction | EAEM |  | EASM, EMSM |  | EMTB |  | EADM
| multiplier | unit | no. | hours |  | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
Fab operations summary
| 0 | hrs/lot | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 0 | hrs/line | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | hrs / coil | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
subtotal |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0
[5 empty] | total fraction | EAEM |  | EASM, EMSM |  | EMTB |  | EADM
Assembly operations summary | [5 empty] | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
| 0 | hr/lot | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| 0 | hr/lot | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | hr/coil | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | hours | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
subtotal |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0

## Installation
WBS 121 Vacuum Vessel Assembly
Installation
This element is not part of the WBS 1 scope of work
notes: | get name of federal QA outfit from Rod Templon's email