## Fab Project
WBS 123 Vacuum Vessel Heating and Cooling system | [10 empty] | 17 |  | Duration of activity per fiscal year (weeks)
Labor
| Activity Title |  | Manhours | FY2003 $$ | Labor Type | Start Date Month/Yr | End Date Month/Yr | Comments |  |  |  | duration (weeks) | 2002-10-01 | 2003-10-01 | 2004-10-01 | 2005-10-01 | 2006-10-01 | 2007-10-01 | 2008-10-01
Preliminary Design (Title I)
|  | ( 33% of design schedule) | 10 |  | EAEM | 2005-12-05 | 2006-01-16 | PPPL Engineer |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0 |  | 33.3333 | 33.33% | of design is preliminary design
|  |  | 0 |  | EADM | 2005-12-05 | 2006-01-16 | PPPL Designer |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | 97.0667 |  | ORNL Eng | 2005-12-05 | 2006-01-16 | Composite of ORNL Engineer / Designer |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | 0 |  | ORNL Phys. | 2005-12-05 | 2006-01-16 | Composite of ORNL Physics / scientific |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | 0 |  | PPPL Phys. | 2005-12-05 | 2006-01-16 | PPPL Physics/scientific |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
Final Design (Title II)
|  | ( 67% of design schedule) | 20 |  | EAEM | 2006-01-16 | 2006-04-10 | PPPL Engineer |  |  |  | 12 | 0 | 0 | 0 | 12 | 0 | 0 |  | 66.6667 | 66.67% | of design schedule is final design
|  |  | 0 |  | EADM | 2006-01-16 | 2006-04-10 | PPPL Designer |  |  |  | 12 | 0 | 0 | 0 | 12 | 0 | 0
|  |  | 194.1333 |  | ORNL Eng | 2006-01-16 | 2006-04-10 | Composite of ORNL Engineer / Designer |  |  |  | 12 | 0 | 0 | 0 | 12 | 0 | 0
|  |  | 0 |  | ORNL Phys. | 2006-01-16 | 2006-04-10 | Composite of ORNL Physicist |  |  |  | 12 | 0 | 0 | 0 | 12 | 0 | 0
|  |  | 0 |  | PPPL Phys. | 2006-01-16 | 2006-04-10 | PPPL Physics/scientific |  |  |  | 12 | 0 | 0 | 0 | 12 | 0 | 0
Lab R&D labor
|  |  | 0 |  | EAEM | 2005-12-05 | 2006-01-16 | PPPL Engineer |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | 0 |  | EADM | 2005-12-05 | 2006-01-16 | PPPL Designer |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | 0 |  | ORNL Eng | 2005-12-05 | 2006-01-16 | Composite of ORNL Engineer / Designer |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | 0 |  | EASM | 2005-12-05 | 2006-01-16 | PPPL monthly support |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | 0 |  | EMTB | 2005-12-05 | 2006-01-16 | PPPL Technician |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
Lab Fab/Assembly/Installation (Title III)
|  |  | 7.6 |  | EAEM | 2006-04-10 | 2007-01-01 | PPPL Engineer |  |  |  | 38 | 0 | 0 | 0 | 24.8571 | 13.1429 | 0
|  |  | 0 |  | EADM | 2006-04-10 | 2007-01-01 | PPPL Designer |  |  |  | 38 | 0 | 0 | 0 | 24.8571 | 13.1429 | 0
|  |  | 48.4 |  | ORNL Eng | 2006-04-10 | 2007-01-01 | Composite of ORNL Engineer / Designer |  |  |  | 38 | 0 | 0 | 0 | 24.8571 | 13.1429 | 0
|  |  | 0 |  | EASM | 2006-04-10 | 2007-01-01 | PPPL monthly support |  |  |  | 38 | 0 | 0 | 0 | 24.8571 | 13.1429 | 0
|  |  | 0 |  | EMTB | 2006-04-10 | 2007-01-01 | PPPL Technician |  |  |  | 38 | 0 | 0 | 0 | 24.8571 | 13.1429 | 0
Labor
Manhours per fiscal year by labor category
Level of Effort |  |  |  | FY2003 | FY2004 | FY2005 | FY2006 | FY2007 | FY2008 | TOTAL
| PPPL Engineer |  | EAEM | 0 | 0 | 0 | 34.9714 | 2.6286 | 0 | 37.6 |  | 5752.8 | 153 | per hour
| PPPL Designer |  | EADM | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 100 | per hour
| Composite of ORNL Engineer / Designer |  | ORNL Eng | 0 | 0 | 0 | 322.8602 | 16.7398 | 0 | 339.6 |  | 44148 | 130 | per hour
| PPPL monthly support |  | EASM | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 100 | per hour
| PPPL Technician |  | EMTB | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 73 | per hour
| Composite of ORNL Physics / scientific |  | ORNL Phy | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 160 | per hour
| PPPL Physics/scientific |  | PPPL Phy | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 141 | per hour
[12 empty] | 37.6 | 5752.8 | PPPL
[12 empty] | 339.6 | 44148 | ORNL
M&S Costs
| Activity Title |  |  | FY2003 $$ |  | Comment
Manufacturing Development (R&D)
|  | Purchased Design Services |  | 0
|  | Procured Hardware/Material |  | 0
|  | Profit |  | 0 |  | included in hardware estimate
|  | total, manf/dev (R&D) |  | 0 |  | w/o G&A
Procured Hardware/Material
|  | tubing, manifolds, headers |  | 246560
|  | Profit |  | 0 |  | included in hardware estimate
|  | total, procured hdwe/matl. |  | 246560 |  | w/o G&A
| Purchased Design Services |  |  | 0 |  | no purchased services anticipated
| Procured Installation/Assembly Costs |  |  | 0 |  | All installation and assembly costs are included in WBS 7
Other Costs
| Activity Title |  |  | FY2003 $$ |  | Comment
| Travel |  |  | 0 |  | no trips are anticipated for this WBS
Summary Costs
| Activity Title |  | Manhours | FY2003 $$ |  | Comment
Labor
| PPPL Effort |  | 37.6 | 5752.8 |  | Assumed rates: |  | EASM | 100 $/hr
| ORNL effort |  | 339.6 | 44148 |  | EAEM | 153 $/hr | EMTB | 73 $/hr
|  | subtotal, labor | 377.2 | 49900.8 |  | EADM | 100 $/hr | PPPL Phys | 141 $/hr
[6 empty] | ORNL Eng | 130 $/hr | ORNL Phys | 160 $/hr
M&S, Other
| Manufacturing Development (R&D) |  |  | 0
| Procured Hardware/Material |  |  | 246560
| Purchased Design Services |  |  | 0
| Procured Installation/Assembly Costs |  |  | 0
| Travel |  |  | 0
|  | subtotal, M&S |  | 246560
| G&A |  |  | 61640 |  | 25% | on all purchased materials, subcontracts, travel
| Subtotal without contingency |  |  | 358100.8
| Contingency |  |  | 114592.256 |  | 32% | Overall on this WBS
| Total cost |  |  | 472693.056

## Other Costs
|  | 1808-NCSX-1701 | [5 empty] | XX represents the 2 digit WBS code
| Activity Title |  | Manhours | FY2002 $$ | Labor Type | Start Date Month/Year | End Date Month/Year | Comments
Level of Effort | [7 empty] | Research Prep Activities
FY2003
[5 empty] | RMRM3 |  |  | SAMPLE - Put in specific labor type
[5 empty] | FCEM |  |  | SAMPLE - Put in specific labor type
FY2004
FY2005
FY2006
FY2007
Research Planning/Preparations
FY2003
[5 empty] | RMRM3 |  |  | SAMPLE - Put in specific labor type
[5 empty] | FCEM |  |  | SAMPLE - Put in specific labor type
FY2004
FY2005
FY2006
FY2007
Operational Spares
M&S Costs
Manufacturing Development
Purchased Design Services
|  | Procured Hardware/Material | [5 empty] | Include any M&S carried over from FY2002
| Procured Hardware/Material | [6 empty] | Identify each procurement over $100K individually
Purchased Design Services
Procured Installation/Assembly Costs
Other Costs
Travel
FY2003
[5 empty] | RMRM3 |  |  | SAMPLE - Put in specific labor type
[5 empty] | FCEM |  |  | SAMPLE - Put in specific labor type
FY2004
FY2005
FY2006
FY2007
Allocations (WBS 81 only)
Instructions for Completing Form
(1) One form for each 3 digit WBS element (e.g., 111, 121, 452, etc.) => if no 3 digit WBS, use 2 digit WBS (e.g., 81, 82, 84)
(2) For Lab labor, provide estimate in manhours => provide estimate by specific labor type.
(3) For M&S, provide estimate in FY2002 direct dollars if procured by PPPL, or in fully loaded dollars if procured by ORNL
(4) Start and end date provided in month/year format => March/2003

## Engr
WBS 123 Vacuum Vessel Heating and Cooling system
Engineering, Title I, II and III
Description:
This effort covers all Title I, II, and III engineering for the vacuum vessel heating and cooling distribution system, which includes the cooling lines wrapped on the vessel shell and port extensions and the necessary manifolding and connections to interface with the ex-cryostat helium supply system. The heating and cooling system will be fabricated in-house by PPPL. All Title III engr associated with installation is included in WBS 7. |  |  |  |  | Labor category
[5 empty] | total fraction | EAEM |  | EADM |  | ORNL Eng |  | ORNL Physics |  | PPPL Physics
| multiplier | unit | no. | hours |  | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
Title I, II design
Pro-E models (avg) | 4 | hrs/model | 26 | 104 | 1 | 0 | 0 | 0 | 0 | 1 | 104 | 0 | 0 | 0 | 0
assy dwgs | 8 | hrs/dwg | 4 | 32 | 1 | 0 | 0 | 0 | 0 | 1 | 32 | 0 | 0 | 0 | 0
Detail drawings | 4 | hrs/dwg | 1 | 4 | 1 | 0 | 0 | 0 | 0 | 1 | 4 | 0 | 0 | 0 | 0
installation dwg | 8 | hrs/dwg | 4 | 32 | 1 | 0 | 0 | 0 | 0 | 1 | 32 | 0 | 0 | 0 | 0
cooling schematic | 20 | hrs/dwg | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
electrical schematic | 0 | hrs/dwg | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
I&C schematic | 20 | hrs/dwg | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
stress analysis | 40 | hrs/calc | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
thermal analysis | 40 | hrs/calc | 1 | 40 | 1 | 0 | 0 | 0 | 0 | 1 | 40 | 0 | 0 | 0 | 0
special analysis (electromagnetics) | 160 | hrs/calc | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
procurement/fab specifications | 40 | hrs/spec | 1 | 40 | 1 | 0.75 | 30 | 0 | 0 | 0.25 | 10 | 0 | 0 | 0 | 0
preliminary and final design reviews | 40 | hrs/rev | 1 | 40 | 1 | 0 | 0 | 0 | 0 | 1 | 40 | 0 | 0 | 0 | 0
meetings/reporting/presentations | 10% | % of tot | 292 | 29.2 | 1 | 0 | 0 | 0 | 0 | 1 | 29.2 | 0 | 0 | 0 | 0
subtotal |  |  |  | 321.2 |  |  | 30 |  | 0 |  | 291.2 |  | 0 |  | 0
[5 empty] | total fraction | EAEM |  | EASM |  | EADM |  | ORNL Eng
Title III | [5 empty] | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
vendor oversight, inspection | 0 | hrs/wk | 12 | 0 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0
Disposition of deviation requests and non-conformances | 1 | hrs/wk | 38 | 38 | 1 | 0.2 | 7.6 | 0 | 0 | 0 | 0 | 0.8 | 30.4
As-built drawings | 2 | hrs/dwg | 9 | 18 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 18
subtotal |  |  |  | 56 |  |  | 7.6 |  | 0 |  | 0 |  | 48.4
Schedule assumptions | start | duration (weeks) | end
Title I Design | 2005-12-05 | 6 | 2006-01-16
Title II Design | 2006-01-16 | 12 | 2006-04-10
Procurement | 2006-04-10 | 12 | 2006-07-03
In-house fab / sub-assy | 2006-07-03 | 12 | 2006-09-25
Installation / final assembly | 2006-09-25 | 14 | 2007-01-01
Notes and worksheets
vessel thermal insulation blankets
| total | vessel torus, | port extensions | NBI duct | connecting pipes | headers
Pro-E models | 26 | 10 | 13 | 2 | 1 | 2 | models for each type of tube, manifold, and header
assy dwgs | 4 | 1 | 1 | 1 | 1 | 1
Detail drawings | 1 | 0 | 0 | 0 | 1 | 2 | drawings of each manifold and header
installation dwg | 4 | 1 | 1 | 1 | 1 |  | on drawing per type of part
cooling schematic | 0
electrical schematic | 0
I&C schematic | 0
stress analysis | 0
thermal analysis | 1 | 1 |  |  |  |  | one analysis for all cooling lines
special analysis | 0
procurement specifications | 1 | [5 empty] | one procurement spec for the tubing, piping and fittings
preliminary and final design reviews | 1 | [5 empty] | one review for all the plumbing
meetings/reporting/presentations | 15%
Formulas:
multiplier = [no.]-[unit]*7
no. = [multiplier, row below]

## R&D
WBS 123 Vacuum Vessel Heating and Cooling system
R&D
Description:
No R&D is expected for this WBS element
Summary
Purchased Design Services
0
subtotal | 0 |  | w/o G&A
Procured Hardware/Material
0
subtotal | 0 |  | w/o G&A
Subcontractor labor rates:
design rate: | 0 | per hour
fab rate | 0 | per hour
inspection/technician rate | 0 | per hour
Labor category
R&D design | [5 empty] | total fraction | EAEM |  | EADM |  | ORNL Eng |  | EASM |  | Vendor
|  | unit | no. | hours |  |  | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
Task
Pro-E models | 24 | hrs/model | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
assy dwgs | 20 | hrs/dwg | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
Detail drawings | 24 | hrs/dwg | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
installation dwg | 0 | hrs/dwg | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
cooling schematic | 0 | hrs/dwg | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
electrical schematic | 0 | hrs/dwg | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
I&C schematic | 0 | hrs/dwg | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
special analysis | 0 | hrs/calc | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
procurement specifications | 80 | hrs/spec | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
vendor shop drawings | 0 | hrs/dwg | 0 | 0 |  | 1 | [8 empty] | 1 | 0
vendor part programming | 0 | hrs/model | 0 | 0 |  | 1 | [8 empty] | 1 | 0
vendor misc engineering | 0% | % of tot | 0 | 0 |  | 1 | [8 empty] | 1 | 0
preliminary and final design reviews | 80 | hrs/rev | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
meetings/reporting/presentations | 20% | % of tot | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
subtotal |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
[5 empty] | total fraction |  | EAEM |  | EADM |  | ORNL Eng |  | EASM, EMSM |  | EMTB
[7 empty] | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
R&D Tasks and Title III (see notes)
Procurement assistance | 0 | hrs/wk | 12 | 0 |  | 1 | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0
Vendor surveillance, oversight | 0 | hrs/wk | 52 | 0 |  | 1 | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0
Disposition of deviation requests and non-conformances | 0 | hrs/wk | 52 | 0 |  | 1 | 0.25 | 0 | 0 | 0 | 0.75 | 0 | 0 | 0 | 0 | 0
subtotal |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Schedule assumptions | start | duration (weeks) | end
Bid and award | 2003-07-10 | 12 | 2003-10-02
Vessel R&D | 2003-10-02 | 52 | 2004-09-30
Notes and worksheets
[17 empty] | 130 | yen/$
[17 empty] | 1.14 | euro/$
[17 empty] | 10.6383 | SWE/$
Formulas:
start = [no.]-[unit]*7
no. = [start, row below]

## M&S
WBS 123 Vacuum Vessel Heating and Cooling system
Materials and Subcontracts (M&S)
Description:
This effort covers procurement of materials for the vacuum vessel heating and cooling system lines, manifolding and headers by fixed price subcontract.
Assumptions:
outside engr rate = | 120 | $ per hour
outside fab rate = | 60 | $ per hour
outside inspection/technician rate = | 80 | $ per hour
Purchased parts:
tracing on VV shell - material | 44160 | see notes below
Forming tubes | 60800
heaters on port extensions | 31920
heaters on NBI ports | 4560
header piping, connections | 75120
electrical breaks | 30000
subtotal, purchased parts | 246560
Worksheet:
tracing on VV shell - material
avg poloidal perimeter of torus | 16 | ft
spacing of tubes | 0.5 | ft
approx no. poloidal loops/period | 64
cost of tubing | 10 | per foot, Inco 600
cost per field period | 10240
spacing of tube hold-downs | 0.8 | ft
no. of hold downs/period | 640 | connections
cost per holddown | 5 | double tube clamp
cost per field period | 3200
hydraulic conn's per pol. loop | 2
no. of hydraulic conn/period | 128
matl. cost per connection | 10 | swagelock connection
cost per field period | 1280
total matl cost for torus tracing | 44160
Forming tubes to shape
cost for translating tube shape to NC language | 1000 | per tube shape
no of shapes | 16
cost for forming tubes to shape | 200 | per tube
no. of tubes formed for each shape | 14 | includes two spares per shape
total cost for forming tubes | 60800
heaters on port extensions
no. of heaters per port | 2
no. of port ext. | 28 | per period
cost of heaters | 150 | per heater, avg
cost per field period | 8400
no. of heater hold-downs/port | 20
no. of hold downs/period | 560 | connections
cost per holddown | 2 | simple spot-welded strip
cost per field period | 1120
electrical conn's per port ext | 2
no. of elec conn/period | 56
matl. cost per connection | 20
cost per field period | 1120
total matl cost for port ext.tracing | 31920
heaters on NBI ports
no. of heaters per port | 8
no. of port ext. | 1 | per period
cost of heaters | 150 | per heater, avg
cost per field period | 1200
no. of heater hold-downs/port | 80
no. of hold downs/period | 80 | connections
cost per holddown | 2 | simple spot-welded strip
cost per field period | 160
electrical conn's per port ext | 8
no. of elec conn/period | 8
matl. cost per connection | 20
cost per field period | 160
total matl cost for NBI port tracing | 4560
Headers for cooling lines
Assume 4 pairs of half-ring headers for the VV heating piping that ride with and are installed at the vertical ports of each of the field periods
no. of lines per header | 16
approx dia of header | 1.6 | in
length of each header pair | 4 | ft
no of headers | 8 | per period | a | = | pi*r^2
cost of tubing | 45 | per foot, Inco 600 | r | = | sqrt(a/pi)
cost per field period | 180 | per header
cost per connection | 5 | per nipple
cost of nipples | 640 | per header
welding consumables | 50 | per header
no. connections for supply piping | 1 | per header
cost per connection | 100 | per header
material cost per header | 970 | per header
forming labor | 4 | hours
machining labor | 8 | hours
welding labor | 20 | 1 hour per connection + 2 hours each end
inspection | 4 | hours/header
total hours per header | 36 | hours
labor cost per header | 2160
total cost per header | 3130
total procured cost for manifolds | 75120 | all 3 field periods
Electrical breaks
breaks per manifold | 1
total no. of breaks | 8
cost per break | 1000
overage | 25%
| 10000 | per period
total cost | 30000 | all periods

## Fab_assy
WBS 123 Vacuum Vessel Heating and Cooling system
In-house Fabrication and Assembly
Description:
This effort describes the assembly time to put the cooling line tracing on the exterior of the vessel and to put the heaters on the ports. The actual assembly time is covered in the WBS 184 estimate. |  |  |  |  | Labor category
[5 empty] | total fraction | EAEM |  | EASM, EMSM |  | EMTB |  | EADM
| multiplier | unit | no. | hours |  | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
Fab operations summary
| 0 | hrs/lot | 1 | 0 | 1 | 0 | 0 | 0.2 | 0 | 0.8 | 0 | 0 | 0
| 0 | hrs/line | 0 | 0 | 1 | 0 | 0 | 0.2 | 0 | 0.8 | 0 | 0 | 0
| 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
subtotal |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0
[5 empty] | total fraction | EAEM |  | EASM, EMSM |  | EMTB |  | EADM
Assembly operations summary* | [5 empty] | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
coolant line tracing on VV shell | 0 | hr/period | 3 | 0 | 1 | 0 | 0 | 0.2 | 0 | 0.8 | 0 | 0 | 0
heaters on ports | 0 | hr/period | 3 | 0 | 1 | 0 | 0 | 0.2 | 0 | 0.8 | 0 | 0 | 0
heaters on NBI duct | 0 | hr/period | 3 | 0 | 1 | 0 | 0 | 0.2 | 0 | 0.8 | 0 | 0 | 0
install manifolds and connect | 0 | hr/period | 3 | 0 | 1 | 0 | 0 |  | 0 | 1 | 0 | 0 | 0
subtotal |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0
* included in WBS 184
Worksheets
coolant line tracing on VV shell
avg poloidal perimeter of torus | 16 | ft
spacing of tubes | 0.5 | ft
approx no. poloidal loops/period | 64
spacing of tube hold-downs | 0.8 | ft
no. of hold downs/period | 1280 | hold-downs
hydraulic loops per period | 64
no. of hydraulic conn/period | 128
hours per connection | 1 | hours
no. of tubes per shift | 8
crew size | 2
shifts per field period | 8 | shifts
tech hours per field period | 128 | hours/period
technical oversight, inspection | 32 | hrs/period
total hours, tracing on torus | 160 | hrs/period
total hours, all periods | 480 | hours
heaters on port extensions
no. of heaters per port | 2
no. of port ext. | 28 | per period
no of heaters per shift | 8
crew size | 2
shifts per field period | 7 | shifts
tech hours per field period | 112 | hours/period
technical oversight, inspection | 28 | hrs/period
total hours, heater tracing on ports | 140 | hours/period
total hours, all periods | 420 | hours
heaters on NBI ports
no. of heaters per port | 8
no. of port ext. | 1 | per period
no of heaters per shift | 4
crew size | 2
shifts per field period | 2 | shifts
tech hours per field period | 32 | hours/period
technical oversight, inspection | 8 | hrs/period
total hours, heater tracing on ports | 40 | hours/period
total hours, all periods | 120 | hours
Connection of tubes to manifolds
Assume 32 double loops per field period
assume inconel 600 tubing
The connections connect each loop to the headers above and below the machine.
number of tubes per period | 64
connections per tube | 2
total number of coolant connections per period | 128
hours to make swagelock connection | 0.5 | per connecting tubes
shifts for inspection, leak check | 2 | per period
crew size for inspection | 2
total shifts for connecting tube | 12
tech hours for connecting tubes | 96 | hrs per period
technical oversight, inspection | 24 | hrs per period
electrical check of breaks | 20 | hrs per period
total hours per period | 140 | hrs per period
total hours, all periods | 420 | hours
total hours, per period | 480
total hours, 3 periods | 1440

## Installation
WBS 123 Vacuum Vessel Heating and Cooling system
Installation
This element is not part of the WBS 1 scope of work
notes: | get name of federal QA outfit from Rod Templon's email