## Fab Project
WBS 131 TF Coils | [10 empty] | 17 |  | Duration of activity per fiscal year (weeks)
Labor
| Activity Title |  | Manhours | FY2003 $$ | Labor Type | Start Date Month/Yr | End Date Month/Yr | Comments |  |  |  | duration (weeks) | 2002-10-01 | 2003-10-01 | 2004-10-01 | 2005-10-01 | 2006-10-01 | 2007-10-01 | 2008-10-01
Preliminary Design (Title I)
|  | ( 50% of design schedule) | 275.4 |  | EAEM | 2003-10-26 | 2004-02-29 | PPPL Engineer |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0 |  | 50 | 50% | of design is preliminary design
|  |  | 290 |  | EADM | 2003-10-26 | 2004-02-29 | PPPL Designer |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
|  |  | 72.6 |  | ORNL Eng | 2003-10-26 | 2004-02-29 | Composite of ORNL Engineer / Designer |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
|  |  | 0 |  | ORNL Phys. | 2003-10-26 | 2004-02-29 | Composite of ORNL Physics / scientific |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
|  |  | 0 |  | PPPL Phys. | 2003-10-26 | 2004-02-29 | PPPL Physics/scientific |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
Final Design (Title II)
|  | ( 50% of design schedule) | 275.4 |  | EAEM | 2004-02-29 | 2004-07-04 | PPPL Engineer |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0 |  | 50 | 50% | of design schedule is final design
|  |  | 290 |  | EADM | 2004-02-29 | 2004-07-04 | PPPL Designer |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
|  |  | 72.6 |  | ORNL Eng | 2004-02-29 | 2004-07-04 | Composite of ORNL Engineer / Designer |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
|  |  | 0 |  | ORNL Phys. | 2004-02-29 | 2004-07-04 | Composite of ORNL Physicist |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
|  |  | 0 |  | PPPL Phys. | 2004-02-29 | 2004-07-04 | PPPL Physics/scientific |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
Lab R&D labor
|  |  | 0 |  | EAEM | 2003-10-26 | 2004-02-29 | PPPL Engineer |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
|  |  | 0 |  | EADM | 2003-10-26 | 2004-02-29 | PPPL Designer |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
|  |  | 0 |  | ORNL Eng | 2003-10-26 | 2004-02-29 | Composite of ORNL Engineer / Designer |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
|  |  | 0 |  | EASM | 2003-10-26 | 2004-02-29 | PPPL monthly support |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
|  |  | 0 |  | EMTB | 2003-10-26 | 2004-02-29 | PPPL Technician |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
Lab Fab/Assembly/Installation (Title III)
|  |  | 665.6 |  | EAEM | 2004-07-04 | 2006-01-01 | PPPL Engineer |  |  |  | 78 | 0 | 12.7143 | 52.1429 | 13.1429 | 0 | 0
|  |  | 96 |  | EADM | 2004-07-04 | 2006-01-01 | PPPL Designer |  |  |  | 78 | 0 | 12.7143 | 52.1429 | 13.1429 | 0 | 0
|  |  | 62.4 |  | ORNL Eng | 2004-07-04 | 2006-01-01 | Composite of ORNL Engineer / Designer |  |  |  | 78 | 0 | 12.7143 | 52.1429 | 13.1429 | 0 | 0
|  |  | 0 |  | EASM | 2004-07-04 | 2006-01-01 | PPPL monthly support |  |  |  | 78 | 0 | 12.7143 | 52.1429 | 13.1429 | 0 | 0
|  |  | 0 |  | EMTB | 2004-07-04 | 2006-01-01 | PPPL Technician |  |  |  | 78 | 0 | 12.7143 | 52.1429 | 13.1429 | 0 | 0
Labor
Manhours per fiscal year by labor category
Level of Effort |  |  |  | FY2003 | FY2004 | FY2005 | FY2006 | FY2007 | FY2008 | TOTAL
| PPPL Engineer |  | EAEM | 0 | 659.2952 | 444.9524 | 112.1524 | 0 | 0 | 1216.4 |  | 186109.2 | 153 | per hour
| PPPL Designer |  | EADM | 0 | 595.6484 | 64.1758 | 16.1758 | 0 | 0 | 676 |  | 67600 | 100 | per hour
| Composite of ORNL Engineer / Designer |  | ORNL Eng | 0 | 155.3714 | 41.7143 | 10.5143 | 0 | 0 | 207.6 |  | 26988 | 130 | per hour
| PPPL monthly support |  | EASM | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 100 | per hour
| PPPL Technician |  | EMTB | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 73 | per hour
| Composite of ORNL Physics / scientific |  | ORNL Phy | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 160 | per hour
| PPPL Physics/scientific |  | PPPL Phy | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 141 | per hour
[12 empty] | 1892.4 | 253709.2 | PPPL
[12 empty] | 207.6 | 26988 | ORNL
M&S Costs
| Activity Title |  |  | FY2003 $$ |  | Comment
Manufacturing Development (R&D)
|  | Purchased Design Services |  | 0
|  | Procured Hardware/Material |  | 0
|  | Profit |  | 0 |  | included in hardware estimate
|  | total, manf/dev (R&D) |  | 0 |  | w/o G&A
Procured Hardware/Material
|  | set of 18 TF coils |  | 1026394.0966
|  | Profit |  | 102639.4097 |  | assume 10%
|  | total, procured hdwe/matl. |  | 1129033.5063 |  | w/o G&A
| Purchased Design Services |  |  | 0 |  | no purchased services anticipated
| Procured Installation/Assembly Costs |  |  | 0 |  | All installation and assembly costs are included in WBS 7
Other Costs
| Activity Title |  |  | FY2003 $$ |  | Comment
| Travel |  |  | 2000 |  | only two trips are anticipated
Summary Costs
| Activity Title |  | Manhours | FY2003 $$ |  | Comment
Labor
| PPPL Effort |  | 1892.4 | 253709.2 |  | Assumed rates: |  | EASM | 100 $/hr
| ORNL effort |  | 207.6 | 26988 |  | EAEM | 153 $/hr | EMTB | 73 $/hr
|  | subtotal, labor | 2100 | 280697.2 |  | EADM | 100 $/hr | PPPL Phys | 141 $/hr
[6 empty] | ORNL Eng | 130 $/hr | ORNL Phys | 160 $/hr
M&S, Other
| Manufacturing Development (R&D) |  |  | 0
| Procured Hardware/Material |  |  | 1129033.5063
| Purchased Design Services |  |  | 0
| Procured Installation/Assembly Costs |  |  | 0
| Travel |  |  | 2000
|  | subtotal, M&S |  | 1131033.5063
| G&A |  |  | 151159.8524 |  | 25% | on all purchased materials, subcontracts, travel
[6 empty] | 131598.5241 | G&A adjustment on large procurement
| Subtotal without contingency |  |  | 1562890.5587
| Contingency |  |  | 375093.7341 |  | 24% | Overall on this WBS
| Total cost |  |  | 1937984.2927

## Other Costs
|  | 1808-NCSX-1701 | [5 empty] | XX represents the 2 digit WBS code
| Activity Title |  | Manhours | FY2003 $$ | Labor Type | Start Date Month/Year | End Date Month/Year | Comments
Level of Effort | [7 empty] | Research Prep Activities
FY2003
[5 empty] | RMRM3 |  |  | SAMPLE - Put in specific labor type
[5 empty] | FCEM |  |  | SAMPLE - Put in specific labor type
FY2004
FY2005
FY2006
FY2007
Research Planning/Preparations
FY2003
[5 empty] | RMRM3 |  |  | SAMPLE - Put in specific labor type
[5 empty] | FCEM |  |  | SAMPLE - Put in specific labor type
FY2004
FY2005
FY2006
FY2007
Operational Spares
M&S Costs
Manufacturing Development
Purchased Design Services
|  | Procured Hardware/Material | [5 empty] | Include any M&S carried over from FY2002
| Procured Hardware/Material | [6 empty] | Identify each procurement over $100K individually
Purchased Design Services
Procured Installation/Assembly Costs
Other Costs
Travel
FY2003
[5 empty] | RMRM3 |  |  | SAMPLE - Put in specific labor type
[5 empty] | FCEM |  |  | SAMPLE - Put in specific labor type
FY2004
FY2005
FY2006
FY2007
Allocations (WBS 81 only)
Instructions for Completing Form
(1) One form for each 3 digit WBS element (e.g., 111, 121, 452, etc.) => if no 3 digit WBS, use 2 digit WBS (e.g., 81, 82, 84)
(2) For Lab labor, provide estimate in manhours => provide estimate by specific labor type.
(3) For M&S, provide estimate in FY2002 direct dollars if procured by PPPL, or in fully loaded dollars if procured by ORNL
(4) Start and end date provided in month/year format => March/2003

## Engr
WBS 131 TF Coils
Engineering, Title I, II and III
Description:
This effort covers all Title I, II, and III engineering for the TF coil windings. The coils are procured via a fixed price contract. All installation oversight will be performed as part of WBS 7. |  |  |  |  | Labor category
[5 empty] | total fraction | EAEM |  | EADM |  | ORNL Eng |  | ORNL Physics |  | PPPL Physics
| multiplier | unit | no. | hours |  | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
Title I, II design
Pro-E models (avg) | 40 | hrs/model | 5 | 200 | 1 | 0.25 | 50 | 0.5 | 100 | 0.25 | 50 | 0 | 0 | 0 | 0
assy dwgs | 40 | hrs/dwg | 4 | 160 | 1 | 0 | 0 | 1 | 160 | 0 | 0 | 0 | 0 | 0 | 0
Detail drawings | 40 | hrs/dwg | 6 | 240 | 1 | 0 | 0 | 1 | 240 | 0 | 0 | 0 | 0 | 0 | 0
installation dwg | 40 | hrs/dwg | 1 | 40 | 1 | 0 | 0 | 1 | 40 | 0 | 0 | 0 | 0 | 0 | 0
cooling schematic | 20 | hrs/dwg | 1 | 20 | 1 | 0 | 0 | 1 | 20 | 0 | 0 | 0 | 0 | 0 | 0
electrical schematic | 20 | hrs/dwg | 1 | 20 | 1 | 0 | 0 | 1 | 20 | 0 | 0 | 0 | 0 | 0 | 0
I&C schematic | 20 | hrs/dwg | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
stress analysis | 40 | hrs/calc | 2 | 80 | 1 | 1 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
thermal analysis | 40 | hrs/calc | 2 | 80 | 1 | 1 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
special analysis (electromagnetics) | 80 | hrs/calc | 1 | 80 | 1 | 0.5 | 40 | 0 | 0 | 0.5 | 40 | 0 | 0 | 0 | 0
procurement/fab specifications | 80 | hrs/spec | 1 | 80 | 1 | 1 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
preliminary and final design reviews | 80 | hrs/rev | 2 | 160 | 1 | 0.8 | 128 | 0 | 0 | 0.2 | 32 | 0 | 0 | 0 | 0
meetings/reporting/presentations | 10% | % of tot | 1160 | 116 | 1 | 0.8 | 92.8 | 0 | 0 | 0.2 | 23.2 | 0 | 0 | 0 | 0
subtotal |  |  |  | 1276 |  |  | 550.8 |  | 580 |  | 145.2 |  | 0 |  | 0
[5 empty] | total fraction | EAEM |  | EASM |  | EADM |  | ORNL Eng
Title III | [5 empty] | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
vendor oversight, inspection | 8 | hrs/wk | 52 | 416 | 1 | 1 | 416 | 0 | 0 | 0 | 0 | 0 | 0
Disposition of deviation requests and non-conformances | 4 | hrs/wk | 78 | 312 | 1 | 0.8 | 249.6 | 0 | 0 | 0 | 0 | 0.2 | 62.4
As-built drawings | 8 | hrs/dwg | 12 | 96 | 1 | 0 | 0 | 0 | 0 | 1 | 96 | 0 | 0
subtotal |  |  |  | 824 |  |  | 665.6 |  | 0 |  | 96 |  | 62.4
Schedule assumptions | start | duration (weeks) | end
Title I Design | 2003-10-26 | 18 | 2004-02-29
Title II Design | 2004-02-29 | 18 | 2004-07-04
Procurement | 2004-07-04 | 52 | 2005-07-03
In-house fab / sub-assy | 2005-07-03 | 0 | 2005-07-03
Installation / final assembly | 2005-07-03 | 26 | 2006-01-01
Notes and worksheets
TF Coil winding design
| total | Windings | Crossovers and lead blocks
Pro-E models | 5 | 2 | 3
assy dwgs | 4 | 2 | 2 | double pancake, crossover/lead area, overall assy
Detail drawings | 6 | 2 | 4 | winding, lead blocks, crossover fillers
installation dwg | 1 | 1 | 0
cooling schematic | 1 | 1
electrical schematic | 1 | 1
I&C schematic | 0 |  |  | covered in WBS 133
stress analysis | 2 | 1 | 1 | global and local analysis of winding pack and lead regions
thermal analysis | 2 | 1 | 1 | global and local analysis of winding pack and lead regions
special analysis | 1 | em analysis of lead area, general analysis in WBS 171
procurement specifications | 1 | one procurement specification for winding
preliminary and final design reviews | 2 | reviews
meetings/reporting/presentations | 15%
Formulas:
multiplier = [no.]-[unit]*7
no. = [multiplier, row below]

## R&D
WBS 131 TF Coils
R&D
Description:
No R&D is associated with this WBS
Summary
Purchased Design Services
Vendor surveillance via | 0
subtotal | 0 |  | w/o G&A
Procured Hardware/Material
Cast and machined winding forms | 0
subtotal | 0 |  | w/o G&A
Subcontractor labor rates:
design rate: | 130 | per hour
fab rate | 60 | per hour
inspection/technician rate | 60 | per hour

## M&S
WBS 131 TF Coils
Materials and Subcontracts (M&S)
Description:
This effort covers procurement of the TF coil windings. The coils are procured via a fixed price contract and include the winding assembly with terminal blocks for attachment of leads.
Purchased parts:
TF Coil windings | 1026394.0966 | see notes below
subtotal, purchased parts | 1026394.0966
outside engr rate = | 130 | $ per hour
outside fab rate = | 60 | $ per hour
outside inspection/technician rate = | 60 | $ per hour
Worksheet:
TF Winding geometry
Length_m | 8.6568 | average perimeter per turn
NumberCoils | 18
TurnsHigh | 6
TurnsWide | 2
Turns | 12
ConductorLengthPerDP_m | 103.8814
EnvelopeHeight_mm | 88
EnvelopeWidth_mm | 100
BundleHeight_mm | 80.645
BundleWidth_mm | 134.2136
BundleArea_mm2 | 10823.6558
BundleArea_m2 | 0.010824
EquivRadius_m | 0.074428
GroundWrap_mm | 0.762
TurnInsulation_mm | 1.0668
PancakeInsulation_mm | 0.762
ConductorHeight_mm | 11.02
ConductorWidth_mm | 63.83
CornerRadius_mm | 1.27
CornerArea_mm2 | 1.3845
CoolingHoleDia_mm (equiv.) | 12.8655
CoolingArea_mm2 | 130
ConductorArea_mm2 | 572.0221
FillFactor | 1
CopperArea_mm2 | 572.0221
copper density_kg/mm^3 | 8.58e-06
Weight/coil, kg | 509.8446
TF Winding cost details | Ref. P. Heitzenroeder
I. Tooling by vendor
Tooling engineering/mfg. Plans | hrs. | 160
Tooling engineering | $ | 20800
Tooling design | hrs. | 160
Tooling design | $ | 9600
Tooling fabrication (200% of 1 coil matl) | $ | 34679.0116
Tooling for Nose shaving&curing | hrs. | 160 | incl in tooling design
Tooling Fab for nose | $ | 40000
Total tooling design hours | hrs. | 480 | (half engineer; half designer)
Total tooling cost | $ | 105079.0116
II. Materials
Ordering/stocking materials | hrs. | 500 | technician hours
" " | $ | 30000
copper extrusion cost | 10 | $/kg
Copper order factor | 1.25 | factor | assume 25% overage
copper cost , 18 coils ; | $ | 114715.0373
misc matl -$ per lb of Cu in coils | 2 | $/kg
misc. matl. Cost, pair of coils | $ | 18354.406
glass insul width | mm | 25.4
turn insul.: length/meter of cond./layer | m/m | 5.8937
turn ins. Tape Thickness | mm | 0.1778
No. half lapped layers | # | 2
meters of ins. /roll | m | 10
no. rolls/coil | # | 122.4492
insulation waste factor | multiplier | 1.3
total rolls of turn ins. reqd. | # | 2865.3105
turn insulation cost per roll | $/roll | 4
Kapton insul width | mm | 25.4
turn insul.: length/meter of cond./layer | m/m | 5.8937
turn ins. Tape Thickness | mm | 0.2667
No. half lapped Kapton layers | # | 1
meters of ins. /roll | m | 10
no. rolls/coil | # | 61.2246
insulation waste factor | multiplier | 1.3
total rolls of turn ins. reqd. | # | 1432.6553
turn insulation cost per roll | $/roll | 40
turn insulation total cost, 18 coils | $ | 68767.4522
ground wall tape thickness | mm | 0.254
No. half lapped layers | # | 6
total ground wall thick. | mm | 3.048
ground wall tape width | cm | 5.08
gw tape length reqd. | m | 439.3663
meters of ins. /roll | m | 10
no. rolls/coil | # | 43.9366
insulation waste factor | multiplier | 1.3
no. rolls of GW insulation, 18 coils | # | 1028.1172
GW tape cost per roll | $ | 28
GW insulation cost, 18 coils | $ | 28787.2828
Epoxy volume reqd. (15% void fraction) | l | 14.0547
Epoxy cost/liter | $/l | 30
Epoxy cost for 18 coils | $ | 9486.926
Leads and coolant connections/coil | $ | 4000
Leads & coolant con's., all coils | $ | 72000
II. Material cost for 18 coils | $ | 312111.1042 | M&S w/o G&A
III. Labor
Tooling prep. | shifts | 1
turns/8 hr. shift, incl. Insulation application | # | 4
crew size | # | 3
Shifts reqd. per coil | # | 3
person-hours to prep & wind coil | hrs. | 80
technical oversight/coil | hrs. | 16 | half time for all shifts
tech. Oversight cost | $ | 2080
GW application time-rolls/shift | # | 12
crew size for GW | # | 2
person hours to apply | hrs. | 76.1568
VPI prep & process.- hrs/ m-coil | hrs. | 8
crew size for VPI | # | 3
person hours/coil for VPI | hrs. | 69.2543
Shave nose Machinist | hrs. | 224
Wrap & Cure nose (2 men 4 days) | hrs. | 64
elec/hydraulic test | hrs. | 16
Total labor hours for 18 coils | hrs. | 9529.3997 | (technician labor)
Total labor hours for 18 coils | hrs. | 288
III.Total Labor Cost | $ | 609203.9808
Total Manufacturing Costs,TF Coils | $ | 1026394.0966

## Fab_assy
WBS 131 TF Coils
In-house Fabrication and Assembly
Description:
No fabrication and assembly is associated with this WBS |  |  |  |  | Labor category
[5 empty] | total fraction | EAEM |  | EASM, EMSM |  | EMTB |  | EADM
| multiplier | unit | no. | hours |  | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
Fab operations summary
| 0 | hrs/lot | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 0 | hrs/line | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | hrs / coil | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
subtotal |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0
[5 empty] | total fraction | EAEM |  | EASM, EMSM |  | EMTB |  | EADM
Assembly operations summary | [5 empty] | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
| 0 | hr/lot | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| 0 | hr/lot | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | hr/coil | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | hours | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
subtotal |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0

## Installation
WBS 131 TF Coils
Installation
This element is not part of the WBS 1 scope of work