## Fab Project
WBS 132 PF Coils | [10 empty] | 17 |  | Duration of activity per fiscal year (weeks)
Labor
| Activity Title |  | Manhours | FY2003 $$ | Labor Type | Start Date Month/Yr | End Date Month/Yr | Comments |  |  |  | duration (weeks) | 2002-10-01 | 2003-10-01 | 2004-10-01 | 2005-10-01 | 2006-10-01 | 2007-10-01 | 2008-10-01
Preliminary Design (Title I)
|  | ( 50% of design schedule) | 439.12 |  | EAEM | 2003-10-26 | 2004-02-29 | PPPL Engineer |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0 |  | 50 | 50% | of design is preliminary design
|  |  | 732 |  | EADM | 2003-10-26 | 2004-02-29 | PPPL Designer |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
|  |  | 109.28 |  | ORNL Eng | 2003-10-26 | 2004-02-29 | Composite of ORNL Engineer / Designer |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
|  |  | 0 |  | ORNL Phys. | 2003-10-26 | 2004-02-29 | Composite of ORNL Physics / scientific |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
|  |  | 0 |  | PPPL Phys. | 2003-10-26 | 2004-02-29 | PPPL Physics/scientific |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
Final Design (Title II)
|  | ( 50% of design schedule) | 439.12 |  | EAEM | 2004-02-29 | 2004-07-04 | PPPL Engineer |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0 |  | 50 | 50% | of design schedule is final design
|  |  | 732 |  | EADM | 2004-02-29 | 2004-07-04 | PPPL Designer |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
|  |  | 109.28 |  | ORNL Eng | 2004-02-29 | 2004-07-04 | Composite of ORNL Engineer / Designer |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
|  |  | 0 |  | ORNL Phys. | 2004-02-29 | 2004-07-04 | Composite of ORNL Physicist |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
|  |  | 0 |  | PPPL Phys. | 2004-02-29 | 2004-07-04 | PPPL Physics/scientific |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
Lab R&D labor
|  |  | 0 |  | EAEM | 2003-10-26 | 2004-02-29 | PPPL Engineer |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
|  |  | 0 |  | EADM | 2003-10-26 | 2004-02-29 | PPPL Designer |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
|  |  | 0 |  | ORNL Eng | 2003-10-26 | 2004-02-29 | Composite of ORNL Engineer / Designer |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
|  |  | 0 |  | EASM | 2003-10-26 | 2004-02-29 | PPPL monthly support |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
|  |  | 0 |  | EMTB | 2003-10-26 | 2004-02-29 | PPPL Technician |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
Lab Fab/Assembly/Installation (Title III)
|  |  | 704 |  | EAEM | 2004-07-04 | 2006-01-01 | PPPL Engineer |  |  |  | 78 | 0 | 12.7143 | 52.1429 | 13.1429 | 0 | 0
|  |  | 96 |  | EADM | 2004-07-04 | 2006-01-01 | PPPL Designer |  |  |  | 78 | 0 | 12.7143 | 52.1429 | 13.1429 | 0 | 0
|  |  | 62.4 |  | ORNL Eng | 2004-07-04 | 2006-01-01 | Composite of ORNL Engineer / Designer |  |  |  | 78 | 0 | 12.7143 | 52.1429 | 13.1429 | 0 | 0
|  |  | 0 |  | EASM | 2004-07-04 | 2006-01-01 | PPPL monthly support |  |  |  | 78 | 0 | 12.7143 | 52.1429 | 13.1429 | 0 | 0
|  |  | 0 |  | EMTB | 2004-07-04 | 2006-01-01 | PPPL Technician |  |  |  | 78 | 0 | 12.7143 | 52.1429 | 13.1429 | 0 | 0
Labor
Manhours per fiscal year by labor category
Level of Effort |  |  |  | FY2003 | FY2004 | FY2005 | FY2006 | FY2007 | FY2008 | TOTAL
| PPPL Engineer |  | EAEM | 0 | 992.9946 | 470.6227 | 118.6227 | 0 | 0 | 1582.24 |  | 242082.72 | 153 | per hour
| PPPL Designer |  | EADM | 0 | 1479.6484 | 64.1758 | 16.1758 | 0 | 0 | 1560 |  | 156000 | 100 | per hour
| Composite of ORNL Engineer / Designer |  | ORNL Eng | 0 | 228.7314 | 41.7143 | 10.5143 | 0 | 0 | 280.96 |  | 36524.8 | 130 | per hour
| PPPL monthly support |  | EASM | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 100 | per hour
| PPPL Technician |  | EMTB | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 73 | per hour
| Composite of ORNL Physics / scientific |  | ORNL Phy | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 160 | per hour
| PPPL Physics/scientific |  | PPPL Phy | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 141 | per hour
[12 empty] | 3142.24 | 398082.72 | PPPL
[12 empty] | 280.96 | 36524.8 | ORNL
M&S Costs
| Activity Title |  |  | FY2003 $$ |  | Comment
Manufacturing Development (R&D)
|  | Purchased Design Services |  | 0
|  | Procured Hardware/Material |  | 0
|  | Profit |  | 0 |  | included in hardware estimate
|  | total, manf/dev (R&D) |  | 0 |  | w/o G&A
Procured Hardware/Material
|  | set of PF coils |  | 852103.2437
|  | Profit |  | 85210.3244 |  | 10% profit
|  | total, procured hdwe/matl. |  | 937313.568 |  | w/o G&A
| Purchased Design Services |  |  | 0 |  | no purchased services anticipated
| Procured Installation/Assembly Costs |  |  | 0 |  | All installation and assembly costs are included in WBS 7
Other Costs
| Activity Title |  |  | FY2003 $$ |  | Comment
| Travel |  |  | 4000 |  | two trips are anticipated for this WBS
Summary Costs
| Activity Title |  | Manhours | FY2003 $$ |  | Comment
Labor
| PPPL Effort |  | 3142.24 | 398082.72 |  | Assumed rates: |  | EASM | 100 $/hr
| ORNL effort |  | 280.96 | 36524.8 |  | EAEM | 153 $/hr | EMTB | 73 $/hr
|  | subtotal, labor | 3423.2 | 434607.52 |  | EADM | 100 $/hr | PPPL Phys | 141 $/hr
[6 empty] | ORNL Eng | 130 $/hr | ORNL Phys | 160 $/hr
M&S, Other
| Manufacturing Development (R&D) |  |  | 0
| Procured Hardware/Material |  |  | 937313.568
| Purchased Design Services |  |  | 0
| Procured Installation/Assembly Costs |  |  | 0
| Travel |  |  | 4000
|  | subtotal, M&S |  | 941313.568
| G&A |  |  | 126000 |  | 25% | on all purchased materials, subcontracts, travel
[6 empty] | 109328.392 | G&A adjustment on large procurement
| Subtotal without contingency |  |  | 1501921.088
| Contingency |  |  | 360461.0611 |  | 24% | Overall on this WBS
| Total cost |  |  | 1862382.1492
Central Solenoid Support Structures => Moved from old WBS 152 | [10 empty] | 17 |  | Duration of activity per fiscal year (weeks)
Labor
| Activity Title |  | Manhours | FY2003 $$ | Labor Type | Start Date Month/Yr | End Date Month/Yr | Comments |  |  |  | duration (weeks) | 2002-10-01 | 2003-10-01 | 2004-10-01 | 2005-10-01 | 2006-10-01 | 2007-10-01 | 2008-10-01
Preliminary Design (Title I)
|  | #DIV/0! | #DIV/0! |  | EAEM | 2003-10-26 | 2004-02-29 | PPPL Engineer |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0 |  | #DIV/0! | #DIV/0! | of design is preliminary design
|  |  | #DIV/0! |  | EADM | 2003-10-26 | 2004-02-29 | PPPL Designer |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
|  |  | #DIV/0! |  | ORNL Eng | 2003-10-26 | 2004-02-29 | Composite of ORNL Engineer / Designer |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
|  |  | #DIV/0! |  | ORNL Phys. | 2003-10-26 | 2004-02-29 | Composite of ORNL Physics / scientific |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
|  |  | #DIV/0! |  | PPPL Phys. | 2003-10-26 | 2004-02-29 | PPPL Physics/scientific |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
Final Design (Title II)
|  | #DIV/0! | #DIV/0! |  | EAEM | 2004-02-29 | 2004-07-04 | PPPL Engineer |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0 |  | #DIV/0! | #DIV/0! | of design schedule is final design
|  |  | #DIV/0! |  | EADM | 2004-02-29 | 2004-07-04 | PPPL Designer |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
|  |  | #DIV/0! |  | ORNL Eng | 2004-02-29 | 2004-07-04 | Composite of ORNL Engineer / Designer |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
|  |  | #DIV/0! |  | ORNL Phys. | 2004-02-29 | 2004-07-04 | Composite of ORNL Physicist |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
|  |  | #DIV/0! |  | PPPL Phys. | 2004-02-29 | 2004-07-04 | PPPL Physics/scientific |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
Lab R&D labor
|  |  | 0 |  | EAEM | 2003-10-26 | 2004-02-29 | PPPL Engineer |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
|  |  | 0 |  | EADM | 2003-10-26 | 2004-02-29 | PPPL Designer |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
|  |  | 0 |  | ORNL Eng | 2003-10-26 | 2004-02-29 | Composite of ORNL Engineer / Designer |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
|  |  | 0 |  | EASM | 2003-10-26 | 2004-02-29 | PPPL monthly support |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
|  |  | 0 |  | EMTB | 2003-10-26 | 2004-02-29 | PPPL Technician |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
Lab Fab/Assembly/Installation (Title III)
|  |  | 0 |  | EAEM | 2004-07-04 | 2006-01-01 | PPPL Engineer |  |  |  | 78 | 0 | 12.7143 | 52.1429 | 13.1429 | 0 | 0
|  |  | 0 |  | EADM | 2004-07-04 | 2006-01-01 | PPPL Designer |  |  |  | 78 | 0 | 12.7143 | 52.1429 | 13.1429 | 0 | 0
|  |  | 0 |  | ORNL Eng | 2004-07-04 | 2006-01-01 | Composite of ORNL Engineer / Designer |  |  |  | 78 | 0 | 12.7143 | 52.1429 | 13.1429 | 0 | 0
|  |  | 0 |  | EASM | 2004-07-04 | 2006-01-01 | PPPL monthly support |  |  |  | 78 | 0 | 12.7143 | 52.1429 | 13.1429 | 0 | 0
|  |  | 0 |  | EMTB | 2004-07-04 | 2006-01-01 | PPPL Technician |  |  |  | 78 | 0 | 12.7143 | 52.1429 | 13.1429 | 0 | 0
Labor
Manhours per fiscal year by labor category
Level of Effort |  |  |  | FY2003 | FY2004 | FY2005 | FY2006 | FY2007 | FY2008 | TOTAL
| PPPL Engineer |  | EAEM | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | 153 | per hour
| PPPL Designer |  | EADM | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | 100 | per hour
| Composite of ORNL Engineer / Designer |  | ORNL Eng | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | 130 | per hour
| PPPL monthly support |  | EASM | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 100 | per hour
| PPPL Technician |  | EMTB | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 73 | per hour
| Composite of ORNL Physics / scientific |  | ORNL Phy | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | 160 | per hour
| PPPL Physics/scientific |  | PPPL Phy | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | 141 | per hour
[12 empty] | #DIV/0! | #DIV/0! | PPPL
[12 empty] | #DIV/0! | #DIV/0! | ORNL
M&S Costs
| Activity Title |  |  | FY2003 $$ |  | Comment
Manufacturing Development (R&D)
|  | Purchased Design Services |  | 0
|  | Procured Hardware/Material |  | 0
|  | Profit |  | 0 |  | included in hardware estimate
|  | total, manf/dev (R&D) |  | 0 |  | w/o G&A
Procured Hardware/Material
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | Profit |  | 0 |  | included in hardware estimate
|  | total, procured hdwe/matl. |  | 0 |  | w/o G&A
| Purchased Design Services |  |  | 0 |  | no purchased services anticipated
| Procured Installation/Assembly Costs |  |  | 0 |  | All installation and assembly costs are included in WBS 7
Other Costs
| Activity Title |  |  | FY2003 $$ |  | Comment
| Travel |  |  | 2 |  | only one trip is anticipated
Summary Costs
| Activity Title |  | Manhours | FY2003 $$ |  | Comment
Labor
| PPPL Effort |  | #DIV/0! | #DIV/0! |  | Assumed rates: |  | EASM | 100 $/hr
| ORNL effort |  | #DIV/0! | #DIV/0! |  | EAEM | 153 $/hr | EMTB | 73 $/hr
|  | subtotal, labor | #DIV/0! | #DIV/0! |  | EADM | 100 $/hr | PPPL Phys | 141 $/hr
[6 empty] | ORNL Eng | 130 $/hr | ORNL Phys | 160 $/hr
M&S, Other
| Manufacturing Development (R&D) |  |  | 0
| Procured Hardware/Material |  |  | 0
| Purchased Design Services |  |  | 0
| Procured Installation/Assembly Costs |  |  | 0
| Travel |  |  | 2
|  | subtotal, M&S |  | 2
| G&A |  |  | 0.5 |  | 25% | on all purchased materials, subcontracts, travel
| Subtotal without contingency |  |  | #DIV/0!
| Contingency |  |  | #DIV/0! |  | 32% | Overall on this WBS
| Total cost |  |  | #DIV/0!
Formulas:
FY2005 = '[1]Engr'!B$38
FY2006 = '[1]Engr'!D$38

## Other Costs
|  | 1808-NCSX-1701 | [5 empty] | XX represents the 2 digit WBS code
| Activity Title |  | Manhours | FY2002 $$ | Labor Type | Start Date Month/Year | End Date Month/Year | Comments
Level of Effort | [7 empty] | Research Prep Activities
FY2003
[5 empty] | RMRM3 |  |  | SAMPLE - Put in specific labor type
[5 empty] | FCEM |  |  | SAMPLE - Put in specific labor type
FY2004
FY2005
FY2006
FY2007
Research Planning/Preparations
FY2003
[5 empty] | RMRM3 |  |  | SAMPLE - Put in specific labor type
[5 empty] | FCEM |  |  | SAMPLE - Put in specific labor type
FY2004
FY2005
FY2006
FY2007
Operational Spares
M&S Costs
Manufacturing Development
Purchased Design Services
|  | Procured Hardware/Material | [5 empty] | Include any M&S carried over from FY2002
| Procured Hardware/Material | [6 empty] | Identify each procurement over $100K individually
Purchased Design Services
Procured Installation/Assembly Costs
Other Costs
Travel
FY2003
[5 empty] | RMRM3 |  |  | SAMPLE - Put in specific labor type
[5 empty] | FCEM |  |  | SAMPLE - Put in specific labor type
FY2004
FY2005
FY2006
FY2007
Allocations (WBS 81 only)
Instructions for Completing Form
(1) One form for each 3 digit WBS element (e.g., 111, 121, 452, etc.) => if no 3 digit WBS, use 2 digit WBS (e.g., 81, 82, 84)
(2) For Lab labor, provide estimate in manhours => provide estimate by specific labor type.
(3) For M&S, provide estimate in FY2002 direct dollars if procured by PPPL, or in fully loaded dollars if procured by ORNL
(4) Start and end date provided in month/year format => March/2003
|  | 1808-NCSX-01 | [5 empty] | XX represents the 2 digit WBS code
| Activity Title |  | Manhours | FY2002 $$ | Labor Type | Start Date Month/Year | End Date Month/Year | Comments
Level of Effort | [7 empty] | Research Prep Activities
FY2003
[5 empty] | RMRM3 |  |  | SAMPLE - Put in specific labor type
[5 empty] | FCEM |  |  | SAMPLE - Put in specific labor type
FY2004
FY2005
FY2006
FY2007
Research Planning/Preparations
FY2003
[5 empty] | RMRM3 |  |  | SAMPLE - Put in specific labor type
[5 empty] | FCEM |  |  | SAMPLE - Put in specific labor type
FY2004
FY2005
FY2006
FY2007
Operational Spares
M&S Costs
Manufacturing Development
Purchased Design Services
|  | Procured Hardware/Material | [5 empty] | Include any M&S carried over from FY2002
| Procured Hardware/Material | [6 empty] | Identify each procurement over $100K individually
Purchased Design Services
Procured Installation/Assembly Costs
Other Costs
Travel
FY2003
[5 empty] | RMRM3 |  |  | SAMPLE - Put in specific labor type
[5 empty] | FCEM |  |  | SAMPLE - Put in specific labor type
FY2004
FY2005
FY2006
FY2007
Allocations (WBS 81 only)
Instructions for Completing Form
(1) One form for each 3 digit WBS element (e.g., 111, 121, 452, etc.) => if no 3 digit WBS, use 2 digit WBS (e.g., 81, 82, 84)
(2) For Lab labor, provide estimate in manhours => provide estimate by specific labor type.
(3) For M&S, provide estimate in FY2002 direct dollars if procured by PPPL, or in fully loaded dollars if procured by ORNL
(4) Start and end date provided in month/year format => March/2003

## Engr
WBS 132 PF Coils
Engineering, Title I, II and III
Description:
This effort covers all Title I, II, and III engineering for the PF coils. All installation oversight will be performed as part of WBS 7. |  |  |  |  | Labor category
[5 empty] | total fraction | EAEM |  | EADM |  | ORNL Eng |  | ORNL Physics |  | PPPL Physics
| multiplier | unit | no. | hours |  | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
Title I, II design
Pro-E models (avg) | 16 | hrs/model | 33 | 528 | 1 | 0.25 | 132 | 0.5 | 264 | 0.25 | 132 | 0 | 0 | 0 | 0
assy dwgs | 40 | hrs/dwg | 9 | 360 | 1 | 0 | 0 | 1 | 360 | 0 | 0 | 0 | 0 | 0 | 0
Detail drawings | 16 | hrs/dwg | 30 | 480 | 1 | 0 | 0 | 1 | 480 | 0 | 0 | 0 | 0 | 0 | 0
installation dwg | 40 | hrs/dwg | 4 | 160 | 1 | 0 | 0 | 1 | 160 | 0 | 0 | 0 | 0 | 0 | 0
cooling schematic | 20 | hrs/dwg | 5 | 100 | 1 | 0 | 0 | 1 | 100 | 0 | 0 | 0 | 0 | 0 | 0
electrical schematic | 20 | hrs/dwg | 5 | 100 | 1 | 0 | 0 | 1 | 100 | 0 | 0 | 0 | 0 | 0 | 0
I&C schematic | 20 | hrs/dwg | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
stress analysis | 40 | hrs/calc | 3 | 120 | 1 | 1 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
thermal analysis | 40 | hrs/calc | 2 | 80 | 1 | 1 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
special analysis (electromagnetics) | 80 | hrs/calc | 1 | 80 | 1 | 0.5 | 40 | 0 | 0 | 0.5 | 40 | 0 | 0 | 0 | 0
procurement/fab specifications | 80 | hrs/spec | 4 | 320 | 1 | 1 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
preliminary and final design reviews | 80 | hrs/rev | 0 | 0 | 1 | 0.8 | 0 | 0 | 0 | 0.2 | 0 | 0 | 0 | 0 | 0
meetings/reporting/presentations | 10% | % of tot | 2328 | 232.8 | 1 | 0.8 | 186.24 | 0 | 0 | 0.2 | 46.56 | 0 | 0 | 0 | 0
subtotal |  |  |  | 2560.8 |  |  | 878.24 |  | 1464 |  | 218.56 |  | 0 |  | 0
[5 empty] | total fraction | EAEM |  | EASM |  | EADM |  | ORNL Eng
Title III | [5 empty] | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
vendor oversight, inspection | 8 | hrs/wk | 52 | 416 | 1 | 1 | 416 | 0 | 0 | 0 | 0 | 0 | 0
Disposition of deviation requests and non-conformances | 4 | hrs/wk | 78 | 312 | 1 | 0.8 | 249.6 | 0 | 0 | 0 | 0 | 0.2 | 62.4
As-built drawings | 4 | hrs/dwg | 48 | 192 | 0.7 | 0.2 | 38.4 | 0 | 0 | 0.5 | 96 | 0 | 0
subtotal |  |  |  | 920 |  |  | 704 |  | 0 |  | 96 |  | 62.4
Schedule assumptions | start | duration (weeks) | end
Title I Design | 2003-10-26 | 18 | 2004-02-29
Title II Design | 2004-02-29 | 18 | 2004-07-04
Procurement | 2004-07-04 | 52 | 2005-07-03
In-house fab / sub-assy | 2005-07-03 | 0 | 2005-07-03
Installation / final assembly | 2005-07-03 | 26 | 2006-01-01
Notes and worksheets
Central solenoid assembly design
| total | integrated assembly | PF!,PF2, PF3 coils |  |  | PF4 coils | PF5 coils | PF6 coils
Pro-E models | 33 | 1 | 8 |  |  | 8 | 8 | 8 | models of all parts
assy dwgs | 9 | 1 | 2 |  |  | 2 | 2 | 2 | double pancake, crossover/lead area, structure tube, overall assy
Detail drawings | 30 | 6 | 6 |  |  | 6 | 6 | 6 | winding, lead blocks, crossover fillers, structure tube, spacer blocks
installation dwg | 4 | 1 |  |  |  | 1 | 1 | 1
cooling schematic | 5 |  | 2 |  |  | 1 | 1 | 1
electrical schematic | 5 |  | 2 |  |  | 1 | 1 | 1
I&C schematic | 0 |  |  |  |  | 0 | 0 | 0 | covered in WBS 134
stress analysis | 3 | 1 | 2 |  |  | 0 | 0 | 0 | global and local analysis of winding pack and lead regions
thermal analysis | 2 |  | 2 |  |  | 0 | 0 | 0 | global and local analysis of winding pack and lead regions
special analysis | 1 | 1 |  |  |  | 0 | 0 | 0 | em analysis of lead area, general analysis in WBS 171
procurement specifications | 4 | 1 |  |  |  | 1 | 1 | 1 | one procurement specification for central solenoid assembly
preliminary and final design reviews | 0 |  |  |  |  | 0 | 0 | 0 | standard reviews
meetings/reporting/presentations | 10%
CS Solenoid Support Structure => Moved from WBS 152
Engineering, Title I, II and III
Description:
This effort covers all Title I, II, and III engineering for the coil support structure, which includes the TF and PF structure, the interface structure between the TF coil structure and the modular coil shell assembly, and the interface structure to the base assembly. The pieces of structure are procured via one or more fixed price contracts. All installation oversight will be performed as part of WBS 7. |  |  |  |  | Labor category
[5 empty] | total fraction | EAEM |  | EADM |  | ORNL Eng |  | ORNL Physics |  | PPPL Physics
| multiplier | unit | no. | hours |  | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
Title I, II design
Pro-E models (avg) | 24 | hrs/model | 8 | 192 | 1 | 0.5 | 96 | 0.25 | 48 | 0.25 | 48 | 0 | 0 | 0 | 0
assy dwgs | 40 | hrs/dwg | 6 | 240 | 1 | 0.5 | 120 | 0.5 | 120 | 0 | 0 | 0 | 0 | 0 | 0
Detail drawings | 20 | hrs/dwg | 6 | 120 | 1 | 0.5 | 60 | 0.5 | 60 | 0 | 0 | 0 | 0 | 0 | 0
installation dwg | 40 | hrs/dwg | 1 | 40 | 1 | 0 | 0 | 0.5 | 20 | 0.5 | 20 | 0 | 0 | 0 | 0
cooling schematic | 20 | hrs/dwg | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
electrical schematic | 20 | hrs/dwg | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
I&C schematic | 20 | hrs/dwg | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
stress analysis | 40 | hrs/calc | 1 | 40 | 1 | 1 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
thermal analysis | 40 | hrs/calc | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
special analysis (electromagnetics) | 40 | hrs/calc | 0 | 0 | 1 | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0
procurement/fab specifications | 40 | hrs/spec | 1 | 40 | 1 | 1 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
preliminary and final design reviews | 80 | hrs/rev | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
meetings/reporting/presentations | 10% | % of tot | 672 | 67.2 | 1 | 1 | 67.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
subtotal |  |  |  | 739.2 |  |  | 423.2 |  | 248 |  | 68 |  | 0 |  | 0
[5 empty] | total fraction | EAEM |  | EASM |  | EADM |  | ORNL Eng
Title III | [5 empty] | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
vendor oversight, inspection | 2 | hrs/wk | 52 | 104 | 1 | 1 | 104 | 0 | 0 | 0 | 0 | 0 | 0
Disposition of deviation requests and non-conformances | 2 | hrs/wk | 78 | 156 | 1 | 0.8 | 124.8 | 0 | 0 | 0 | 0 | 0.2 | 31.2
As-built drawings | 8 | hrs/dwg | 13 | 104 | 1 | 0.2 | 20.8 | 0 | 0 | 0.8 | 83.2 | 0 | 0
subtotal |  |  |  | 364 |  |  | 249.6 |  | 0 |  | 83.2 |  | 31.2
Schedule assumptions | start | duration (weeks) | end
Title I Design | 2003-10-26 | 18 | 2004-02-29
Title II Design | 2004-02-29 | 18 | 2004-07-04
Procurement | 2004-07-04 | 52 | 2005-07-03
In-house fab / sub-assy | 2005-07-03 | 0 | 2005-07-03
Installation / final assembly | 2005-07-03 | 26 | 2006-01-01
Notes and worksheets
Coil support structure
| total | integrated PF1,PF2,PF3 assembly | brackets to TF | spacers and tie rods
Pro-E models | 8 | 2 | 2 | 4 |  |  | models of all parts
assy dwgs | 6 | 3 | 1 | 2 |  |  | typical assemblies of half field period, whole field period, and full structure
Detail drawings | 6 | 0 | 2 | 4 |  |  | each part is detailed
installation dwg | 1 | 1 | 0 | 0
cooling schematic | 0 | [5 empty] | assume passive cooling of base interface structure
electrical schematic | 0
I&C schematic | 0 | [5 empty] | covered in WBS 153
stress analysis | 1 | 1 |  |  |  |  | local analyses of each subsystem
thermal analysis | 0
special analysis | 0 | [5 empty] | seismic analysis
procurement specifications | 1 | 1 | 0 | 0 |  |  | one procurement specification for each major system
preliminary and final design reviews | 0 | [5 empty] | standard reviews
meetings/reporting/presentations | 10%
Formulas:
multiplier = [no.]-[unit]*7
no. = [multiplier, row below]

## R&D
WBS 132 PF Coils
R&D
Description:
No R&D is associated with this WBS
Summary
Purchased Design Services
Vendor surveillance via | 0
subtotal | 0 |  | w/o G&A
Procured Hardware/Material
Cast and machined winding forms | 0
subtotal | 0 |  | w/o G&A
Subcontractor labor rates:
design rate: | 130 | per hour
fab rate | 60 | per hour
inspection/technician rate | 80 | per hour
CS Support Structure => Moved from old WBS 152
R&D
Description:
No R&D is associated with this WBS
Summary
Purchased Design Services
Vendor surveillance via | 0
subtotal | 0 |  | w/o G&A
Procured Hardware/Material
Cast and machined winding forms | 0
subtotal | 0 |  | w/o G&A
Subcontractor labor rates:
design rate: | 130 | per hour
fab rate | 60 | per hour
inspection/technician rate | 80 | per hour

## M&S
WBS 132 PF Coils
Materials and Subcontracts (M&S)
Description:
This effort covers the manufacturing costs for the center solenoid assembly, which includes the PF1 and PF2 coil pairs, the central solenoid structure, and the integration of the coils and structure. The coils and structure are procured via a fixed price contract. All installation oversight will be performed as part of WBS 7.
Purchased parts:
PF Coil windings | 852103.2437 | see notes below
Centerstack structure | 0 | see wbs 152
Centerstack assembly/integration | 0 | see wbs 152
subtotal, purchased parts | 852103.2437
outside engr rate = | 130 | $ per hour
outside fab rate = | 60 | $ per hour
outside inspection/technician rate = | 80 | $ per hour
Worksheets:
PF1,2 Winding geometry
|  | PF1 | PF2 | PF3 | PF4 | PF5 | PF6
Max. Total current | MA-turns | 1.6315 | 1.6315 | 1.2857 | 1.1913 | 0.20885 | 0.11399
radius | m | 0.21907 | 0.21907 | 0.21907 | 0.52194 | 2.2232 | 2.7205
height, Z | m | 0.23973 | 0.71915 | 1.1986 | 1.5834 | 1.5303 | 0.95407
bundle dr | mm | 96.9264 | 96.9264 | 96.9264 | 188.4934 | 96.9264 | 51.1302
bundle dz | mm | 426.593 | 426.593 | 426.593 | 249.555 | 161.036 | 183.1594
gross cur. dens. | A/mm^2 | 39.4581 | 39.4581 | 31.0946 | 25.3251 | 13.3803 | 12.1717
no. of turns |  | 72 | 72 | 72 | 80 | 24 | 14
current per turn | A | 22660 | 22660 | 17857 | 19000 | 7916.6667 | 11250
packing fraction |  | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75
approx. wt./coil | kg | 366.2495 | 366.2495 | 0 | 0 | 0 | 0
length per turn | m | 1.3765 | 1.3765 | 1.3765 | 3.2795 | 13.9687 | 17.0932
total length of cu per coil | m | 99.1072 | 99.1072 | 99.1072 | 262.358 | 335.2485 | 239.3048
turn height | mm | 19.9898 | 19.9898 | 19.9898 | 19.9898 | 19.9898 | 19.9898
turn width | mm | 19.9898 | 19.9898 | 19.9898 | 19.9898 | 19.9898 | 19.9898
coolant hole dia. | mm | 8.9916 | 8.9916 | 8.9916 | 8.9916 | 8.9916 | 8.9916
corner radii | mm | 1.016 | 1.016 | 1.016 | 1.016 | 1.016 | 1.016
conductor area | mm^2 | 335.2075 | 335.2075 | 335.2075 | 335.2075 | 335.2075 | 335.2075
Initial resistance of coil | ohms | 0.00058836 | 0.00058836 | 0.00058836 | 0.0015575 | 0.0019902 | 0.0014207
calculated coil Cu wt. | kg | 285.0402 | 285.0402 | 285.0402 | 754.5625 | 964.2015 | 688.2597
Cu density | 8.58e-06 | kg/mm^3
Resistivity | 1.99e-09 | ohm-m
copper extrusion cost (Outokumpu standard size) | 10 | $/kg | (latest quote is ~ $8.16/kg)
PF Coil winding cost details | Ref. P. Heitzenroeder
I. Tooling by vendor |  | PF1 | PF2 | PF3 | PF4 | PF5 | PF6
Tooling engineering/mfg. Plans | hrs. | 80 | 0 | 0 | 80 | 80 | 80
Tooling engineering | $ | 10400 | 0 | 0 | 10400 | 10400 | 10400
Tooling design | hrs. | 120 | 0 | 0 | 100 | 100 | 100
Tooling design | $ | 9600 | 0 | 0 | 8000 | 8000 | 8000
Tooling fabrication (% of coil matl) | $ | 11095.0981 | 9845.0981 | 11095.0981 | 25065.1288 | 32194.4613 | 24337.0852
Total tooling design hours | hrs. | 200 | 0 | 0 | 180 | 180 | 180 |  | (half engineer; half designer)
Total tooling cost | $ | 31095.0981 | 9845.0981 | 11095.0981 | 43465.1288 | 50594.4613 | 42737.0852 | 188831.9695
II. Materials
Ordering/stocking materials | hrs. | 200 | 200 | 200 | 200 | 200 | 200 | technician hours
" " | $ | 16000 | 16000 | 16000 | 16000 | 16000 | 16000
copper extrusion cost | 10 | $/kg | $/kg | $/kg | $/kg | $/kg | $/kg
Copper order factor | 1.25 | factor | factor | factor | factor | factor | factor | assume 25% overage
copper cost , 2 coils ; | $ | 7126.0054 | 7126.0054 | 7126.0054 | 18864.0625 | 24105.0387 | 17206.4917
misc matl -$ per lb of Cu in coils | 2 | $/kg | $/kg | $/kg | $/kg | $/kg | $/kg
misc. matl. Cost, pair of coils | $ | 1140.1609 | 1140.1609 | 1140.1609 | 3018.25 | 3856.8062 | 2753.0387
glass insul width | mm | 25.4 | 25.4 | 25.4 | 25.4 | 25.4 | 25.4
turn insul.: length/meter of cond./layer | m/m | 3.148 | 3.148 | 3.148 | 3.148 | 3.148 | 3.148
turn ins. Tape Thickness | mm | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19
No. half lapped layers | # | 2 | 2 | 2 | 2 | 2 | 2
meters of ins. /roll | m | 10 | 10 | 10 | 10 | 10 | 10
no. rolls/coil | # | 124.7958 | 124.7958 | 124.7958 | 330.3612 | 422.1449 | 301.3326
insulation waste factor | multiplier | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3
total rolls of turn ins. reqd., 2 coils | # | 324.469 | 324.469 | 324.469 | 858.939 | 1097.5768 | 783.4647
turn insulation cost per roll | $/roll | 4 | 4 | 4 | 4 | 4 | 4
Kapton insul width | mm | 25.4 | 25.4 | 25.4 | 25.4 | 25.4 | 25.4
turn insul. length/meter of cond./layer | m/m | 3.148 | 3.148 | 3.148 | 3.148 | 3.148 | 3.148
turn ins. Tape Thickness | mm | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19
No. half lapped layers | # | 1 | 1 | 1 | 1 | 1 | 1
meters of ins. /roll | m | 10 | 10 | 10 | 10 | 10 | 10
no. rolls/coil | # | 62.3979 | 62.3979 | 62.3979 | 165.1806 | 211.0725 | 150.6663
insulation waste factor | multiplier | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3
total rolls of turn ins. reqd., 2 coils | # | 162.2345 | 162.2345 | 162.2345 | 429.4695 | 548.7884 | 391.7323
turn insulation cost per roll | $/roll | 40 | 40 | 40 | 40 | 40 | 40
turn insulation total cost, 2 coils | $ | 7787.2567 | 7787.2567 | 7787.2567 | 20614.5362 | 26341.8441 | 18803.1526
ground wall tape thickness | mm | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38
No. half lapped layers | # | 2 | 2 | 2 | 2 | 2 | 2
total ground wall thick. | mm | 1.52 | 1.52 | 1.52 | 1.52 | 1.52 | 1.52
ground wall tape width | cm | 6 | 6 | 6 | 6 | 6 | 6
gw tape length reqd. | m | 48.0412 | 48.0412 | 48.0412 | 95.7712 | 240.2264 | 266.9839
meters of ins. /roll | m | 10 | 10 | 10 | 10 | 10 | 10
no. rolls/coil | # | 4.8041 | 4.8041 | 4.8041 | 9.5771 | 24.0226 | 26.6984
insulation waste factor | multiplier | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3
no. rolls of GW insulation, pair of coils | # | 12.4907 | 12.4907 | 12.4907 | 24.9005 | 62.4589 | 69.4158
GW tape cost per roll | $ | 50 | 50 | 50 | 50 | 50 | 50
GW insulation cost, 2 coils | $ | 624.5361 | 624.5361 | 624.5361 | 1245.0261 | 3122.9435 | 3470.7908
Epoxy volume reqd. (15% void fraction) | l | 8.5373 | 8.5373 | 8.5373 | 23.1397 | 32.7048 | 24.0116
Epoxy cost/liter | $/l | 30 | 30 | 30 | 30 | 30 | 30
Epoxy cost for pair of coils | $ | 512.2371 | 512.2371 | 512.2371 | 1388.3828 | 1962.29 | 1440.6966
Leads and coolant connections/coil | $ | 2500 | 1250 | 2500 | 2500 | 2500 | 2500
Leads & coolant con's., pair of coils | $ | 5000 | 2500 | 5000 | 5000 | 5000 | 5000
II. Material cost for coil pairs | $ | 22190.1962 | 19690.1962 | 22190.1962 | 50130.2577 | 64388.9225 | 48674.1704 | 227263.9391 | M&S w/o G&A
III. Labor
Tooling prep. | shifts | 1 | 1 | 1 | 1 | 1 | 1
turns/8 hr. shift, incl. Insulation application | # | 8 | 8 | 8 | 8 | 8 | 8
crew size | # | 3 | 3 | 3 | 3 | 3 | 3
Shifts reqd. per coil | # | 9 | 9 | 9 | 10 | 3 | 1.75
person-hours to prep & wind coil | hrs. | 240 | 240 | 240 | 264 | 96 | 66
technical oversight/coil (half time) | hrs. | 62.5997 | 62.5997 | 62.5997 | 65.268 | 58.3472 | 60.7557 | half time for all shifts
tech. Oversight cost | $ | 8137.9549 | 8137.9549 | 8137.9549 | 8484.8381 | 7585.1345 | 7898.2409
GW application time-rolls/shift | # | 12 | 12 | 12 | 12 | 12 | 12
crew size for GW | # | 2 | 2 | 2 | 2 | 2 | 2
person hours to apply | hrs. | 8.3271 | 8.3271 | 8.3271 | 16.6003 | 41.6392 | 46.2772
VPI prep & process.- hrs/ m-coil | hrs. | 24 | 24 | 24 | 8 | 4 | 4
crew size for VPI | # | 3 | 3 | 3 | 3 | 3 | 3
person hours/coil for VPI | hrs. | 99.1072 | 99.1072 | 99.1072 | 78.7074 | 167.6243 | 205.1184
elec/hydraulic test | hrs. | 16 | 16 | 16 | 16 | 16 | 16
Total labor hours for 2 coils | hrs. | 726.8687 | 726.8687 | 726.8687 | 750.6155 | 642.527 | 666.7912 | (technician labor)
III.Total Winding Labor Cost | $ | 74425.4047 | 74425.4047 | 74425.4047 | 77018.9147 | 66572.4302 | 69139.7761
Total Manf Costs,by Coil type |  | 127710.6989 | 103960.6989 | 107710.6989 | 170614.3012 | 181555.8139 | 160551.0318 | 852103.2437
CS Support Structure => Moved from old WBS 152
Materials and Subcontracts (M&S)
Description:
This effort covers manufacturing of the central solenoid support structure and integration of the PF1, PF2, and PF3 with the structure. The pieces of structure are procured via one or more fixed price contracts.
Purchased parts:
upper and lower interface hub | 45904 | see notes below
brackets to TF structure | 13280
spacers and tie rods | 23261.9467
solenoid integration | 19400
subtotal, purchased parts | 101845.9467
outside engr rate = | 130 | $ per hour
outside fab rate = | 60 | $ per hour
outside inspection/technician rate = | 80 | $ per hour
Worksheet:
Center solenoid upper/lower interface hub
Fabrication / parts costs
Item / description |  |  | Value | Unit | Cost $/unit | No. | Cost $
Upper and lower solenoid hub casting |  |  | 52 | lbs | 12 | 6 | 3744
Machining of upper and lower hub casting, 2 setups |  |  | 64 | hrs | 80 | 6 | 30720
Pattern for upper and lower hub casting (120 deg.) |  |  | 1 | lot | 10000 | 1 | 10000
Inspection |  |  | 8 | hrs | 80 | 6 | 3840
Insulation and shims between castings |  |  | 1 | interface | 1500 | 12 | 18000
misc bolts and assembly hardware |  |  | 1 | lot | 10000 | 1 | 10000
|  |  |  | subtotal Integrated TF structure fab./matl |  |  | 44464
Subassembly costs
Item / description |  |  | Value | Unit | Cost $/unit | No. | Cost $
Pre-assembly and fit check, crew of 2, 16 hours/assy |  |  | 48 | hrs | 0 | 2 | 0
technical oversight |  |  | 12 | hrs | 60 | 2 | 1440
|  |  |  | subtotal Integrated TF structure pre-assembly |  |  | 1440
|  |  |  | total, Integrated TF structure |  |  | 45904
Brackets to TF structure
Fabrication / parts costs
Item / description |  |  | Value | Unit | Cost $/unit | No. | Cost $
Upper tie plate to TF coil structure |  |  | 500 | lbs | 8 | 1 | 4000
Machining of upper and lower crown segment casting |  |  | 40 | hrs | 80 | 2 | 6400
lower brackets to TF coil structure |  |  | 30 | lbs | 8 | 6 | 1440
machining of lower brackets |  |  | 16 | hrs | 60 | 6 | 5760
|  |  |  | subtotal brackets to TF coil fab./matl |  |  | 11840
Subassembly costs
Item / description |  |  | Value | Unit | Cost $/unit | No. | Cost $
Pre-assembly and fit check |  |  | 40 | hrs | 0 | 2 | 0
technical oversight |  |  | 12 | hrs | 60 | 2 | 1440
|  |  |  | subtotal bracket fit check and pre-assembly |  |  | 1440
|  |  |  | total, brackets to TF coil struct. |  |  | 13280
Center Solenoid assembly hardware
Item / Description |  | Value | Unit | Cost $/unit | No Units | Cost $
1"OD, 96" long Tie Rods |  | 90.4779 | lbs | 25 | 6 | 2261.9467
G-10 separation discs & misc. |  | 150 | lbs | 20 | 7 | 21000
[5 empty] | Total: | 23261.9467
Assembly and integration costs
Task | shifts | crew | hours | FY-03$
Measure and adjust separation discs | 3 | 2 | 48 | 2880
Route leads to top and bottom | 4 | 2 | 64 | 3840
Fit up coils to cylinder and grout | 8 | 2 | 128 | 7680
Oversight (half time) | 7 | 1 | 60 | 0
misc materials |  |  |  | 5000
|  |  | Total: | 19400

## Fab_assy
WBS 132 PF Coils
In-house Fabrication and Assembly
Description:
No fabrication and assembly is associated with this WBS |  |  |  |  | Labor category
[5 empty] | total fraction | EAEM |  | EASM, EMSM |  | EMTB |  | EADM
| multiplier | unit | no. | hours |  | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
Fab operations summary
| 0 | hrs/lot | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 0 | hrs/line | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | hrs / coil | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
subtotal |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0
[5 empty] | total fraction | EAEM |  | EASM, EMSM |  | EMTB |  | EADM
Assembly operations summary | [5 empty] | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
| 0 | hr/lot | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| 0 | hr/lot | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | hr/coil | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | hours | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
subtotal |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0
CS Support Structure => Moved from old WBS 152
In-house Fabrication and Assembly
Description:
No fabrication and assembly is associated with this WBS |  |  |  |  | Labor category
[5 empty] | total fraction | EAEM |  | EASM, EMSM |  | EMTB |  | EADM
| multiplier | unit | no. | hours |  | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
Fab operations summary
| 0 | hrs/lot | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 0 | hrs/line | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | hrs / coil | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
subtotal |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0
[5 empty] | total fraction | EAEM |  | EASM, EMSM |  | EMTB |  | EADM
Assembly operations summary | [5 empty] | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
| 0 | hr/lot | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| 0 | hr/lot | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | hr/coil | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | hours | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
subtotal |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0

## Installation
WBS 132 PF Coils
Installation
This element is not part of the WBS 1 scope of work
CS Support Structure => Moved from old WBS 152
Installation
This element is not part of the WBS 1 scope of work