## Fab Project
WBS 141 Modular Coil Winding forms | [10 empty] | 17 |  | Duration of activity per fiscal year (weeks)
Labor
| Activity Title |  | Manhours | FY2003 $$ | Labor Type | Start Date Month/Yr | End Date Month/Yr | Comments |  |  |  | duration (weeks) | 2002-10-01 | 2003-10-01 | 2004-10-01 | 2005-10-01 | 2006-10-01 | 2007-10-01 | 2008-10-01
Preliminary Design (Title I)
|  | ( 48% of design schedule) | 203.0886 |  | EAEM | 2003-04-01 | 2003-10-09 | PPPL Engineer |  |  |  | 27.2857 | 26.1429 | 1.1429 | 0 | 0 | 0 | 0 |  | 48.3544 | 48.35% | of design is preliminary design
|  |  | 0 |  | EADM | 2003-04-01 | 2003-10-09 | PPPL Designer |  |  |  | 27.2857 | 26.1429 | 1.1429 | 0 | 0 | 0 | 0
|  |  | 3100.0025 |  | ORNL Eng | 2003-04-01 | 2003-10-09 | Composite of ORNL Engineer / Designer |  |  |  | 27.2857 | 26.1429 | 1.1429 | 0 | 0 | 0 | 0
|  |  | 0 |  | ORNL Phys. | 2003-04-01 | 2003-10-09 | Composite of ORNL Physics / scientific |  |  |  | 27.2857 | 26.1429 | 1.1429 | 0 | 0 | 0 | 0
|  |  | 0 |  | PPPL Phys. | 2003-04-01 | 2003-10-09 | PPPL Physics/scientific |  |  |  | 27.2857 | 26.1429 | 1.1429 | 0 | 0 | 0 | 0
Final Design (Title II)
|  | ( 52% of design schedule) | 216.9114 |  | EAEM | 2003-10-09 | 2004-04-30 | PPPL Engineer |  |  |  | 29.1429 | 0 | 29.1429 | 0 | 0 | 0 | 0 |  | 51.6456 | 51.65% | of design schedule is final design
|  |  | 0 |  | EADM | 2003-10-09 | 2004-04-30 | PPPL Designer |  |  |  | 29.1429 | 0 | 29.1429 | 0 | 0 | 0 | 0
|  |  | 3310.9975 |  | ORNL Eng | 2003-10-09 | 2004-04-30 | Composite of ORNL Engineer / Designer |  |  |  | 29.1429 | 0 | 29.1429 | 0 | 0 | 0 | 0
|  |  | 0 |  | ORNL Phys. | 2003-10-09 | 2004-04-30 | Composite of ORNL Physicist |  |  |  | 29.1429 | 0 | 29.1429 | 0 | 0 | 0 | 0
|  |  | 0 |  | PPPL Phys. | 2003-10-09 | 2004-04-30 | PPPL Physics/scientific |  |  |  | 29.1429 | 0 | 29.1429 | 0 | 0 | 0 | 0
Lab R&D labor
|  |  | 228 |  | EAEM | 2003-04-01 | 2003-10-09 | PPPL Engineer |  |  |  | 27.2857 | 26.1429 | 1.1429 | 0 | 0 | 0 | 0
|  |  | 0 |  | EADM | 2003-04-01 | 2003-10-09 | PPPL Designer |  |  |  | 27.2857 | 26.1429 | 1.1429 | 0 | 0 | 0 | 0
|  |  | 1250.4 |  | ORNL Eng | 2003-04-01 | 2003-10-09 | Composite of ORNL Engineer / Designer |  |  |  | 27.2857 | 26.1429 | 1.1429 | 0 | 0 | 0 | 0
|  |  | 0 |  | EASM | 2003-04-01 | 2003-10-09 | PPPL monthly support |  |  |  | 27.2857 | 26.1429 | 1.1429 | 0 | 0 | 0 | 0
|  |  | 0 |  | EMTB | 2003-04-01 | 2003-10-09 | PPPL Technician |  |  |  | 27.2857 | 26.1429 | 1.1429 | 0 | 0 | 0 | 0
Lab Fab/Assembly/Installation (Title III)
|  |  | 341.6 |  | EAEM | 2004-04-30 | 2006-10-01 | PPPL Engineer |  |  |  | 126.2857 | 0 | 22 | 52.1429 | 52.1429 | 0 | 0
|  |  | 0 |  | EADM | 2004-04-30 | 2006-10-01 | PPPL Designer |  |  |  | 126.2857 | 0 | 22 | 52.1429 | 52.1429 | 0 | 0
|  |  | 1066.4 |  | ORNL Eng | 2004-04-30 | 2006-10-01 | Composite of ORNL Engineer / Designer |  |  |  | 126.2857 | 0 | 22 | 52.1429 | 52.1429 | 0 | 0
|  |  | 0 |  | EASM | 2004-04-30 | 2006-10-01 | PPPL monthly support |  |  |  | 126.2857 | 0 | 22 | 52.1429 | 52.1429 | 0 | 0
|  |  | 0 |  | EMTB | 2004-04-30 | 2006-10-01 | PPPL Technician |  |  |  | 126.2857 | 0 | 22 | 52.1429 | 52.1429 | 0 | 0
Labor | [11 empty] | R&D labor cost = |  | 197436
[12 empty] | total R&D costs |  | 1372436
Manhours per fiscal year by labor category
Level of Effort |  |  |  | FY2003 | FY2004 | FY2005 | FY2006 | FY2007 | FY2008 | TOTAL
| PPPL Engineer |  | EAEM | 413.0325 | 294.477 | 141.0452 | 141.0452 | 0 | 0 | 989.6 |  | 151408.8 | 153 | per hour
| PPPL Designer |  | EADM | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 100 | per hour
| Composite of ORNL Engineer / Designer |  | ORNL Eng | 4168.1867 | 3678.9888 | 440.3122 | 440.3122 | 0 | 0 | 8727.8 |  | 1134614 | 130 | per hour
| PPPL monthly support |  | EASM | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 100 | per hour
| PPPL Technician |  | EMTB | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 73 | per hour
| Composite of ORNL Physics / scientific |  | ORNL Phy | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 160 | per hour
| PPPL Physics/scientific |  | PPPL Phy | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 141 | per hour
[12 empty] | 989.6 | 151408.8 | PPPL
[12 empty] | 8727.8 | 1134614 | ORNL
M&S Costs
9717.4
| Activity Title |  |  | FY2003 $$ |  | Comment | [5 empty] | 9717.4
Manufacturing Development (R&D)
|  | Purchased Design Services |  | 0
|  | Procured Hardware/Material |  | 1175000
|  | Profit |  | 0 |  | included in hardware estimate
|  | total, manf/dev (R&D) |  | 1175000 |  | w/o G&A
Procured Hardware/Material
|  | set of 18 machined coil forms |  | 4839300
|  | Profit |  | 0 |  | included in hardware estimate
|  | total, procured hdwe/matl. |  | 4839300 |  | w/o G&A
| Purchased Design Services |  |  | 0 |  | no purchased services anticipated
| Procured Installation/Assembly Costs |  |  | 0 |  | All installation and assembly costs are included in WBS 7
Other Costs
| Activity Title |  |  | FY2003 $$ |  | Comment
| Travel |  |  | 48000 |  | at least one trip per month is expected for two years
Summary Costs
| Activity Title |  | Manhours | FY2003 $$ |  | Comment
Labor
| PPPL Effort |  | 989.6 | 151408.8 |  | Assumed rates: |  | EASM | 100 $/hr
| ORNL effort |  | 8727.8 | 1134614 |  | EAEM | 153 $/hr | EMTB | 73 $/hr
|  | subtotal, labor | 9717.4 | 1286022.8 |  | EADM | 100 $/hr | PPPL Phys | 141 $/hr
[6 empty] | ORNL Eng | 130 $/hr | ORNL Phys | 160 $/hr
M&S, Other
| Manufacturing Development (R&D) |  |  | 1175000
| Procured Hardware/Material |  |  | 4839300
| Purchased Design Services |  |  | 0
| Procured Installation/Assembly Costs |  |  | 0
| Travel |  |  | 48000
|  | subtotal, M&S |  | 6062300
| G&A |  |  | 430750 |  | 25% | on all purchased materials, subcontracts, travel
[6 empty] | 1084825 | G&A adjustment on large procurement
| Subtotal without contingency |  |  | 7779072.8
| Contingency |  |  | 3111629.12 |  | 40% | Overall on this WBS
| Total cost |  |  | 10890701.92

## Other Costs
|  | 1808-NCSX-1701 | [5 empty] | XX represents the 2 digit WBS code
| Activity Title |  | Manhours | FY2002 $$ | Labor Type | Start Date Month/Year | End Date Month/Year | Comments
Level of Effort | [7 empty] | Research Prep Activities
FY2003
[5 empty] | RMRM3 |  |  | SAMPLE - Put in specific labor type
[5 empty] | FCEM |  |  | SAMPLE - Put in specific labor type
FY2004
FY2005
FY2006
FY2007
Research Planning/Preparations
FY2003
[5 empty] | RMRM3 |  |  | SAMPLE - Put in specific labor type
[5 empty] | FCEM |  |  | SAMPLE - Put in specific labor type
FY2004
FY2005
FY2006
FY2007
Operational Spares
M&S Costs
Manufacturing Development
Purchased Design Services
|  | Procured Hardware/Material | [5 empty] | Include any M&S carried over from FY2002
| Procured Hardware/Material | [6 empty] | Identify each procurement over $100K individually
Purchased Design Services
Procured Installation/Assembly Costs
Other Costs
Travel
FY2003
[5 empty] | RMRM3 |  |  | SAMPLE - Put in specific labor type
[5 empty] | FCEM |  |  | SAMPLE - Put in specific labor type
FY2004
FY2005
FY2006
FY2007
Allocations (WBS 81 only)
Instructions for Completing Form
(1) One form for each 3 digit WBS element (e.g., 111, 121, 452, etc.) => if no 3 digit WBS, use 2 digit WBS (e.g., 81, 82, 84)
(2) For Lab labor, provide estimate in manhours => provide estimate by specific labor type.
(3) For M&S, provide estimate in FY2002 direct dollars if procured by PPPL, or in fully loaded dollars if procured by ORNL
(4) Start and end date provided in month/year format => March/2003

## Engr
WBS 141 Modular Coil Winding forms
Engineering, Title I, II and III
Description:
This effort covers all Title I, II, and III engineering for the modular coil winding forms. The coils will be wound in-house by PPPL under WBS 142. All installation oversight will be performed as part of WBS 7. |  |  |  |  | Labor category
[5 empty] | total fraction | EAEM |  | EADM |  | ORNL Eng |  | ORNL Physics |  | PPPL Physics
| multiplier | unit | no. | hours |  | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
Title I, II design
Pro-E models (avg) | 210 | hrs/model | 15 | 3150 | 1 | 0 | 0 | 0 | 0 | 1 | 3150 | 0 | 0 | 0 | 0
assy dwgs | 40 | hrs/dwg | 9 | 360 | 1 | 0 | 0 | 0 | 0 | 1 | 360 | 0 | 0 | 0 | 0
Detail drawings | 40 | hrs/dwg | 36 | 1440 | 1 | 0 | 0 | 0 | 0 | 1 | 1440 | 0 | 0 | 0 | 0
installation dwg | 40 | hrs/dwg | 6 | 240 | 1 | 0 | 0 | 0 | 0 | 1 | 240 | 0 | 0 | 0 | 0
cooling schematic | 0 | hrs/dwg | 3 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
electrical schematic | 0 | hrs/dwg | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
I&C schematic | 20 | hrs/dwg | 3 | 60 | 1 | 0 | 0 | 0 | 0 | 1 | 60 | 0 | 0 | 0 | 0
stress analysis | 80 | hrs/calc | 6 | 480 | 1 | 0.5 | 240 | 0 | 0 | 0.5 | 240 | 0 | 0 | 0 | 0
thermal analysis | 40 | hrs/calc | 3 | 120 | 1 | 0.5 | 60 | 0 | 0 | 0.5 | 60 | 0 | 0 | 0 | 0
special analysis (electromagnetics) | 160 | hrs/calc | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
procurement/fab specifications | 80 | hrs/spec | 2 | 160 | 1 | 0.75 | 120 | 0 | 0 | 0.25 | 40 | 0 | 0 | 0 | 0
preliminary and final design reviews | 100 | hrs/rev | 2 | 200 | 1 | 0 | 0 | 0 | 0 | 1 | 200 | 0 | 0 | 0 | 0
meetings/reporting/presentations | 10% | % of tot | 6210 | 621 | 1 | 0 | 0 | 0 | 0 | 1 | 621 | 0 | 0 | 0 | 0
subtotal |  |  |  | 6831 |  |  | 420 |  | 0 |  | 6411 |  | 0 |  | 0
[5 empty] | total fraction | EAEM |  | EASM |  | EADM |  | ORNL Eng
Title III | [5 empty] | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
vendor oversight, inspection | 8 | hrs/wk | 61 | 488 | 1 | 0.5 | 244 | 0 | 0 | 0 | 0 | 0.5 | 244
Disposition of deviation requests and non-conformances | 8 | hrs/wk | 61 | 488 | 1 | 0.2 | 97.6 | 0 | 0 | 0 | 0 | 0.8 | 390.4
As-built drawings | 8 | hrs/dwg | 54 | 432 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 432
subtotal |  |  |  | 1408 |  |  | 341.6 |  | 0 |  | 0 |  | 1066.4
Schedule assumptions | start | duration (weeks) | end
Title I Design | 2003-04-01 | 27.2857 | 2003-10-09
Title II Design | 2003-10-09 | 29.1429 | 2004-04-30
Procurement | 2004-04-30 | 61 | 2005-07-01
In-house fab / sub-assy | 2005-01-04 | 72 | 2006-05-23
Installation / final assembly | 2005-09-28 | 52.5714 | 2006-10-01
Notes and worksheets
Coil Form Design
| total | per coil | Casting form | bolts and shim hardware
Pro-E models | 15 | 5 | 2 | 3
assy dwgs | 9 | 3 | 1 | 2
Detail drawings | 36 | 12 | 6 | 6 |  | flanges, TF interfaces, port interfaces, left and right winding cavities
installation dwg | 6 | 2 | 1 | 1
cooling schematic | 3 | 1 | 1
electrical schematic | 0 | 0
I&C schematic | 3 | 1 | 1
stress analysis | 6 | 2 | 1 | 1
thermal analysis | 3 | 1 | 1
special analysis | 0 | em analysis covered under WBS 171
procurement specifications | 2 | procurement specifications for set of machined castings and for hardware, revise to reflect R&D results
preliminary and final design reviews | 2 | reviews
meetings/reporting/presentations | 15%
Formulas:
multiplier = [no., row above]

## R&D
WBS 141 Modular Coil Winding forms
R&D
Description:
This effort covers all R&D necessary for developing the casting and machining processes for the winding forms. This R&D will be performed by at two vendors, after which a fixed price subcontract will be let for the production castings.
Summary
Purchased Design Services
Vendor surveillance via | 16074
subtotal | 16070 |  | w/o G&A
Procured Hardware/Material
Cast and machined winding forms | 1175000 |  | allocations for 2 forms from different vendors
subtotal | 1175000 |  | w/o G&A
Subcontractor labor rates:
design rate: | 120 | per hour
fab rate | 60 | per hour
inspection/technician rate | 80 | per hour
Labor category
R&D design | [5 empty] | total fraction | EAEM |  | EADM |  | ORNL Eng |  | EASM |  | Vendor
|  | unit | no. | hours |  |  | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
Task
Pro-E models | 60 | hrs/model | 6 | 360 |  | 1 | 0 | 0 | 0 | 0 | 1 | 360 | 0 | 0 | 0 | 0
assy dwgs | 20 | hrs/dwg | 6 | 120 |  | 1 | 0 | 0 | 0 | 0 | 1 | 120 | 0 | 0 | 0 | 0
Detail drawings | 8 | hrs/dwg | 24 | 192 |  | 1 | 0 | 0 | 0 | 0 | 1 | 192 | 0 | 0 | 0 | 0
installation dwg | 0 | hrs/dwg | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
cooling schematic | 0 | hrs/dwg | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
electrical schematic | 0 | hrs/dwg | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
I&C schematic | 0 | hrs/dwg | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
special analysis | 0 | hrs/calc | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
procurement specifications | 80 | hrs/spec | 1 | 80 |  | 1 | 0 | 0 | 0 | 0 | 1 | 80 | 0 | 0 | 0 | 0
vendor shop drawings | 0 | hrs/dwg | 0 | 0 |  | 1 | [8 empty] | 1 | 0
vendor part programming | 0 | hrs/model | 0 | 0 |  | 1 | [8 empty] | 1 | 0
vendor misc engineering | 0% | % of tot | 0 | 0 |  | 1 | [8 empty] | 1 | 0
preliminary and final design reviews | 40 | hrs/rev | 1 | 40 |  | 1 | 0 | 0 | 0 | 0 | 1 | 40 | 0 | 0 | 0 | 0
meetings/reporting/presentations | 20% | % of tot | 792 | 158.4 |  | 1 | 0 | 0 | 0 | 0 | 1 | 158.4 | 0 | 0 | 0 | 0
subtotal |  |  |  | 950.4 |  |  |  | 0 |  | 0 |  | 950.4 |  | 0 |  | 0
[5 empty] | total fraction |  | EAEM |  | EADM |  | ORNL Eng |  | EASM, EMSM |  | EMTB
[7 empty] | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
R&D Tasks and Title III (see notes)
Procurement assistance | 8 | hrs/wk | 12 | 96 |  | 1 | 0.5 | 48 | 0 | 0 | 0.5 | 48 | 0 | 0 | 0 | 0
Vendor surveillance, oversight | 8 | hrs/wk | 36 | 288 |  | 1 | 0.5 | 144 | 0 | 0 | 0.5 | 144 | 0 | 0 | 0 | 0
Disposition of deviation requests and non-conformances | 4 | hrs/wk | 36 | 144 |  | 1 | 0.25 | 36 | 0 | 0 | 0.75 | 108 | 0 | 0 | 0 | 0
subtotal |  |  |  | 528 |  |  |  | 228 |  | 0 |  | 300 |  | 0 |  | 0
Schedule assumptions | start | duration (weeks) | end
Bid and award | 2002-10-29 | 12 | 2003-01-21
Winding form manufacture | 2003-01-21 | 36 | 2003-09-30
Notes and worksheets
Engineering Design
Pro-E models | 6 | models required to conceptually define all castings and hardware prior to ordering two types
assy dwgs | 6 | drawings of shell structure
Detail drawings | 24 | drawings of winding forms, bolts, shims etc.
installation dwg | 0
cooling schematic | 0
electrical schematic | 0
I&C schematic | 0
special analysis | 0
procurement specifications | 1 | specification for winding form
vendor shop drawings | 0 | included in quote for R&D castings
vendor part programming | 0 | included in quote for R&D castings
vendor misc engineering | 0 | included in quote for R&D castings
preliminary and final design reviews | 1 | one review of spec, plan, parts
meetings/reporting/presentations | 20%
Cast and machined winding forms
Cost developed as composite input from several vendors via manufacturing study subcontracts
| Composite Cost Estimate |  |  | vendor 1 |  |  | vendor 2
| (FY-02$) | ($) |  | (FY-02$) |  |  | (FY-02$)
Total for 2 coil forms, 2 vendors | 1175000
0
R&D Schedule | 14 months | 12 months |  | 13 months |  |  | 14 months
|  |  |  | 558000 |  |  | 500000
|  |  |  | 109335.6 |  |  | 5412
|  |  |  | 125096.4 |  |  | 90406.8
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0
|  |  |  | 12883.2 |  |  | 6243.6
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0
|  |  |  | 362774.05 |  |  | 555961.24
|  |  |  | 0 |  |  | 0
|  |  |  | 26555.32 |  |  | 10853.27
|  |  |  | 15888.02 |  |  | 16074
|  |  |  | 87376.65 |  |  | 33167.57
|  |  |  | 739909.24 |  |  | 739909.24
1479818.48
notes on poloidal break
G11 is key
machining
testing with Meggar tester
soaked in oils and coolant
rechecked for conductivity and size
material is stable
no size change
did not effect conductivity
good for poloidal break
should not have to change material out after machining
machining procedure:
machine locator holes on face
plunge in with end mill
saw style cutter to finish break
install g11 with shims
Formulas:
start = [no.]-[unit]*7
no. = [start, row below]

## M&S
WBS 141 Modular Coil Winding forms
Materials and Subcontracts (M&S)
Description:
This effort covers procurement of the cast and machined winding forms via fixed price subcontract. The R&D is costed separately.
[5 empty] | outside engr rate = | 120 | $ per hour
Purchased parts: |  |  |  |  | outside fab rate = | 60 | $ per hour
Coil winding forms | 4839300 | see notes below |  |  | outside inspection/technician rate = | 80 | $ per hour
subtotal, purchased parts | 4839300
Worksheet:
Cast and machined winding forms
Cost developed as composite input from two vendors
| Composite Cost Estimate |  | vendor 1 | vendor 2
| (FY-03$) | ($) | (FY-03$) | (FY-03$)
#REF!
Production castings (total for 18)
Vendor design, tooling, fixtures
Patterns
Casting
Machining
Inspection
Shipping
Production Total | 4839300 |  | 4368600 | 5310000
Production Schedule |  | 24 months | 16 months
|  | 36 months | 2004-02-01
2005-06-01
Note on C25: Bob Simmons: Assumed 2 vendors

## Fab_assy
WBS 141 Modular Coil Winding forms
In-house Fabrication and Assembly
Description:
No fabrication and assembly is associated with this WBS |  |  |  |  | Labor category
[5 empty] | total fraction | EAEM |  | EASM, EMSM |  | EMTB |  | EADM
| multiplier | unit | no. | hours |  | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
Fab operations summary
| 0 | hrs/lot | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 0 | hrs/line | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | hrs / coil | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
subtotal |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0
[5 empty] | total fraction | EAEM |  | EASM, EMSM |  | EMTB |  | EADM
Assembly operations summary | [5 empty] | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
| 0 | hr/lot | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| 0 | hr/lot | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | hr/coil | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | hours | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
subtotal |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0

## Installation
WBS 141 Modular Coil Winding forms
Installation
This element is not part of the WBS 1 scope of work