## Fab Project
WBS 163 Coil Protection System | [10 empty] | 11 |  | Duration of activity per fiscal year (weeks)
Labor
| Activity Title |  | Manhours | FY2003 $$ | Labor Type | Start Date Month/Yr | End Date Month/Yr | Comments |  |  |  | duration (weeks) | 2002-10-01 | 2003-10-01 | 2004-10-01 | 2005-10-01 | 2006-10-01 | 2007-10-01 | 2008-10-01
Preliminary Design (Title I)
|  | ( 50% of design schedule) | 0 |  | EAEM | 2006-03-22 | 2006-05-03 | PPPL Engineer |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0 |  | 50 | 50% | of design is preliminary design
|  |  | 0 |  | EADM | 2006-03-22 | 2006-05-03 | PPPL Designer |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | 82 |  | ORNL Eng | 2006-03-22 | 2006-05-03 | Composite of ORNL Engineer / Designer |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | 80 |  | ORNL Phys. | 2006-03-22 | 2006-05-03 | Composite of ORNL Physics / scientific |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | 80 |  | PPPL Phys. | 2006-03-22 | 2006-05-03 | PPPL Physics/scientific |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
Final Design (Title II)
|  | ( 50% of design schedule) | 0 |  | EAEM | 2006-05-03 | 2006-06-14 | PPPL Engineer |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0 |  | 50 | 50% | of design schedule is final design
|  |  | 0 |  | EADM | 2006-05-03 | 2006-06-14 | PPPL Designer |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | 82 |  | ORNL Eng | 2006-05-03 | 2006-06-14 | Composite of ORNL Engineer / Designer |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | 80 |  | ORNL Phys. | 2006-05-03 | 2006-06-14 | Composite of ORNL Physicist |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | 80 |  | PPPL Phys. | 2006-05-03 | 2006-06-14 | PPPL Physics/scientific |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
Lab R&D labor
|  |  | 0 |  | EAEM | 2006-03-22 | 2006-05-03 | PPPL Engineer |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | 0 |  | EADM | 2006-03-22 | 2006-05-03 | PPPL Designer |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | 0 |  | ORNL Eng | 2006-03-22 | 2006-05-03 | Composite of ORNL Engineer / Designer |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | 0 |  | EASM | 2006-03-22 | 2006-05-03 | PPPL monthly support |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | 0 |  | EMTB | 2006-03-22 | 2006-05-03 | PPPL Technician |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
Lab Fab/Assembly/Installation (Title III)
|  |  | 0 |  | EAEM | 2006-06-14 | 2006-11-01 | PPPL Engineer |  |  |  | 20 | 0 | 0 | 0 | 15.5714 | 4.4286 | 0
|  |  | 0 |  | EADM | 2006-06-14 | 2006-11-01 | PPPL Designer |  |  |  | 20 | 0 | 0 | 0 | 15.5714 | 4.4286 | 0
|  |  | 0 |  | ORNL Eng | 2006-06-14 | 2006-11-01 | Composite of ORNL Engineer / Designer |  |  |  | 20 | 0 | 0 | 0 | 15.5714 | 4.4286 | 0
|  |  | 0 |  | EASM | 2006-06-14 | 2006-11-01 | PPPL monthly support |  |  |  | 20 | 0 | 0 | 0 | 15.5714 | 4.4286 | 0
|  |  | 0 |  | EMTB | 2006-06-14 | 2006-11-01 | PPPL Technician |  |  |  | 20 | 0 | 0 | 0 | 15.5714 | 4.4286 | 0
Labor
Manhours per fiscal year by labor category
Level of Effort |  |  |  | FY2003 | FY2004 | FY2005 | FY2006 | FY2007 | FY2008 | TOTAL
| PPPL Engineer |  | EAEM | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 153 | per hour
| PPPL Designer |  | EADM | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 100 | per hour
| Composite of ORNL Engineer / Designer |  | ORNL Eng | 0 | 0 | 0 | 164 | 0 | 0 | 164 |  | 21320 | 130 | per hour
| PPPL monthly support |  | EASM | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 100 | per hour
| PPPL Technician |  | EMTB | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 73 | per hour
| Composite of ORNL Physics / scientific |  | ORNL Phy | 0 | 0 | 0 | 160 | 0 | 0 | 160 |  | 25600 | 160 | per hour
| PPPL Physics/scientific |  | PPPL Phy | 0 | 0 | 0 | 160 | 0 | 0 | 160 |  | 22560 | 141 | per hour
[12 empty] | 160 | 22560 | PPPL
[12 empty] | 324 | 46920 | ORNL
M&S Costs
| Activity Title |  |  | FY2003 $$ |  | Comment
Manufacturing Development (R&D)
|  | Purchased Design Services |  | 0
|  | Procured Hardware/Material |  | 0
|  | Profit at 10% |  | 0
|  | total, manf/dev (R&D) |  | 0 |  | w/o G&A
Procured Hardware/Material
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | materials for in-house fab |  | 0
|  | subtotal, purchased parts |  | 0
|  | Profit at 10% |  | 0
|  | total, procured hdwe/matl. |  | 0 |  | w/o G&A
| Purchased Design Services |  |  | 0 |  | no purchased services anticipated
| Procured Installation/Assembly Costs |  |  | 0 |  | All installation and assembly costs are included in WBS 7
Other Costs
| Activity Title |  |  | FY2003 $$ |  | Comment
| Travel |  |  | 0 |  | No travel is anticipated for this WBS
Summary Costs
| Activity Title |  | Manhours | FY2003 $$ |  | Comment
Labor
| PPPL Effort |  | 160 | 22560 |  | Assumed rates: |  | EASM | 100 $/hr
| ORNL effort |  | 324 | 46920 |  | EAEM | 153 $/hr | EMTB | 73 $/hr
|  | subtotal, labor | 484 | 69480 |  | EADM | 100 $/hr | PPPL Phys | 141 $/hr
[6 empty] | ORNL Eng | 130 $/hr | ORNL Phys | 160 $/hr
M&S, Other
| Manufacturing Development (R&D) |  |  | 0
| Procured Hardware/Material |  |  | 0
| Purchased Design Services |  |  | 0
| Procured Installation/Assembly Costs |  |  | 0
| Travel |  |  | 0
|  | subtotal, M&S |  | 0
| G&A |  |  | 0 |  | 25% | on all purchased materials, subcontracts, travel
| Subtotal without contingency |  |  | 69480
| Contingency |  |  | 19454.4 |  | 28% | Overall on this WBS
| Total cost |  |  | 88934.4

## Other Costs
|  | 1808-NCSX-1101 | [5 empty] | XX represents the 2 digit WBS code
| Activity Title |  | Manhours | FY2002 $$ | Labor Type | Start Date Month/Year | End Date Month/Year | Comments
Level of Effort | [7 empty] | Research Prep Activities
FY2003
[5 empty] | RMRM3 |  |  | SAMPLE - Put in specific labor type
[5 empty] | FCEM |  |  | SAMPLE - Put in specific labor type
FY2004
FY2005
FY2006
FY2007
Research Planning/Preparations
FY2003
[5 empty] | RMRM3 |  |  | SAMPLE - Put in specific labor type
[5 empty] | FCEM |  |  | SAMPLE - Put in specific labor type
FY2004
FY2005
FY2006
FY2007
Operational Spares
M&S Costs
Manufacturing Development
Purchased Design Services
|  | Procured Hardware/Material | [5 empty] | Include any M&S carried over from FY2002
| Procured Hardware/Material | [6 empty] | Identify each procurement over $100K individually
Purchased Design Services
Procured Installation/Assembly Costs
Other Costs
Travel
FY2003
[5 empty] | RMRM3 |  |  | SAMPLE - Put in specific labor type
[5 empty] | FCEM |  |  | SAMPLE - Put in specific labor type
FY2004
FY2005
FY2006
FY2007
Allocations (WBS 81 only)
Instructions for Completing Form
(1) One form for each 3 digit WBS element (e.g., 111, 121, 452, etc.) => if no 3 digit WBS, use 2 digit WBS (e.g., 81, 82, 84)
(2) For Lab labor, provide estimate in manhours => provide estimate by specific labor type.
(3) For M&S, provide estimate in FY2002 direct dollars if procured by PPPL, or in fully loaded dollars if procured by ORNL
(4) Start and end date provided in month/year format => March/2003

## Engr
WBS 163 Coil Protection System
Engineering, Title I, II and III
Description:
This effort covers all Title I, II, and III engineering for the Coil Protection System. No hardware is anticipated for this job, only design interface with WBS 4 and 5. |  |  |  |  | Labor category
[5 empty] | total fraction | EAEM |  | EADM |  | ORNL Eng |  | ORNL Physics |  | PPPL Physics
| multiplier | unit | no. | hours |  | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
Title I, II design
Pro-E models | 8 | hrs/model | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
assy dwgs | 24 | hrs/dwg | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
Detail drawings | 16 | hrs/dwg | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
installation dwg | 16 | hrs/dwg | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
cooling schematic | 0 | hrs/dwg | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
electrical schematic | 8 | hrs/dwg | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
I&C schematic | 20 | hrs/dwg | 4 | 80 | 1 | 0 | 0 | 0 | 0 | 1 | 80 | 0 | 0 | 0 | 0
stress analysis | 0 | hrs/calc | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
thermal analysis | 24 | hrs/calc | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
special analysis | 160 | hrs/calc | 2 | 320 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 160 | 0.5 | 160
procurement specifications | 16 | hrs/spec | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
preliminary and final design reviews | 40 | hrs/rev | 1 | 40 | 1 | 0 | 0 | 0 | 0 | 1 | 40 | 0 | 0 | 0 | 0
meetings/reporting/presentations | 10% | % of tot | 440 | 44 | 1 | 0 | 0 | 0 | 0 | 1 | 44 | 0 | 0 | 0 | 0
subtotal |  |  |  | 484 |  |  | 0 |  | 0 |  | 164 |  | 160 |  | 160
[5 empty] | total fraction | EAEM |  | EASM |  | EADM |  | ORNL Eng
Title III | [5 empty] | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
vendor oversight, inspection | 0 | hrs/lot | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
in-house fab/assy oversight and inspection | 0 | hrs/wk | 4 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
Disposition of deviation requests and non-conformances | 0 | hrs/wk | 20 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
As-built drawings | 0 | hrs/dwg | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Installation oversight and inspection | 0 | hrs/wk | 4 | 0 | 1 | 0.25 | 0 | 0.75 | 0 | 0 | 0 | 0 | 0
subtotal |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0
Schedule assumptions | start | duration (weeks) | end
Title I Design, R&D | 2006-03-22 | 6 | 2006-05-03
Title II Design | 2006-05-03 | 6 | 2006-06-14
Procurement | 2006-06-14 | 12 | 2006-09-06
In-house fab / sub-assy | 2006-09-06 | 4 | 2006-10-04
Installation / final assembly | 2006-10-04 | 4 | 2006-11-01
Notes and worksheets
Pro-E models
assy dwgs
Detail drawings
installation dwg
cooling schematic
electrical schematic
I&C schematic | 4 | minimum of one schematic for each signal type
stress analysis
thermal analysis
special analysis | 2 | analysis of potential fault conditions based on reaction times of various systems
specification of correct current, voltage, strain, and temperature waveforms to be compared with actual
procurement specifications
preliminary and final design reviews | 1
meetings/reporting/presentations
Formulas:
multiplier = [no.]-[unit]*7
no. = [multiplier, row below]

## R&D
WBS 163 Coil Protection System
R&D
Description:
No R&D is anticipated for this WBS element
Summary
Purchased Design Services | 0 | w/o G&A
design rate | 120 | per hour
Procured Hardware/Material | 0 | w/o G&A
fab rate | 60 | per hour
inspection/technician rate | 80 | per hour |  |  | Labor category
R&D design | [5 empty] | total fraction | EAEM |  | EADM |  | ORNL Eng |  | EASM |  | Vendor
|  | unit | no. | hours |  |  | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
Task
Pro-E models | 0 | hrs/model | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
assy dwgs | 0 | hrs/dwg | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
Detail drawings | 0 | hrs/dwg | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
installation dwg | 0 | hrs/dwg | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
cooling schematic | 0 | hrs/dwg | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
electrical schematic | 0 | hrs/dwg | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
I&C schematic | 0 | hrs/dwg | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
special analysis | 0 | hrs/calc | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
procurement specifications | 8 | hrs/spec | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
vendor shop drawings | 0 | hrs/dwg | 0 | 0 |  | 1 | [8 empty] | 1 | 0
vendor part programming | 0 | hrs/model | 0 | 0 |  | 1 | [8 empty] | 1 | 0
vendor misc engineering | 20% | % of tot | 0 | 0 |  | 1 | [8 empty] | 1 | 0
preliminary and final design reviews | 0 | hrs/rev | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
meetings/reporting/presentations | 10% | % of tot | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
subtotal |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
[5 empty] | total fraction |  | EAEM |  | EADM |  | ORNL Eng |  | EASM |  | EMTB
[7 empty] | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
R&D Title III
vendor oversight, inspection | 0 | hrs/wk | 4 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
in-house fab/assy, oversight, and inspection | 0 | hrs/wk | 4 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
Testing and experiments | 0 | hrs/wk | 1 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
subtotal |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Schedule assumptions | start | duration (weeks) | end
R&D planning | 2006-03-11 | 4 | 2006-04-08
Bid and award | 2006-04-08 | 2 | 2006-04-22
R&D procurement / in-house fab. | 2006-04-22 | 4 | 2006-04-26
R&D testing | 2006-04-26 | 1 | 2006-05-03
Notes and worksheets
Formulas:
start = [no.]-[unit]*7
start = [no.]-[unit]
no. = [start, row below]

## M&S
WBS 163 Coil Protection System
Materials and Subcontracts (M&S)
Description:
No materials or subcontracts are anticipated for this WBS element
Assumptions:
outside engr rate = | 120 | $ per hour
outside fab rate = | 60 | $ per hour
outside inspection/technician rate = | 80 | $ per hour
Purchased parts:
subtotal, purchased parts | 0
Purchased materials for in-house fabrication and sub-assembly
None required | 0
subtotal purchased materials | 0

## Fab_assy
WBS 163 Coil Protection System
In-house Fabrication and Assembly
Description:
No local fab or assembly is anticipated for the Coil leads. Installation is part of WBS 7. |  |  |  |  | Labor category
[5 empty] | total fraction | EAEM |  | EASM |  | EMTB |  | ORNL Eng
| multiplier | unit | no. | hours |  | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
Fab operations
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
none anticipated | 0 | hrs/tile | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
subtotal |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0
[5 empty] | total fraction | EAEM |  | EASM |  | EMTB |  | ORNL Eng
Assembly operations | [5 empty] | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
none anticipated |  | man/shift |  | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
|  | man/shift |  | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
|  | man/shift |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | man/shift |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
subtotal |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0
Schedule assumptions | start | duration (weeks) | end
Title I Design, R&D | 2006-03-22 | 6 | 2006-05-03
Title II Design | 2006-05-03 | 6 | 2006-06-14
Procurement | 2006-06-14 | 12 | 2006-09-06
In-house fab / sub-assy | 2006-09-06 | 4 | 2006-10-04
Installation / final assembly | 2006-10-04 | 4 | 2006-11-01
Notes and worksheets

## Installation
WBS 163 Coil Protection System
Installation
This element is not part of the WBS 1 scope of work