## Fab Project
WBS 185 Assembly of Field Periods | [10 empty] | 17 |  | Duration of activity per fiscal year (weeks)
Labor
| Activity Title |  | Manhours | FY2003 $$ | Labor Type | Start Date Month/Yr | End Date Month/Yr | Comments |  |  |  | duration (weeks) | 2002-10-01 | 2003-10-01 | 2004-10-01 | 2005-10-01 | 2006-10-01 | 2007-10-01 | 2008-10-01
Preliminary Design (Title I)
|  | ( 44% of design schedule) | 0 |  | EAEM | 2003-04-01 | 2003-11-01 | PPPL Engineer |  |  |  | 30.5714 | 26.1429 | 4.4286 | 0 | 0 | 0 | 0 |  | 43.8525 | 43.85% | of design is preliminary design
|  |  | 0 |  | EADM | 2003-04-01 | 2003-11-01 | PPPL Designer |  |  |  | 30.5714 | 26.1429 | 4.4286 | 0 | 0 | 0 | 0
|  |  | 0 |  | ORNL Eng | 2003-04-01 | 2003-11-01 | Composite of ORNL Engineer / Designer |  |  |  | 30.5714 | 26.1429 | 4.4286 | 0 | 0 | 0 | 0
|  |  | 0 |  | ORNL Phys. | 2003-04-01 | 2003-11-01 | Composite of ORNL Physics / scientific |  |  |  | 30.5714 | 26.1429 | 4.4286 | 0 | 0 | 0 | 0
|  |  | 0 |  | PPPL Phys. | 2003-04-01 | 2003-11-01 | PPPL Physics/scientific |  |  |  | 30.5714 | 26.1429 | 4.4286 | 0 | 0 | 0 | 0
Final Design (Title II)
|  | ( 56% of design schedule) | 0 |  | EAEM | 2003-11-01 | 2004-08-01 | PPPL Engineer |  |  |  | 39.1429 | 0 | 39.1429 | 0 | 0 | 0 | 0 |  | 56.1475 | 56.15% | of design schedule is final design
|  |  | 0 |  | EADM | 2003-11-01 | 2004-08-01 | PPPL Designer |  |  |  | 39.1429 | 0 | 39.1429 | 0 | 0 | 0 | 0
|  |  | 0 |  | ORNL Eng | 2003-11-01 | 2004-08-01 | Composite of ORNL Engineer / Designer |  |  |  | 39.1429 | 0 | 39.1429 | 0 | 0 | 0 | 0
|  |  | 0 |  | ORNL Phys. | 2003-11-01 | 2004-08-01 | Composite of ORNL Physicist |  |  |  | 39.1429 | 0 | 39.1429 | 0 | 0 | 0 | 0
|  |  | 0 |  | PPPL Phys. | 2003-11-01 | 2004-08-01 | PPPL Physics/scientific |  |  |  | 39.1429 | 0 | 39.1429 | 0 | 0 | 0 | 0
Lab R&D labor
|  |  | 0 |  | EAEM | 2003-04-01 | 2003-11-01 | PPPL Engineer |  |  |  | 30.5714 | 26.1429 | 4.4286 | 0 | 0 | 0 | 0
|  |  | 0 |  | EADM | 2003-04-01 | 2003-11-01 | PPPL Designer |  |  |  | 30.5714 | 26.1429 | 4.4286 | 0 | 0 | 0 | 0
|  |  | 0 |  | ORNL Eng | 2003-04-01 | 2003-11-01 | Composite of ORNL Engineer / Designer |  |  |  | 30.5714 | 26.1429 | 4.4286 | 0 | 0 | 0 | 0
|  |  | 0 |  | EASM | 2003-04-01 | 2003-11-01 | PPPL monthly support |  |  |  | 30.5714 | 26.1429 | 4.4286 | 0 | 0 | 0 | 0
|  |  | 0 |  | EMTB | 2003-04-01 | 2003-11-01 | PPPL Technician |  |  |  | 30.5714 | 26.1429 | 4.4286 | 0 | 0 | 0 | 0
Lab Fab/Assembly/Installation (Title III)
|  |  | 21 |  | EAEM | 2004-07-01 | 2006-10-01 | PPPL Engineer |  |  |  | 117.4286 | 0 | 13.1429 | 52.1429 | 52.1429 | 0 | 0
|  |  | 0 |  | EADM | 2004-07-01 | 2006-10-01 | PPPL Designer |  |  |  | 117.4286 | 0 | 13.1429 | 52.1429 | 52.1429 | 0 | 0
|  |  | 0 |  | ORNL Eng | 2004-07-01 | 2006-10-01 | Composite of ORNL Engineer / Designer |  |  |  | 117.4286 | 0 | 13.1429 | 52.1429 | 52.1429 | 0 | 0
|  |  | 4194 |  | EASM | 2004-07-01 | 2006-10-01 | PPPL monthly support |  |  |  | 117.4286 | 0 | 13.1429 | 52.1429 | 52.1429 | 0 | 0
|  |  | 10899 |  | EMTB | 2004-07-01 | 2006-10-01 | PPPL Technician |  |  |  | 117.4286 | 0 | 13.1429 | 52.1429 | 52.1429 | 0 | 0
Labor | [11 empty] | R&D labor cost = |  | 0
[12 empty] | total R&D costs |  | 0
Manhours per fiscal year by labor category
Level of Effort |  |  |  | FY2003 | FY2004 | FY2005 | FY2006 | FY2007 | FY2008 | TOTAL
| PPPL Engineer |  | EAEM | 0 | 2.3504 | 9.3248 | 9.3248 | 0 | 0 | 21 |  | 3213 | 153 | per hour
| PPPL Designer |  | EADM | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 100 | per hour
| Composite of ORNL Engineer / Designer |  | ORNL Eng | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 130 | per hour
| PPPL monthly support |  | EASM | 0 | 469.4015 | 1862.2993 | 1862.2993 | 0 | 0 | 4194 |  | 419400 | 100 | per hour
| PPPL Technician |  | EMTB | 0 | 1219.8394 | 4839.5803 | 4839.5803 | 0 | 0 | 10899 |  | 795627 | 73 | per hour
| Composite of ORNL Physics / scientific |  | ORNL Phy | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 160 | per hour
| PPPL Physics/scientific |  | PPPL Phy | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 141 | per hour
[12 empty] | 15114 | 1218240 | PPPL
[12 empty] | 0 | 0 | ORNL
M&S Costs
| Activity Title |  |  | FY2003 $$ |  | Comment
Manufacturing Development (R&D)
|  | Purchased Design Services |  | 0
|  | Procured Hardware/Material |  | 0
|  | Profit |  | 0 |  | profit already included in these items
|  | total, manf/dev (R&D) |  | 0 |  | w/o G&A
Procured Hardware/Material
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | subtotal, purchased parts |  | 0
|  | Profit at 10% |  | 0
|  | total, procured hdwe/matl. |  | 0 |  | w/o G&A
| Purchased Design Services |  |  | 0 |  | no purchased services anticipated
| Procured Installation/Assembly Costs |  |  | 0 |  | All installation and assembly costs are included in WBS 7
Other Costs
| Activity Title |  |  | FY2003 $$ |  | Comment
| Travel |  |  | 0 |  | travel related to this task is in WBS 181
Summary Costs
| Activity Title |  | Manhours | FY2003 $$ |  | Comment
Labor
| PPPL Effort |  | 15114 | 1218240 |  | Assumed rates: |  | EASM | 100 $/hr
| ORNL effort |  | 0 | 0 |  | EAEM | 153 $/hr | EMTB | 73 $/hr
|  | subtotal, labor | 15114 | 1218240 |  | EADM | 100 $/hr | PPPL Phys | 141 $/hr
[6 empty] | ORNL Eng | 130 $/hr | ORNL Phys | 160 $/hr
M&S, Other
| Manufacturing Development (R&D) |  |  | 0
| Procured Hardware/Material |  |  | 0
| Purchased Design Services |  |  | 0
| Procured Installation/Assembly Costs |  |  | 0
| Travel |  |  | 0
|  | subtotal, M&S |  | 0
| G&A |  |  | 0 |  | 25% | on all purchased materials, subcontracts, travel
| Subtotal without contingency |  |  | 1218240
| Contingency |  |  | 487296 |  | 40% | Overall on this WBS
| Total cost |  |  | 1705536

## Other Costs
|  | 1808-NCSX-1701 | [5 empty] | XX represents the 2 digit WBS code
| Activity Title |  | Manhours | FY2002 $$ | Labor Type | Start Date Month/Year | End Date Month/Year | Comments
Level of Effort | [7 empty] | Research Prep Activities
FY2003
[5 empty] | RMRM3 |  |  | SAMPLE - Put in specific labor type
[5 empty] | FCEM |  |  | SAMPLE - Put in specific labor type
FY2004
FY2005
FY2006
FY2007
Research Planning/Preparations
FY2003
[5 empty] | RMRM3 |  |  | SAMPLE - Put in specific labor type
[5 empty] | FCEM |  |  | SAMPLE - Put in specific labor type
FY2004
FY2005
FY2006
FY2007
Operational Spares
M&S Costs
Manufacturing Development
Purchased Design Services
|  | Procured Hardware/Material | [5 empty] | Include any M&S carried over from FY2002
| Procured Hardware/Material | [6 empty] | Identify each procurement over $100K individually
Purchased Design Services
Procured Installation/Assembly Costs
Other Costs
Travel
FY2003
[5 empty] | RMRM3 |  |  | SAMPLE - Put in specific labor type
[5 empty] | FCEM |  |  | SAMPLE - Put in specific labor type
FY2004
FY2005
FY2006
FY2007
Allocations (WBS 81 only)
Instructions for Completing Form
(1) One form for each 3 digit WBS element (e.g., 111, 121, 452, etc.) => if no 3 digit WBS, use 2 digit WBS (e.g., 81, 82, 84)
(2) For Lab labor, provide estimate in manhours => provide estimate by specific labor type.
(3) For M&S, provide estimate in FY2002 direct dollars if procured by PPPL, or in fully loaded dollars if procured by ORNL
(4) Start and end date provided in month/year format => March/2003

## Engr
WBS 185 Assembly of Field Periods
Engineering, Title I, II and III
Description:
Engineering for this effort is covered under WBS 181 |  |  |  |  | Labor category
[5 empty] | total fraction | EAEM |  | EADM |  | ORNL Eng |  | ORNL Physics |  | PPPL Physics
| multiplier | unit | no. | hours |  | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
Title I, II design
Pro-E models (avg) | 8 | hrs/model | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
assy dwgs | 40 | hrs/dwg | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
Detail drawings | 20 | hrs/dwg | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
installation dwg | 40 | hrs/dwg | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
cooling schematic | 20 | hrs/dwg | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
electrical schematic | 20 | hrs/dwg | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
I&C schematic | 20 | hrs/dwg | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
stress analysis | 40 | hrs/calc | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
thermal analysis | 40 | hrs/calc | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
special analysis (electromagnetics) | 160 | hrs/calc | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
procurement/fab specifications | 160 | hrs/spec | 0 | 0 | 1 | 0.75 | 0 | 0 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0
preliminary and final design reviews | 80 | hrs/rev | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
meetings/reporting/presentations | 10% | % of tot | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
subtotal |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
[5 empty] | total fraction | EAEM |  | EASM |  | EADM |  | ORNL Eng
Title III | [5 empty] | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
vendor oversight, inspection | 0 | hrs/wk | 22.1429 | 0 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0
Disposition of deviation requests and non-conformances | 0 | hrs/wk | 147.1429 | 0 | 1 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0.8 | 0
As-built drawings | 0 | hrs/dwg | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Installation oversight and inspection | 0 | hrs/wk | 52.5714 | 0 | 1 | 0.25 | 0 | 0.75 | 0 | 0 | 0 | 0 | 0
subtotal |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0
Schedule assumptions | start | duration (weeks) | end
Title I Design | 2003-04-01 | 30.5714 | 2003-11-01
Title II Design | 2003-11-01 | 39.1429 | 2004-08-01
Procurement | 2004-07-01 | 22.1429 | 2004-12-03
In-house fab / sub-assy | 2005-01-01 | 72.4286 | 2006-05-23
Installation / final assembly | 2005-09-28 | 52.5714 | 2006-10-01
Notes and worksheets
total
Pro-E models | 0
assy dwgs | 0
Detail drawings | 0
installation dwg | 0
cooling schematic | 0
electrical schematic | 0
I&C schematic | 0
stress analysis | 0
thermal analysis | 0
special analysis | 0
procurement specifications | 0
preliminary and final design reviews | 0
meetings/reporting/presentations | 15%
Formulas:
multiplier = [no., row above]

## R&D
WBS 185 Assembly of Field Periods
R&D
Description:
No R&D is anticipated for this element
Summary
Purchased Design Services
subtotal | 0 | w/o G&A
Procured Hardware/Material
subtotal | 0 | w/o G&A
Subcontractor labor rates:
design rate: | 120 | per hour
fab rate | 60 | per hour
inspection/technician rate | 80 | per hour
Labor category
R&D design | [5 empty] | total fraction | EAEM |  | EADM |  | ORNL Eng |  | EASM |  | Vendor
|  | unit | no. | hours |  |  | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
Task
Pro-E models | 12 | hrs/model | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
assy dwgs | 20 | hrs/dwg | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
Detail drawings | 8 | hrs/dwg | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
installation dwg | 0 | hrs/dwg | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
cooling schematic | 0 | hrs/dwg | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
electrical schematic | 0 | hrs/dwg | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
I&C schematic | 0 | hrs/dwg | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
special analysis | 0 | hrs/calc | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
procurement specifications | 40 | hrs/spec | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
vendor shop drawings | 0 | hrs/dwg | 0 | 0 |  | 1 | [8 empty] | 1 | 0
vendor part programming | 0 | hrs/model | 0 | 0 |  | 1 | [8 empty] | 1 | 0
vendor misc engineering | 0% | % of tot | 0 | 0 |  | 1 | [8 empty] | 1 | 0
preliminary and final design reviews | 40 | hrs/rev | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
meetings/reporting/presentations | 20% | % of tot | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
subtotal |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
[5 empty] | total fraction |  | EAEM |  | EADM |  | ORNL Eng |  | EASM, EMSM |  | EMTB
[7 empty] | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
R&D Tasks and Title III (see notes)
| 0 | hrs | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | hrs/setup | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | hrs/setup | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | hrs / coil | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | hrs | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
subtotal |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Schedule assumptions | start | duration (weeks) | end
R&D planning | 2002-11-17 | 4 | 2002-12-15
Bid and award | 2002-12-15 | 2 | 2002-12-29
R&D procurement / in-house fab. | 2002-12-29 | 4 | 2003-01-02
R&D testing | 2003-01-02 | 52 | 2004-01-01
Notes and worksheets
Engineering Design
Pro-E models | 0
assy dwgs | 0
Detail drawings | 0
installation dwg | 0
cooling schematic | 0
electrical schematic | 0
I&C schematic | 0
special analysis | 0
procurement specifications | 0
vendor shop drawings | 0
vendor part programming | 0
vendor misc engineering | 0
preliminary and final design reviews | 0
meetings/reporting/presentations | 10%
Formulas:
start = [no.]-[unit]*7
start = [no.]-[unit]
no. = [start, row below]

## M&S
WBS 185 Assembly of Field Periods
Materials and Subcontracts (M&S)
Description:
No additional materials or supplies are required for this WBS. They are included in WBS 12, 13, 14, 15, etc.
Assumptions:
outside engr rate = | 120 | $ per hour
outside fab rate = | 60 | $ per hour
outside inspection/technician rate = | 80 | $ per hour
Purchased parts:
subtotal, purchased parts | 0
Purchased materials for in-house fabrication and sub-assembly
subtotal purchased materials | 0
Worksheet:

## Fab_assy
WBS 185 Assembly of Field Periods
In-house Fabrication and Assembly
Description:
| This effort covers all PPPL effort involved with actual assembly of the field periods, including sub-assembly of the modular coils and TF coils into partial field periods, assembling over the VV, welding the VV port extensions, etc. | [5 empty] | Labor category
[7 empty] | total fraction | EAEM |  | EASM, EMSM |  | EMTB |  | EADM
|  | multiplier | unit | no. | hours |  |  | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
Sub-assembly
| TF Coils, 3 coil assy - sr tech | 80 | per assy | 6 | 480 |  | 1 | 0 | 0 | 1 | 480 | 0 | 0 | 0 | 0
| TF Coils, 3 coil assy - tech | 320 | per assy | 6 | 1920 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1920 | 0 | 0
| pre-assemble mod coils | 210 | lot | 1 | 210 |  | 1 | 0.1 | 21 | 0.2 | 42 | 0.7 | 147 | 0 | 0
| Mod Coils, 3 coil assy, sr tech. machinist, first assy | 168 | per assy | 1 | 168 |  | 1 | 0 | 0 | 1 | 168 | 0 | 0 | 0 | 0
| Mod coils, 3 coil assy, tech, first assy | 360 | per assy | 1 | 360 |  | 1 | 0 | 0 | 0 | 0 | 1 | 360 | 0 | 0
| Mod Coils, 3 coil assy, sr tech, machinist | 144 | per assy | 5 | 720 |  | 1 | 0 | 0 | 1 | 720 | 0 | 0 | 0 | 0
| Mod coils, 3 coil assy, tech | 288 | per assy | 5 | 1440 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1440 | 0 | 0
| subtotal |  |  |  | 5298 |  |  |  | 21 |  | 1410 |  | 3867 |  | 0
[7 empty] | total fraction | EAEM |  | EASM, EMSM |  | EMTB |  | EADM
| Field period assembly | [6 empty] | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
| assemble mod coils to VV, sr. tech, machinist | 240 | per assy | 3 | 720 |  | 1 | 0 | 0 | 1 | 720 | 0 | 0 | 0 | 0
| assemble mod coils to VV, tech | 800 | per assy | 3 | 2400 |  | 1 | 0 | 0 | 0 | 0 | 1 | 2400 | 0 | 0
| assembly TF coils to VV, sr tech, machinist | 136 | per assy | 3 | 408 |  | 1 | 0 | 0 | 1 | 408 | 0 | 0 | 0 | 0
| assembly TF coils to VV, tech | 384 | per assy | 3 | 1152 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1152 | 0 | 0
| weld VV port assemblies, sr tech, machinist | 240 | per assy | 3 | 720 |  | 1 | 0 | 0 | 1 | 720 | 0 | 0 | 0 | 0
| weld VV port assemblies, tech | 240 | per assy | 3 | 720 |  | 1 | 0 | 0 | 0 | 0 | 1 | 720 | 0 | 0
| Bakeout and leak check, sr tech, machinist | 128 | per assy | 3 | 384 |  | 1 | 0 | 0 | 1 | 384 | 0 | 0 | 0 | 0
| Bakeout and leak check, tech | 304 | per assy | 3 | 912 |  | 1 | 0 | 0 | 0 | 0 | 1 | 912 | 0 | 0
| install external trim coils, sr tech, machinist | 120 | per assy | 3 | 360 |  | 1 | 0 | 0 | 1 | 360 | 0 | 0 | 0 | 0
| install external trim coils, tech | 360 | per assy | 3 | 1080 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1080 | 0 | 0
| ship to test cell, sr tech, machinist | 64 | per assy | 3 | 192 |  | 1 | 0 | 0 | 1 | 192 | 0 | 0 | 0 | 0
| ship to test cell, tech | 256 | per assy | 3 | 768 |  | 1 | 0 | 0 | 0 | 0 | 1 | 768 | 0 | 0
| subtotal |  |  |  | 9816 |  |  |  | 0 |  | 2784 |  | 7032 |  | 0
| Schedule assumptions | start | duration (weeks) | end
| Title I Design, R&D | 2003-12-19 | 30.5714 | 2004-07-20
| Title II Design | 2004-07-20 | 39.1429 | 2005-04-20
| Procurement | 2005-04-20 | 22.1429 | 2005-09-22
| In-house fab / sub-assy | 2005-09-22 | 38.1429 | 2006-06-16
| Installation / final assembly | 2005-03-04 | 67 | 2006-06-16
Notes and worksheets
Field Period Assembly Area Preparation
Ref J. Chrzanowski spreadsheet, April 2003
This proposal includes the costs associated with the fabrication of (18) Modular coils for the NCSX Machine.
This includes inspection of the conductor and castings, coil winding, VPI and Testing activities.
Activity |  | Duration | Start | End | HP | Safety | IH | QC | EAEM | EADM | EMSM | EMSM | EMTB | M&S | M&S
| Activity Description | [7 empty] | Engr | Designer | Sr. Lab | machinist | Tech
ID |  | Days |  |  | hours | hours | hours | hours | hours | hours | hours | hours | hours | w/o G&A | w/G&A
Notes: A number of activities can be performed in parallel and are not
series activities during the field period assemblies.
a) The TF coil sub-assembly
b) The sub-assembly of the modular coils
c) Preparation of the vacuum vessel for assembly
XXXX | Sub-assembly of TF Coils
1) Task involves assemblying together (3) TF coils and structure to form
a TF coil set
2) TF coil sets are required per Field Period Assembly
P1- ? | Assemble (3) TF coils and structure- Right side Field Period #1 | 10 | [8 empty] | 80 |  | 320
P1- ? | Assemble (3) TF coils and structure- Left side Field Period #1 | 10 | [8 empty] | 80 |  | 320
P1- ? | Assemble (3) TF coils and structure- Right side Field Period #2 | 10 | [8 empty] | 80 |  | 320
P1- ? | Assemble (3) TF coils and structure- Left side Field Period #2 | 10 | [8 empty] | 80 |  | 320
P1- ? | Assemble (3) TF coils and structure- Right side Field Period #3 | 10 | [8 empty] | 80 |  | 320
P1- ? | Assemble (3) TF coils and structure- Left side Field Period #3 | 10 | [8 empty] | 80 |  | 320
XXXX | Sub-assembly of Modular Coils
1) Task involves the mounting and aligning of (3) modular coils to form
a coil set [M1, M2, M3].
2) Two complete coil sets are required per complete Field Period Assy.
P1-?? | FP#1 Mount and align right side modular coils in sub-assy fixture | 15 | 2005-08-31 | 2005-09-21
| Install first M1 coil in frame | 2 | [8 empty] | 16 | 0 | 48
| Install M2 coil and align to M1 | 8 | [8 empty] | 64 | 24 | 192
| Install M3 coil and align to M1 and M2 | 5 | 2005-09-15 | [7 empty] | 40 | 24 | 120
Ready for installation
P1-?? | FP#1 Mount and align left side modular coils in sub-assy fixture | 12 | 2005-09-28 | 2005-10-13
| Install first M1 coil in frame | 2 | [8 empty] | 16 |  | 48
| Install M2 coil and align to M1 | 5 | [8 empty] | 40 | 24 | 120
| Install M3 coil and align to M1 and M2 | 5 | 2006-10-07 | [7 empty] | 40 | 24 | 120
Ready for installation
P1-?? | FP#2 Mount and align right side modular coils in sub-assy fixture | 12 | 2005-10-20 | 2005-11-04
| Install first M1 coil in frame | 2 | [8 empty] | 16 |  | 48
| Install M2 coil and align to M1 | 5 | [8 empty] | 40 | 24 | 120
| Install M3 coil and align to M1 and M2 | 5 | 2005-10-31 | [7 empty] | 40 | 24 | 120
Ready for installation
P1-?? | FP#2 Mount and align right side modular coils in sub-assy fixture | 12 | 2005-11-11 | 2005-11-30
| Install first M1 coil in frame | 2 | [8 empty] | 16 |  | 48
| Install M2 coil and align to M1 | 5 | [8 empty] | 40 | 24 | 120
| Install M3 coil and align to M1 and M2 | 5 | 2005-11-22 | [7 empty] | 40 | 24 | 120
Ready for installation
P1-?? | FP#3 Mount and align right side modular coils in sub-assy fixture | 12 | 2005-12-07 | 2005-12-22
| Install first M1 coil in frame | 2 | [8 empty] | 16 |  | 48
| Install M2 coil and align to M1 | 5 | [8 empty] | 40 | 24 | 120
| Install M3 coil and align to M1 and M2 | 5 | 2005-12-16 | [7 empty] | 40 | 24 | 120
Ready for installation
P1-?? | FP#3 Mount and align right side modular coils in sub-assy fixture | 12 | 2006-01-05 | 2006-01-20
| Install first M1 coil in frame | 2 | [8 empty] | 16 |  | 48
| Install M2 coil and align to M1 | 5 | [8 empty] | 40 | 24 | 120
| Install M3 coil and align to M1 and M2 | 5 | 2006-01-16 | [7 empty] | 40 | 24 | 120
Ready for installation
185 | Assemble Field Periods
1) Task involves assemblying the VV, Modular coils, TF coils and Trim
coils together to complete a Field Period Assembly
2) Includes the welding of VV ports, bakeout of VV and vacuum leak
testing activities
P1-??? | Assemble Field Period #1 | 37 | 2005-09-22 | 2005-12-15
| Assemble and align right side modular coils to vacuum vessel | 10 | 2005-09-22 | [7 empty] | 80 |  | 320
| Assemble and align left side modular coils to vacuum vessel | 15 | 2005-10-14 | [7 empty] | 120 | 40 | 480
| Position and align right side TF coils to FP #1 | 5 | 2005-11-15 | [7 empty] | 40 |  | 160
| Position and align left side TF coils to FP#1 | 7 | 2005-11-28 | [7 empty] | 56 | 40 | 224
P1-191 | Position and weld port assemblies | 15 | 2005-12-07 | 2006-01-03 | [6 empty] | 240 |  | 240
P1-201 | Bakeout vessel segment to 150 degrees C | 6 | 2006-01-04 | 2006-01-11 | [6 empty] | 48 |  | 144
P1-211 | Perform vacuum leak check of welded assemblies | 10 | 2006-01-12 | 2006-01-25 | [6 empty] | 80 |  | 160
P1-??? | Install external Trim coils | 15 | 2006-01-16 | 2006-02-15
Total of [8] Trim coils mounted to Modular coil shell
| Install [3] upper coils | 5 | [8 empty] | 40 |  | 120
| Install [2] Mid coils | 4 | [8 empty] | 32 |  | 96
| Install [3] lower coils | 6 | [8 empty] | 48 |  | 144
P1-221 | Prepare field period for shipment | 5 | 2006-02-16 | 2006-02-22 | [6 empty] | 40 |  | 160
P1-231 | Ship 1st. Field Period | 3 | 2006-02-23 | 2006-02-27 | [6 empty] | 24 |  | 96
P1-241 | Field period ready for installation | 1 | 2006-02-28 | 2006-02-28
P1-??? | Assemble Field Period #2 | 45 | 2005-12-07 | 2006-02-06
| Assemble and align right side modular coils to vacuum vessel | 10 | 2005-12-07 | [7 empty] | 80 |  | 320
| Assemble and align left side modular coils to vacuum vessel | 15 | 2005-12-21 | [7 empty] | 120 | 40 | 480
| Position and align right side TF coils to FP #2 | 5 | 2006-01-18 | [7 empty] | 40 |  | 160
| Position and align left side TF coils to FP#2 | 7 | 2006-01-27 | [7 empty] | 56 | 40 | 224
P1-191 | Position and weld port assemblies | 15 | 2006-02-07 | 2006-02-27 | [6 empty] | 240 |  | 240
P1-201 | Bakeout vessel segment to 150 degrees C | 6 | 2006-02-28 | 2006-03-07 | [6 empty] | 48 |  | 144
P1-211 | Perform vacuum leak check of welded assemblies | 10 | 2006-03-08 | 2006-03-21 | [6 empty] | 80 |  | 160
P1-??? | Install external Trim coils | 15 | 2006-03-22 | 2006-04-11
Total of [8] Trim coils mounted to Modular coil shell
| Install [3] upper coils | 5 | [8 empty] | 40 |  | 120
| Install [2] Mid coils | 4 | [8 empty] | 32 |  | 96
| Install [3] lower coils | 6 | [8 empty] | 48 |  | 144
P1-221 | Prepare field period for shipment | 5 | 2006-04-12 | 2006-04-18 | [6 empty] | 40 |  | 160
P1-231 | Ship 2nd. Field Period | 3 | 2006-04-19 | 2006-04-21 | [6 empty] | 24 |  | 96
P1-241 | 2nd. Field period ready for installation | 1 | 2006-04-24 | 2006-04-24
P1-??? | Assemble Field Period #3 | 37 | 2006-02-07 | 2006-03-31
| Assemble and align right side modular coils to vacuum vessel | 10 | 2006-02-07 | 2006-02-20 | [6 empty] | 80 |  | 320
| Assemble and align left side modular coils to vacuum vessel | 15 | 2006-02-21 | 2006-03-13 | [6 empty] | 120 | 40 | 480
| Position and align right side TF coils to FP #3 | 5 | 2006-03-14 | 2006-03-22 | [6 empty] | 40 |  | 160
| Position and align left side TF coils to FP#3 | 7 | 2006-03-23 | 2006-03-31 | [6 empty] | 56 | 40 | 224
P1-191 | Position and weld port assemblies | 15 | 2006-04-03 | 2006-04-21 | [6 empty] | 240 |  | 240
P1-201 | Bakeout vessel segment to 150 degrees C | 5 | 2006-04-24 | 2006-04-28 | [6 empty] | 48 |  | 144
P1-211 | Perform vacuum leak check of welded assemblies | 10 | 2006-05-01 | 2006-05-12 | [6 empty] | 80 |  | 160
P1-??? | Install external Trim coils | 15 | 2006-05-15 | 2006-06-05
Total of [8] Trim coils mounted to Modular coil shell
| Install [3] upper coils | 5 | [8 empty] | 40 |  | 120
| Install [2] Mid coils | 4 | [8 empty] | 32 |  | 96
| Install [3] lower coils | 6 | [8 empty] | 48 |  | 144
P1-221 | Prepare field period for shipment | 5 | 2006-06-06 | 2006-06-12 | [6 empty] | 40 |  | 160
P1-231 | Ship 3rd. Field Period | 3 | 2006-06-13 | 2006-06-16 | [6 empty] | 24 |  | 96
P1-241 | 3rd. Field period ready for installation | 1 | 2006-06-16 | 2006-06-16
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 3624 | 528 | 10752
|  | Rate | per Hr
|  | EM | 155
|  | SM | 101.5
|  | TB | 74
|  | DM | 101.38
Formulas:
multiplier = [no.]-[unit]*7
no. = [multiplier, row below]

## Installation
WBS 185 Assembly of Field Periods
Installation
This element is not part of the WBS 1 scope of work